## WK2 1501
WBS |  | Name Of Employee | [7 empty] | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
| Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John
1 | Meetings | [8 empty] | 16 | 8 | 100%
1.1 | Meetings | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 16 | 8 | 100%
N/A | Minutes | - | - | - | - | - | - | - | - | - | - | -
1.2 | Performance and Document reviews (QA)
2 | Documentation | [8 empty] | 4.5 | 73.6 | -93.89%
2.1 | Functional Specification | [8 empty] | 4.5 | 55 | -91.82%
2.1.1 | Functional Specification Generation | - | 2.5 | 2 | - | - | - | - | - | 4.5 | 34 | -86.76%
2.1.2 | Generate User Stories | - | - | - | - | - | - | - | - | 0 | 12 | -100%
2.1.3 | Functional Specification Compilation | - | - | - | - | - | - | - | - | 0 | 9 | -100%
2.2 | QA Manual | [8 empty] | 0 | 18 | -100%
2.2.1 | Generate QA Roles & Responsibilities | - | - | - | - | - | - | - | - | 0 | 18 | -100%
2.2.2 | Compile QA Manual | - | - | - | - | - | - | - | - | - | - | -
2.3 | Generate WBS, GANNT & PERT | - | - | - | - | - | - | - | - | - | - | -
2.4 | Generate PWS | - | - | - | - | - | - | - | - | - | - | -
2.5 | Negotiate Inter-group contracts | - | - | - | - | - | - | - | - | - | - | -
2.6 | Create tender presentation | - | - | - | - | - | - | - | - | 0 | 0.6 | -100%
2.7 | Create Product demo presentation | - | - | - | - | - | - | - | - | - | - | -
2.8 | Compile hand in document of all deliverables | - | - | - | - | - | - | - | - | - | - | -
2.9 | Give Presentation | - | - | - | - | - | - | - | - | - | - | -
3 | Finance | [8 empty] | 1 | - | N/A
3.1 | Generate Financial Business Plan | - | - | - | - | - | - | 1 | - | 1 | - | N/A
3.2 | Generate Financial Report 1 | - | - | - | - | - | - | - | - | - | - | -
3.3 | Generate Financial Report 2 | - | - | - | - | - | - | - | - | - | - | -
3.4 | Generate Financial Report 3 | - | - | - | - | - | - | - | - | - | - | -
3.5 | Generate Financial Summary Report | - | - | - | - | - | - | - | - | - | - | -
4 | Research & Design | [8 empty] | 5 | 27.75 | -81.98%
4.1 | Research & Analyze Market | - | - | - | - | - | - | - | 3 | 3 | 7.5 | -60%
4.2 | Research advertizement Revenue | - | - | - | - | - | - | 2 | - | 2 | 3 | -33.33%
4.3 | Develop Sales Strategies | - | - | - | - | - | - | - | - | - | - | -
4.4 | Design | [8 empty] | 0 | 17.25 | -100%
4.4.1 | Generate App Mockups | - | - | - | - | - | - | - | - | 0 | 11.67 | -100%
4.4.2 | Design Logo | - | - | - | - | - | - | - | - | 0 | 1.63 | -100%
4.4.3 | Create Class Diagrams | - | - | - | - | - | - | - | - | 0 | 3.97 | -100%
5 | Development | [8 empty] | 0 | - | N/A
5.1 | Source Media for App | - | - | - | - | - | - | - | - | - | - | -
5.2 | Generate Icons for App | - | - | - | - | - | - | - | - | - | - | -
5.3 | Software | [8 empty] | 0 | - | N/A
5.3.1 | GUI Development | [8 empty] | 0 | - | N/A
5.3.1.1 | Prototype GUI Development | - | - | - | - | - | - | - | - | - | - | -
5.3.1.2 | Final GUI Development | - | - | - | - | - | - | - | - | - | - | -
5.3.2 | App Development | [8 empty] | 0 | - | N/A
5.3.2.1 | Prototype App Development | - | - | - | - | - | - | - | - | - | - | -
5.3.2.2 | Final App Development | - | - | - | - | - | - | - | - | - | - | -
5.4 | Testing & Analysis | [8 empty] | 0 | - | N/A
5.4.1 | GUI Testing | - | - | - | - | - | - | - | - | - | - | -
5.4.2 | System Testing | - | - | - | - | - | - | - | - | - | - | -
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | - | - | - | - | - | -
[10 empty] | - | - | -
6 | Deliverables | [8 empty] | 0 | - | N/A
6.1 | Functional Spec to supervisor | - | - | - | - | - | - | - | - | - | - | -
6.2 | QA Manual uploaded to repository | - | - | - | - | - | - | - | - | - | - | -
6.3 | Financial Business Plan submission | - | - | - | - | - | - | - | - | - | - | -
6.4 | PWS Agreed between groups | - | - | - | - | - | - | - | - | - | - | -
6.5 | Group tender presentations | - | - | - | - | - | - | - | - | - | - | -
6.6 | Financial Report 1 sumbission | - | - | - | - | - | - | - | - | - | - | -
6.7 | All contracts agreed and filed | - | - | - | - | - | - | - | - | - | - | -
6.8 | Financial Report 2 submission | - | - | - | - | - | - | - | - | - | - | -
6.9 | First iteration complete | - | - | - | - | - | - | - | - | - | - | -
6.1 | Final test & integration plan | - | - | - | - | - | - | - | - | - | - | -
6.11 | Financial Report 3 submission | - | - | - | - | - | - | - | - | - | - | -
6.12 | Financial Summary Report submission | - | - | - | - | - | - | - | - | - | - | -
6.13 | Demonstration / Sales presentation | - | - | - | - | - | - | - | - | - | - | -
6.14 | Hand in of all deliverables | - | - | - | - | - | - | - | - | - | - | -
Total For Team | [9 empty] | 26.5 | 109.35 | -75.77%
Total Per Employee |  | 2 | 4.5 | 4 | 2 | 2 | 2 | 5 | 5 | 26.5
Forecast Per Employee |  | 6.63 | 27.3 | 22.97 | 13.67 | 4 | 10.3 | 12 | 12.5 | 109.37
Percentage Difference |  | -69.83% | -83.52% | -82.59% | -85.37% | -50% | -80.58% | -58.33% | -60% | -75.77%

## WK3 2201
|  | Name Of Employee | [7 empty] | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John
1 | Meetings | [8 empty] | 22.5 | 8
1.1 | Meetings | 3 | 3 | 3 | 2 | 2 | 3 | 2.5 | 3 | 21.5 | 8 | 168.8%
N/A | Minutes | - | 1 | - | - | - | - | - | - | 1 | - | -
1.2 | Performance and Document reviews (QA)
2 | Documentation | [8 empty] | 19.5 | 18.15 | 7.438%
2.1 | Functional Specification | [8 empty] | 11 | - | N/A
2.1.1 | Functional Specification Generation | 1 | 5 | - | - | - | - | - | - | 6 | - | N/A
2.1.2 | Generate User Stories | - | - | 5 | - | - | - | - | - | 5 | - | N/A
2.1.3 | Functional Specification Compilation | - | - | - | - | - | - | - | - | - | - | N/A
2.2 | QA Manual | [8 empty] | 8.5 | 17 | -50%
2.2.1 | Generate QA Roles & Responsibilities | 2 | 2 | 0.5 | - | 1.5 | - | 1.5 | 1 | 8.5 | 2 | 325%
2.2.2 | Compile QA Manual | - | - | - | - | - | - | - | - | 0 | 15 | -100%
N/A
2.3 | Generate WBS, GANNT & PERT | - | - | - | - | - | - | - | - | 0 | 0.55 | -100%
2.4 | Generate PWS | - | - | - | - | - | - | - | - | 0 | 0.6 | -100%
2.5 | Negotiate Inter-group contracts | - | - | - | - | - | - | - | - | - | - | N/A
2.6 | Create tender presentation | - | - | - | - | - | - | - | - | - | - | N/A
2.7 | Create Product demo presentation | - | - | - | - | - | - | - | - | - | - | N/A
2.8 | Compile hand in document of all deliverables | - | - | - | - | - | - | - | - | - | - | N/A
2.9 | Give Presentation | - | - | - | - | - | - | - | - | - | - | N/A
3 | Finance | [8 empty] | 3.5 | 22.5 | -84.44%
3.1 | Generate Financial Business Plan | - | - | - | - | - | - | 3.5 | - | 3.5 | 22.5 | -84.44%
3.2 | Generate Financial Report 1 | - | - | - | - | - | - | - | - | - | - | N/A
3.3 | Generate Financial Report 2 | - | - | - | - | - | - | - | - | - | - | N/A
3.4 | Generate Financial Report 3 | - | - | - | - | - | - | - | - | - | - | N/A
3.5 | Generate Financial Summary Report | - | - | - | - | - | - | - | - | - | - | N/A
4 | Research & Design | [8 empty] | 24 | 38.65 | -37.9%
4.1 | Research & Analyze Market | - | - | - | 0.75 | - | - | - | 4 | 4.75 | 7.5 | -36.67%
4.2 | Research advertizement Revenue | - | - | - | - | - | - | 5.75 | - | 5.75 | 3 | 91.67%
4.3 | Develop Sales Strategies | - | - | - | - | - | - | - | - | 0 | 8 | -100%
4.4 | Design | [8 empty] | 13.5 | 20.15 | -33%
4.4.1 | Generate App Mockups | - | - | - | 9.5 | 4 | - | - | - | 13.5 | 11.67 | 15.68%
4.4.2 | Design Logo | - | - | - | - | - | - | - | - | 0 | 1.88 | -100%
4.4.3 | Create Class Diagrams | - | - | - | - | - | - | - | - | 0 | 6.6 | -100%
5 | Development | [8 empty] | 1.5 |  | N/A
5.1 | Source Media for App | - | - | - | - | - | - | - | - | - | - | -
5.2 | Generate Icons for App | - | - | - | - | - | - | - | - | - | - | -
5.3 | Software | [8 empty] | 1.5 | - | N/A
5.3.1 | GUI Development | [8 empty] | 0 | - | N/A
5.3.1.1 | Prototype GUI Development | - | - | - | - | - | - | - | - | - | - | -
5.3.1.2 | Final GUI Development | - | - | - | - | - | - | - | - | - | - | -
5.3.2 | App Development | [8 empty] | 1.5 | - | N/A
5.3.2.1 | Prototype App Development | - | - | 1.5 | - | - | - | - | - | 1.5 | - | N/A
5.3.2.2 | Final App Development | - | - | - | - | - | - | - | - | - | - | -
5.4 | Testing & Analysis | [8 empty] | 0 | - | N/A
5.4.1 | GUI Testing | - | - | - | - | - | - | - | - | - | - | -
5.4.2 | System Testing | - | - | - | - | - | - | - | - | - | - | -
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | - | - | - | - | - | -
6 | Deliverables | [8 empty] | 0 | - | N/A
6.1 | Functional Spec to supervisor | - | - | - | - | - | - | - | - | - | - | -
6.2 | QA Manual uploaded to repository | - | - | - | - | - | - | - | - | - | - | -
6.3 | Financial Business Plan submission | - | - | - | - | - | - | - | - | - | - | -
6.4 | PWS Agreed between groups | - | - | - | - | - | - | - | - | - | - | -
6.5 | Group tender presentations | - | - | - | - | - | - | - | - | - | - | -
6.6 | Financial Report 1 sumbission | - | - | - | - | - | - | - | - | - | - | -
6.7 | All contracts agreed and filed | - | - | - | - | - | - | - | - | - | - | -
6.8 | Financial Report 2 submission | - | - | - | - | - | - | - | - | - | - | -
6.9 | First iteration complete | - | - | - | - | - | - | - | - | - | - | -
6.1 | Final test & integration plan | - | - | - | - | - | - | - | - | - | - | -
6.11 | Financial Report 3 submission | - | - | - | - | - | - | - | - | - | - | -
6.12 | Financial Summary Report submission | - | - | - | - | - | - | - | - | - | - | -
6.13 | Demonstration / Sales presentation | - | - | - | - | - | - | - | - | - | - | -
6.14 | Hand in of all deliverables | - | - | - | - | - | - | - | - | - | - | -
Total For Team | [9 empty] | 71
Total Per Employee |  | 6 | 11 | 10 | 12.25 | 7.5 | 3 | 13.25 | 8 | 71
Forecast Per Employee |  | 2.88 | 16.3 | 7.6 | 13.67 | 2 | 1.85 | 30.5 | 12.5 | 87.3
Percentage Difference |  | 108.3% | -32.52% | 31.58% | -10.39% | 275% | 62.16% | -56.56% | -36% | -18.67%

## WK4 2901
WBS |  | Name Of Employee | [7 empty] | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
| Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John
1 | Meetings | [8 empty] | 16.5 | 8 | 100%
1.1 | Meetings | 3 | 2 | 3 | 1 | 0 | 1 | 3 | 3 | 16 | 8 | 100%
N/A | Minutes | - | 0.5 | - | - | - | - | - | - | 0.5 | - | N/A
1.2 | Performance and Document reviews (QA)
2 | Documentation | [8 empty] | 49 | 26.75 | 83.18%
2.1 | Functional Specification | [8 empty] | 28.5 | - | N/A
2.1.1 | Functional Specification Generation | 1 | 3.5 | 0.5 | 4 | 3 | 4 | 2 | - | 18 | - | N/A
2.1.2 | Generate User Stories | - | - | 1.5 | - | - | - | - | - | 1.5 | - | N/A
2.1.3 | Functional Specification Compilation | - | 4.5 | - | - | - | 4.5 | - | - | 9 | - | N/A
2.2 | QA Manual | [8 empty] | 20.5 | - | N/A
2.2.1 | Generate QA Roles & Responsibilities | 1 | 3.5 | 2.5 | 0.75 | - | 1.25 | 4 | - | 13 | - | N/A
2.2.2 | Compile QA Manual | - | 7.5 | - | - | - | - | - | - | 7.5 | - | N/A
[11 empty] | - | N/A
2.3 | Generate WBS, GANNT & PERT | - | - | - | - | - | - | - | - | 0 | 8.35 | -100%
2.4 | Generate PWS | - | - | - | - | - | - | - | - | - | - | N/A
2.5 | Negotiate Inter-group contracts | - | - | - | - | - | - | - | - | 0 | 0.6 | -100%
2.6 | Create tender presentation | - | - | - | - | - | - | - | - | 0 | 17.8 | -100%
2.7 | Create Product demo presentation | - | - | - | - | - | - | - | - | - | - | N/A
2.8 | Compile hand in document of all deliverables | - | - | - | - | - | - | - | - | - | - | N/A
2.9 | Give Presentation | - | - | - | - | - | - | - | - | - | - | N/A
3 | Finance | [8 empty] | 18 | 22.5 | -20%
3.1 | Generate Financial Business Plan | - | - | - | - | - | - | 18 | - | 18 | 22.5 | -20%
3.2 | Generate Financial Report 1 | - | - | - | - | - | - | - | - | - | - | N/A
3.3 | Generate Financial Report 2 | - | - | - | - | - | - | - | - | - | - | N/A
3.4 | Generate Financial Report 3 | - | - | - | - | - | - | - | - | - | - | N/A
3.5 | Generate Financial Summary Report | - | - | - | - | - | - | - | - | - | - | N/A
4 | Research & Design | [8 empty] | 7.25 | 37.45 | -80.64%
4.1 | Research & Analyze Market | - | - | - | - | - | - | - | 2.5 | 2.5 | 5 | -50%
4.2 | Research advertizement Revenue | - | - | - | - | - | - | - | - | 0 | 2 | -100%
4.3 | Develop Sales Strategies | - | - | - | - | - | - | - | - | 0 | 12 | -100%
4.4 | Design | [8 empty] | 4.75 | 18.45 | -74.25%
4.4.1 | Generate App Mockups | - | - | - | 4.75 | - | - | - | - | 4.75 | 11.67 | -59.3%
4.4.2 | Design Logo | - | - | - | - | - | - | - | - | 0 | 1.5 | -100%
4.4.3 | Create Class Diagrams | - | - | - | - | - | - | - | - | 0 | 5.28 | -100%
N/A
5 | Development | [8 empty] | 8 | 13.27 | -39.71%
5.1 | Source Media for App | - | - | - | - | - | - | - | - | 0 | 0.87 | -100%
5.2 | Generate Icons for App | 8 | - | - | - | - | - | - | - | 8 | 0.75 | 966.7%
5.3 | Software | [8 empty] | 0 | 11.65 | -100%
5.3.1 | GUI Development | [8 empty] | 0 | 2.7 | -100%
5.3.1.1 | Prototype GUI Development | - | - | - | - | - | - | - | - | 0 | 2.7 | -100%
5.3.1.2 | Final GUI Development | - | - | - | - | - | - | - | - | - | - | -
5.3.2 | App Development | [8 empty] | 0 | 8.95 | -100%
5.3.2.1 | Prototype App Development | - | - | - | - | - | - | - | - | 0 | 8.95 | -100%
5.3.2.2 | Final App Development | - | - | - | - | - | - | - | - | - | - | -
5.4 | Testing & Analysis | [8 empty] | 0 | - | N/A
5.4.1 | GUI Testing | - | - | - | - | - | - | - | - | - | - | -
5.4.2 | System Testing | - | - | - | - | - | - | - | - | - | - | -
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | - | - | - | - | - | -
6 | Deliverables | [8 empty] | 0 | - | N/A
6.1 | Functional Spec to supervisor | - | - | - | - | - | - | - | - | - | - | -
6.2 | QA Manual uploaded to repository | - | - | - | - | - | - | - | - | - | - | -
6.3 | Financial Business Plan submission | - | - | - | - | - | - | - | - | - | - | -
6.4 | PWS Agreed between groups | - | - | - | - | - | - | - | - | - | - | -
6.5 | Group tender presentations | - | - | - | - | - | - | - | - | - | - | -
6.6 | Financial Report 1 sumbission | - | - | - | - | - | - | - | - | - | - | -
6.7 | All contracts agreed and filed | - | - | - | - | - | - | - | - | - | - | -
6.8 | Financial Report 2 submission | - | - | - | - | - | - | - | - | - | - | -
6.9 | First iteration complete | - | - | - | - | - | - | - | - | - | - | -
6.1 | Final test & integration plan | - | - | - | - | - | - | - | - | - | - | -
6.11 | Financial Report 3 submission | - | - | - | - | - | - | - | - | - | - | -
6.12 | Financial Summary Report submission | - | - | - | - | - | - | - | - | - | - | -
6.13 | Demonstration / Sales presentation | - | - | - | - | - | - | - | - | - | - | -
6.14 | Hand in of all deliverables | - | - | - | - | - | - | - | - | - | - | -
Total For Team | [9 empty] | 98.75
Total Per Employee |  | 13 | 21.5 | 7.5 | 10.5 | 3 | 10.75 | 27 | 5.5 | 98.75
Forecast Per Employee |  | 7.42 | 2.48 | 10.48 | 14.55 | 1 | 15.95 | 37.8 | 18.3 | 107.98
Percentage Difference |  | 75.2% | 766.9% | -28.44% | -27.84% | 200% | -32.6% | -28.57% | -69.95% | -8.548%

## WK5 0502
|  | Name Of Employee | [7 empty] | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John
1 | Meetings | [8 empty] | 16.5 | 8
1.1 | Meetings | 5 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 15 | 8 | 87.5%
N/A | Minutes | - | 0.5 | - | - | - | - | - | - | 0.5 | - | N/A
1.2 | Performance and Document reviews (QA) | - | 1 | - | - | - | - | - | - | 1 | - | N/A
2 | Documentation | [8 empty] | 9 | 27.92 | -67.77%
2.1 | Functional Specification | [8 empty] | 0 | - | N/A
2.1.1 | Functional Specification Generation | - | - | - | - | - | - | - | - | - | - | -
2.1.2 | Generate User Stories | - | - | - | - | - | - | - | - | - | - | -
2.1.3 | Functional Specification Compilation | - | - | - | - | - | - | - | - | - | - | -
2.2 | QA Manual | [8 empty] | 0 | - | N/A
2.2.1 | Generate QA Roles & Responsibilities | - | - | - | - | - | - | - | - | - | - | -
2.2.2 | Compile QA Manual | - | - | - | - | - | - | - | - | - | - | -
2.3 | Generate WBS, GANNT & PERT | - | - | - | - | - | 3.75 | - | - | 3.75 | 6.68 | -43.86%
2.4 | Generate PWS | - | - | - | - | - | - | - | - | - | - | -
2.5 | Negotiate Inter-group contracts | - | - | - | - | - | - | - | - | - | - | -
2.6 | Create tender presentation | - | - | - | - | - | - | 0.25 | 5 | 5.25 | 0.6 | 775%
2.7 | Create Product demo presentation | - | - | - | - | - | - | - | - | 0 | 20.63 | -100%
2.8 | Compile hand in document of all deliverables | - | - | - | - | - | - | - | - | - | - | -
2.9 | Give Presentation | - | - | - | - | - | - | - | - | - | - | -
3 | Finance | [8 empty] | 23.75 | 18.75 | 26.67%
3.1 | Generate Financial Business Plan | - | - | - | - | - | - | 18 | - | 18 | 15 | 20%
3.2 | Generate Financial Report 1 | - | - | - | 1.75 | - | - | 4 | - | 5.75 | 3.75 | 53.33%
3.3 | Generate Financial Report 2 | - | - | - | - | - | - | - | - | - | - | -
3.4 | Generate Financial Report 3 | - | - | - | - | - | - | - | - | - | - | -
3.5 | Generate Financial Summary Report | - | - | - | - | - | - | - | - | - | - | -
4 | Research & Design | [8 empty] | 6.5 |  | N/A
4.1 | Research & Analyze Market | - | - | - | - | - | - | - | - | - | - | -
4.2 | Research advertizement Revenue | - | - | - | - | - | - | - | - | - | - | -
4.3 | Develop Sales Strategies | - | - | - | - | - | - | - | - | - | - | -
4.4 | Design | [8 empty] | 6.5 | - | N/A
4.4.1 | Generate App Mockups | - | - | - | 6.5 | - | - | - | - | 6.5 | - | N/A
4.4.2 | Design Logo | - | - | - | - | - | - | - | - | - | - | -
4.4.3 | Create Class Diagrams | - | - | - | - | - | - | - | - | - | - | -
5 | Development | [8 empty] | 16.5 | 100.58 | -83.6%
5.1 | Source Media for App | - | - | 1.5 | - | - | - | - | - | 1.5 | 4.37 | -65.68%
5.2 | Generate Icons for App | - | - | - | - | - | - | - | - | 0 | 3.75 | -100%
5.3 | Software | [8 empty] | 15 | 92.47 | -83.78%
5.3.1 | GUI Development | [8 empty] | 0 | 38.77 | -100%
5.3.1.1 | Prototype GUI Development | - | - | - | - | - | - | - | - | 0 | 38.77 | -100%
5.3.1.2 | Final GUI Development | - | - | - | - | - | - | - | - | - | - | -
5.3.2 | App Development | [8 empty] | 15 | 53.7 | -72.07%
5.3.2.1 | Prototype App Development | - | - | 13 | - | 2 | - | - | - | 15 | 53.7 | -72.07%
5.3.2.2 | Final App Development | - | - | - | - | - | - | - | - | - | - | -
5.4 | Testing & Analysis | [8 empty] | 0 | - | N/A
5.4.1 | GUI Testing | - | - | - | - | - | - | - | - | - | - | -
5.4.2 | System Testing | - | - | - | - | - | - | - | - | - | - | -
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | - | - | - | - | - | -
6 | Deliverables | [8 empty] | 0 | - | N/A
6.1 | Functional Spec to supervisor | - | - | - | - | - | - | - | - | - | - | -
6.2 | QA Manual uploaded to repository | - | - | - | - | - | - | - | - | - | - | -
6.3 | Financial Business Plan submission | - | - | - | - | - | - | - | - | - | - | -
6.4 | PWS Agreed between groups | - | - | - | - | - | - | - | - | - | - | -
6.5 | Group tender presentations | - | - | - | - | - | - | - | - | - | - | -
6.6 | Financial Report 1 sumbission | - | - | - | - | - | - | - | - | - | - | -
6.7 | All contracts agreed and filed | - | - | - | - | - | - | - | - | - | - | -
6.8 | Financial Report 2 submission | - | - | - | - | - | - | - | - | - | - | -
6.9 | First iteration complete | - | - | - | - | - | - | - | - | - | - | -
6.1 | Final test & integration plan | - | - | - | - | - | - | - | - | - | - | -
6.11 | Financial Report 3 submission | - | - | - | - | - | - | - | - | - | - | -
6.12 | Financial Summary Report submission | - | - | - | - | - | - | - | - | - | - | -
6.13 | Demonstration / Sales presentation | - | - | - | - | - | - | - | - | - | - | -
6.14 | Hand in of all deliverables | - | - | - | - | - | - | - | - | - | - | -
Total For Team | [9 empty] | 72.25
Total Per Employee |  | 5 | 3.5 | 16.5 | 9.25 | 4 | 4.75 | 23.25 | 6 | 72.25
Forecast Per Employee |  | 19.47 | 6.78 | 26.2 | 9.73 | 17.08 | 30.03 | 32.35 | 13.6 | 155.24
Percentage Difference |  | -74.32% | -48.38% | -37.02% | -4.933% | -76.58% | -84.18% | -28.13% | -55.88% | -53.46%

## WK6 1202
|  | Name Of Employee | [7 empty] | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John
1 | Meetings | [8 empty] | 19.25 | 8 | 140.6%
1.1 | Meetings | 2 | 2 | 3 | 3 | 2 | 2 | 3.75 | 1.5 | 19.25 | 8 | 140.6%
N/A | Minutes | - | - | - | - | - | - | - | - | - | - | -
1.2 | Performance and Document reviews (QA) | - | - | - | - | - | - | - | - | - | - | -
2 | Documentation | [8 empty] | 44.5 | 24.93 | 78.5%
2.1 | Functional Specification | [8 empty] | 0 | - | N/A
2.1.1 | Functional Specification Generation | - | - | - | - | - | - | - | - | - | - | -
2.1.2 | Generate User Stories | - | - | - | - | - | - | - | - | - | - | -
2.1.3 | Functional Specification Compilation | - | - | - | - | - | - | - | - | - | - | -
-
2.2 | QA Manual | [8 empty] | 0 | - | N/A
2.2.1 | Generate QA Roles & Responsibilities | - | - | - | - | - | - | - | - | - | - | -
2.2.2 | Compile QA Manual | - | - | - | - | - | - | - | - | - | - | -
2.3 | Generate WBS, GANNT & PERT | - | - | - | - | - | 11 | - | - | 11 | - | N/A
2.4 | Generate PWS | - | - | 3 | - | - | - | - | - | 0 | 8 | -100%
2.5 | Negotiate Inter-group contracts | - | - | - | - | - | - | - | - | 0 | 0.37 | -100%
2.6 | Create tender presentation | - | 3 |  | 5.5 |  | 5.5 | 13 | 6.5 | 33.5 | 16.58 | 102.1%
2.7 | Create Product demo presentation | - | - | - | - | - | - | - | - | - | - | -
2.8 | Compile hand in document of all deliverables | - | - | - | - | - | - | - | - | - | - | -
2.9 | Give Presentation | - | - | - | - | - | - | - | - | - | - | -
3 | Finance | [8 empty] | 14.75 | 18.75 | -21.33%
3.1 | Generate Financial Business Plan | - | - | - | - | - | - | 8.5 | - | 8.5 | - | N/A
3.2 | Generate Financial Report 1 | 0.5 | 0.75 | - | - | - | - | 5 | - | 6.25 | 18.75 | -66.67%
3.3 | Generate Financial Report 2 | - | - | - | - | - | - | - | - | - | - | N/A
3.4 | Generate Financial Report 3 | - | - | - | - | - | - | - | - | - | - | N/A
3.5 | Generate Financial Summary Report | - | - | - | - | - | - | - | - | - | - | N/A
4 | Research & Design | [8 empty] | 10 | - | N/A
4.1 | Research & Analyze Market | - | - | - | - | - | - | - | 5 | 5 | - | N/A
4.2 | Research advertizement Revenue | - | - | - | - | - | - | - | - | - | - | -
4.3 | Develop Sales Strategies | - | - | - | - | - | - | - | - | - | - | -
4.4 | Design | [8 empty] | 5 |  | N/A
4.4.1 | Generate App Mockups | - | - | - | 5 | - | - | - | - | 5 | - | N/A
4.4.2 | Design Logo | - | - | - | - | - | - | - | - | - | - | -
4.4.3 | Create Class Diagrams | - | - | - | - | - | - | - | - | - | - | -
5 | Development | [8 empty] | 22.25 | 100.58 | -77.88%
5.1 | Source Media for App | - | - | - | - | - | - | - | - | 0 | 4.37 | -100%
5.2 | Generate Icons for App | 2 | - | - | - | - | - | - | - | 2 | 3.75 | -46.67%
5.3 | Software | [8 empty] | 20.25 | 92.47 | -78.1%
5.3.1 | GUI Development | [8 empty] | 2.5 | 38.77 | -93.55%
5.3.1.1 | Prototype GUI Development | - | - | - | - | 2.5 | - | - | - | 2.5 | 38.77 | -93.55%
5.3.1.2 | Final GUI Development | - | - | - | - | - | - | - | - | - | - | -
5.3.2 | App Development | [8 empty] | 17.75 | 53.7 | -66.95%
5.3.2.1 | Prototype App Development | - | 4.5 | 11.75 | - | - | - | 1.5 | - | 17.75 | 53.7 | -66.95%
5.3.2.2 | Final App Development | - | - | - | - | - | - | - | - | - | - | -
5.4 | Testing & Analysis | [8 empty] | 0 |  | N/A
5.4.1 | GUI Testing | - | - | - | - | - | - | - | - | - | - | -
5.4.2 | System Testing | - | - | - | - | - | - | - | - | - | - | -
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | - | - | - | - | - | -
6 | Deliverables | [8 empty] | 4 |  | N/A
6.1 | Functional Spec to supervisor | - | - | - | - | - | - | - | - | - | - | -
6.2 | QA Manual uploaded to repository | - | - | - | - | - | - | - | - | - | - | -
6.3 | Financial Business Plan submission | - | - | - | - | - | - | - | - | - | - | -
6.4 | PWS Agreed between groups | - | - | - | - | - | - | - | - | - | - | -
6.5 | Group tender presentations | 4 | - | - | - | - | - | - | - | 4 | - | N/A
6.6 | Financial Report 1 sumbission | - | - | - | - | - | - | - | - | - | - | -
6.7 | All contracts agreed and filed | - | - | - | - | - | - | - | - | - | - | -
6.8 | Financial Report 2 submission | - | - | - | - | - | - | - | - | - | - | -
6.9 | First iteration complete | - | - | - | - | - | - | - | - | - | - | -
6.1 | Final test & integration plan | - | - | - | - | - | - | - | - | - | - | -
6.11 | Financial Report 3 submission | - | - | - | - | - | - | - | - | - | - | -
6.12 | Financial Summary Report submission | - | - | - | - | - | - | - | - | - | - | -
6.13 | Demonstration / Sales presentation | - | - | - | - | - | - | - | - | - | - | -
6.14 | Hand in of all deliverables | - | - | - | - | - | - | - | - | - | - | -
Total For Team | [9 empty] | 110.75
Total Per Employee |  | 4.5 | 10.25 | 17.75 | 13.5 | 4.5 | 18.5 | 31.75 | 13 | 113.75
Forecast Per Employee |  | 19 | 6.58 | 26.2 | 9.35 | 17.08 | 30.48 | 31.15 | 12.4 | 152.24
Percentage Difference |  | -76.32% | 55.78% | -32.25% | 44.39% | -73.65% | -39.3% | 1.926% | 4.839% | -25.28%

## Task Analysis
¯\_(ツ)_/¯ |  | ACTUAL (hrs) | [5 empty] | FORECAST (hrs)
WBS | Task Name | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | Task Name | 15/01/2018 | 22/01/2018 | 29/01/2018 | 05/02/2018 | 12/02/2018
1 | Meetings | 16 | 22.5 | 16.5 | 16.5 | 19.25 | Meetings | 8 | 8 | 8 | 8 | 8
1.1 | Meetings | 16 | 21.5 | 16 | 15 | 19.25 | Meetings | 8 | 8 | 8 | 8 | 8
N/A | Minutes | - | 1 | 0.5 | 0.5 | - | Minutes | - | - | - | - | -
1.2 | Performance and Document reviews (QA) |  |  |  | 1 | - | Performance and Document reviews (QA) |  |  |  | - | -
2 | Documentation | 4.5 | 19.5 | 49 | 9 | 44.5 | Documentation | 73.6 | 18.15 | 26.75 | 27.92 | 24.93
2.1 | Functional Specification | 4.5 | 11 | 28.5 | 0 | 0 | Functional Specification | 55 | - | - | - | -
2.1.1 | Functional Specification Generation | 4.5 | 6 | 18 | - | - | Functional Specification Generation | 34 | - | - | - | -
2.1.2 | Generate User Stories | 0 | 5 | 1.5 | - | - | Generate User Stories | 12 | - | - | - | -
2.1.3 | Functional Specification Compilation | 0 | - | 9 | - | - | Functional Specification Compilation | 9 | - | - | - | -
2.2 | QA Manual | 0 | 8.5 | 20.5 | 0 | 0 | QA Manual | 18 | 17 | - | - | -
2.2.1 | Generate QA Roles & Responsibilities | 0 | 8.5 | 13 | - | - | Generate QA Roles & Responsibilities | 18 | 2 | - | - | -
2.2.2 | Compile QA Manual | - | 0 | 7.5 | - | - | Compile QA Manual | - | 15 | - | - | -
-
2.3 | Generate WBS, GANNT & PERT | - | 0 | 0 | 3.75 | 11 | Generate WBS, GANNT & PERT | - | 0.55 | 8.35 | 6.68 | -
2.4 | Generate PWS | - | 0 | - | - | 0 | Generate PWS | - | 0.6 | - | - | 8
2.5 | Negotiate Inter-group contracts | - | - | 0 | - | 0 | Negotiate Inter-group contracts | - | - | 0.6 | - | 0.37
2.6 | Create tender presentation | 0 | - | 0 | 5.25 | 33.5 | Create tender presentation | 0.6 | - | 17.8 | 0.6 | 16.58
2.7 | Create Product demo presentation | - | - | - | 0 | - | Create Product demo presentation | - | - | - | 20.63 | -
2.8 | Compile hand in document of all deliverables | - | - | - | - | - | Compile hand in document of all deliverables | - | - | - | - | -
2.9 | Give Presentation | - | - | - | - | - | Give Presentation | - | - | - | - | -
3 | Finance | 1 | 3.5 | 18 | 23.75 | 14.75 | Finance | - | 22.5 | 22.5 | 18.75 | 18.75
3.1 | Generate Financial Business Plan | 1 | 3.5 | 18 | 18 | 8.5 | Generate Financial Business Plan | - | 22.5 | 22.5 | 15 | -
3.2 | Generate Financial Report 1 | - | - | - | 5.75 | 6.25 | Generate Financial Report 1 | - | - | - | 3.75 | 18.75
3.3 | Generate Financial Report 2 | - | - | - | - | - | Generate Financial Report 2 | - | - | - | - | -
3.4 | Generate Financial Report 3 | - | - | - | - | - | Generate Financial Report 3 | - | - | - | - | -
3.5 | Generate Financial Summary Report | - | - | - | - | - | Generate Financial Summary Report | - | - | - | - | -
4 | Research & Design | 5 | 24 | 7.25 | 6.5 | 10 | Research & Design | 27.75 | 38.65 | 37.45 |  | -
4.1 | Research & Analyze Market | 3 | 4.75 | 2.5 | - | 5 | Research & Analyze Market | 7.5 | 7.5 | 5 | - | -
4.2 | Research advertizement Revenue | 2 | 5.75 | 0 | - | - | Research advertizement Revenue | 3 | 3 | 2 | - | -
4.3 | Develop Sales Strategies | - | 0 | 0 | - | - | Develop Sales Strategies | - | 8 | 12 | - | -
4.4 | Design | 0 | 13.5 | 4.75 | 6.5 | 5 | Design | 17.25 | 20.15 | 18.45 | -
4.4.1 | Generate App Mockups | 0 | 13.5 | 4.75 | 6.5 | 5 | Generate App Mockups | 11.67 | 11.67 | 11.67 | - | -
4.4.2 | Design Logo | 0 | 0 | 0 | - | - | Design Logo | 1.63 | 1.88 | 1.5 | - | -
4.4.3 | Create Class Diagrams | 0 | 0 | 0 | - | - | Create Class Diagrams | 3.97 | 6.6 | 5.28 | - | -
5 | Development | 0 | 1.5 | 8 | 16.5 | 22.25 | Development | - |  | 13.27 | 100.58 | 100.58
5.1 | Source Media for App | - | - | 0 | 1.5 | 0 | Source Media for App | - | - | 0.87 | 4.37 | 4.37
5.2 | Generate Icons for App | - | - | 8 | 0 | 2 | Generate Icons for App | - | - | 0.75 | 3.75 | 3.75
5.3 | Software | 0 | 1.5 | 0 | 15 | 20.25 | Software | - | - | 11.65 | 92.47 | 92.47
5.3.1 | GUI Development | 0 | 0 | 0 | 0 | 2.5 | GUI Development | - | - | 2.7 | 38.77 | 38.77
5.3.1.1 | Prototype GUI Development | - | - | 0 | 0 | 2.5 | Prototype GUI Development | - | - | 2.7 | 38.77 | 38.77
5.3.1.2 | Final GUI Development | - | - | - | - | - | Final GUI Development | - | - | - | - | -
5.3.2 | App Development | 0 | 1.5 | 0 | 15 | 17.75 | App Development | - | - | 8.95 | 53.7 | 53.7
5.3.2.1 | Prototype App Development | - | 1.5 | 0 | 15 | 17.75 | Prototype App Development | - | - | 8.95 | 53.7 | 53.7
5.3.2.2 | Final App Development | - | - | - | - | - | Final App Development | - | - | - | - | -
5.4 | Testing & Analysis | 0 | 0 | 0 | 0 | 0 | Testing & Analysis | - | - | - | -
5.4.1 | GUI Testing | - | - | - | - | - | GUI Testing | - | - | - | - | -
5.4.2 | System Testing | - | - | - | - | - | System Testing | - | - | - | - | -
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | Perform & gather consumer feedback | - | - | - | - | -
|  | - | [5 empty] | -
6 | Deliverables | 0 | 0 | 0 | 0 | 4 | Deliverables | - | - | - | -
6.1 | Functional Spec to supervisor | - | - | - | - | - | Functional Spec to supervisor | - | - | - | - | -
6.2 | QA Manual uploaded to repository | - | - | - | - | - | QA Manual uploaded to repository | - | - | - | - | -
6.3 | Financial Business Plan submission | - | - | - | - | - | Financial Business Plan submission | - | - | - | - | -
6.4 | PWS Agreed between groups | - | - | - | - | - | PWS Agreed between groups | - | - | - | - | -
6.5 | Group tender presentations | - | - | - | - | 4 | Group tender presentations | - | - | - | - | -
6.6 | Financial Report 1 sumbission | - | - | - | - | - | Financial Report 1 sumbission | - | - | - | - | -
6.7 | All contracts agreed and filed | - | - | - | - | - | All contracts agreed and filed | - | - | - | - | -
6.8 | Financial Report 2 submission | - | - | - | - | - | Financial Report 2 submission | - | - | - | - | -
6.9 | First iteration complete | - | - | - | - | - | First iteration complete | - | - | - | - | -
6.1 | Final test & integration plan | - | - | - | - | - | Final test & integration plan | - | - | - | - | -
6.11 | Financial Report 3 submission | - | - | - | - | - | Financial Report 3 submission | - | - | - | - | -
6.12 | Financial Summary Report submission | - | - | - | - | - | Financial Summary Report submission | - | - | - | - | -
6.13 | Demonstration / Sales presentation | - | - | - | - | - | Demonstration / Sales presentation | - | - | - | - | -
6.14 | Hand in of all deliverables | - | - | - | - | - | Hand in of all deliverables | - | - | - | - | -

## Sheet7
Week No. | 2 | 3 | 4 | 5 | 6
Date | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12
Actual | 26.5 | 71 | 98.75 | 72.25 | 113.75
Forecast | 109.37 | 87.3 | 107.98 | 155.24 | 152.24
Difference (%) | -75.77% | -18.67% | -8.548% | -53.46% | -25.28%