## wk9 0503
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | [8 empty] | 4.5 | 16 | 71.88%
1.1 | Meetings | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 4 | 8 | -
N/A | Minutes |  | 0.5 | [6 empty] | 0.5 | - | -
1.2 | Performance and Document reviews (QA) | [8 empty] | 0 | 8 | -
2 | Documentation | [8 empty] | 0 | 0 | N/A
2.1 | Functional Specification | [8 empty] | 0 | 0 | 0
2.1.1 | Functional Specification Generation | [8 empty] | - | - | -
2.1.2 | Generate User Stories | [8 empty] | - | - | -
2.1.3 | Functional Specification Compilation | [8 empty] | - | - | -
2.2 | QA Manual | [8 empty] | 0 | 0 | 0
2.2.1 | Generate QA Roles & Responsibilities | [8 empty] | - | - | -
2.2.2 | Compile QA Manual | [8 empty] | - | - | -
2.3 | Generate WBS, GANNT & PERT | [8 empty] | - | - | -
2.4 | Generate PWS | [8 empty] | - | - | -
2.5 | Negotiate Inter-group contracts | [8 empty] | 0 | - | -
2.6 | Create tender presentation | [8 empty] | - | - | -
2.7 | Create Product demo presentation | [8 empty] | - | - | -
2.8 | Compile hand in document of all deliverables | [8 empty] | - | - | -
2.9 | Give Presentation | [8 empty] | - | - | -
3 | Finance | [8 empty] | 24.75 | 13.75 | -80%
3.1 | Generate Financial Business Plan | [8 empty] | 0 | - | -
3.2 | Generate Financial Report 1 | [8 empty] | 0 | 12.5 | -
3.3 | Generate Financial Report 2 |  | 2.25 |  |  | 1 |  | 20.5 | 1 | 24.75 | 1.25 | -
3.4 | Generate Financial Report 3 | [6 empty] | 0.25 |  | - | - | -
3.5 | Generate Financial Summary Report | [8 empty] | - | - | -
4 | Research & Design | [8 empty] | 0 | 0 | N/A
4.1 | Research & Analyze Market | [8 empty] | - | - | -
4.2 | Research advertizement Revenue | [8 empty] | - | - | -
4.3 | Develop Sales Strategies | [8 empty] | 0 | - | -
4.4 | Design | [8 empty] | 0 | 0 | 0
4.4.1 | Generate App Mockups | [8 empty] | - | - | -
4.4.2 | Design Logo | [8 empty] | - | - | -
4.4.3 | Create Class Diagrams | [8 empty] | - | - | -
5 | Development | [8 empty] | 115.25 | 100.59 | -14.57%
5.1 | Source Media for App | [8 empty] | - | 4.37 | -
5.2 | Generate Icons for App | [8 empty] | - | 3.75 | -
5.3 | Software | [8 empty] | 115.25 | 92.47 | 0
5.3.1 | GUI Development | [8 empty] | 0 | 38.77 | 0
5.3.1.1 | Prototype GUI Development | [8 empty] | 0 | 38.77 | -
5.3.1.2 | Final GUI Development | [8 empty] | - | - | -
5.3.2 | App Development | [8 empty] | 115.25 | 53.7 | 0
5.3.2.1 | Prototype App Development | 12.5 | 9.5 | 39.25 | 6.5 | 15 | 2.5 | 23.75 | 6.25 | 115.25 | 53.7 | -
5.3.2.2 | Final App Development | [8 empty] | - | - | -
5.4 | Testing & Analysis | [8 empty] | 0 | 0 | 0
5.4.1 | GUI Testing | [8 empty] | - | - | -
5.4.2 | System Testing | [8 empty] | - | - | -
5.4.3 | Perform & gather consumer feedback | [8 empty] | - | - | -
6 | Deliverables | [8 empty] | 0 | 0 | N/A
6.1 | Functional Spec to supervisor | [8 empty] | - | - | -
6.2 | QA Manual uploaded to repository | [8 empty] | - | - | -
6.3 | Financial Business Plan submission | [8 empty] | - | - | -
6.4 | PWS Agreed between groups | [8 empty] | - | - | -
6.5 | Group tender presentations | [8 empty] | 0 | - | -
6.6 | Financial Report 1 sumbission | [8 empty] | - | - | -
6.7 | All contracts agreed and filed | [8 empty] | - | - | -
6.8 | Financial Report 2 submission | [8 empty] | - | - | -
6.9 | First iteration complete | [8 empty] | - | - | -
6.1 | Final test & integration plan | [8 empty] | - | - | -
6.11 | Financial Report 3 submission | [8 empty] | - | - | -
6.12 | Financial Summary Report submission | [8 empty] | - | - | -
6.13 | Demonstration / Sales presentation | [8 empty] | - | - | -
6.14 | Hand in of all deliverables | [8 empty] | - | - | -
Total For Team | [9 empty] | 144.5
Total Per Employee |  | 13 | 12.75 | 39.75 | 7 | 16.5 | 3 | 45 | 7.75 | 144.75
Forecast Per Employee |  | 18.2 | 7.1 | 27.2 | 8.48 | 18 | 20.3 | 22.3 | 8.6 | 130.18
Percentage Difference |  | -28.57% | 79.58% | 46.14% | -17.45% | -8.333% | -85.22% | 101.8% | -9.884% | 11.19%

## wk10 1203
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | [8 empty] | 7 | 16 | 56.25%
1.1 | Meetings | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 7 | 8 | -
N/A | Minutes | [8 empty] | 0 | - | -
1.2 | Performance and Document reviews (QA) | [8 empty] | 0 | 8 | -
2 | Documentation | [8 empty] | 0 | 0 | N/A
2.1 | Functional Specification | [8 empty] | 0 | 0 | 0
2.1.1 | Functional Specification Generation | [8 empty] | - | - | -
2.1.2 | Generate User Stories | [8 empty] | - | - | -
2.1.3 | Functional Specification Compilation | [8 empty] | - | - | -
2.2 | QA Manual | [8 empty] | 0 | 0 | 0
2.2.1 | Generate QA Roles & Responsibilities | [8 empty] | - | - | -
2.2.2 | Compile QA Manual | [8 empty] | - | - | -
2.3 | Generate WBS, GANNT & PERT | [8 empty] | - | - | -
2.4 | Generate PWS | [8 empty] | - | - | -
2.5 | Negotiate Inter-group contracts | [8 empty] | 0 | - | -
2.6 | Create tender presentation | [8 empty] | - | - | -
2.7 | Create Product demo presentation | [8 empty] | - | - | -
2.8 | Compile hand in document of all deliverables | [8 empty] | - | - | -
2.9 | Give Presentation | [8 empty] | - | - | -
3 | Finance | [8 empty] | 0 | 13.75 | 100%
3.1 | Generate Financial Business Plan | [8 empty] | 0 | - | -
3.2 | Generate Financial Report 1 | [8 empty] | 0 | 12.5 | -
3.3 | Generate Financial Report 2 | [8 empty] | 0 | 1.25 | -
3.4 | Generate Financial Report 3 | [8 empty] | - | - | -
3.5 | Generate Financial Summary Report | [6 empty] | 0.75 |  | - | - | -
4 | Research & Design | [8 empty] | 0 | 0 | N/A
4.1 | Research & Analyze Market | [8 empty] | - | - | -
4.2 | Research advertizement Revenue | [8 empty] | - | - | -
4.3 | Develop Sales Strategies | [8 empty] | 0 | - | -
4.4 | Design | [8 empty] | 0 | 0 | 0
4.4.1 | Generate App Mockups | [8 empty] | - | - | -
4.4.2 | Design Logo | [8 empty] | - | - | -
4.4.3 | Create Class Diagrams | [8 empty] | - | - | -
5 | Development | [8 empty] | 93.75 | 100.59 | 6.8%
5.1 | Source Media for App | 1 | [7 empty] | - | 4.37 | -
5.2 | Generate Icons for App | [8 empty] | - | 3.75 | -
5.3 | Software | [8 empty] | 93.75 | 92.47 | 0
5.3.1 | GUI Development | [8 empty] | 0 | 38.77 | 0
5.3.1.1 | Prototype GUI Development | [8 empty] | 0 | 38.77 | -
5.3.1.2 | Final GUI Development | [8 empty] | - | - | -
5.3.2 | App Development | [8 empty] | 93.75 | 53.7 | 0
5.3.2.1 | Prototype App Development |  |  | 22 | 12 | 7.25 | 22.5 | 22.5 | 7.5 | 93.75 | 53.7 | -
5.3.2.2 | Final App Development | [8 empty] | - | - | -
5.4 | Testing & Analysis | [8 empty] | 0 | 0 | 0
5.4.1 | GUI Testing |  |  | 11 |  |  |  | 1 |  | - | - | -
5.4.2 | System Testing | [8 empty] | - | - | -
5.4.3 | Perform & gather consumer feedback | [8 empty] | - | - | -
6 | Deliverables | [8 empty] | 0 | 0 | N/A
6.1 | Functional Spec to supervisor | [8 empty] | - | - | -
6.2 | QA Manual uploaded to repository | [8 empty] | - | - | -
6.3 | Financial Business Plan submission | [8 empty] | - | - | -
6.4 | PWS Agreed between groups | [8 empty] | - | - | -
6.5 | Group tender presentations | [8 empty] | 0 | - | -
6.6 | Financial Report 1 sumbission | [8 empty] | - | - | -
6.7 | All contracts agreed and filed | [8 empty] | - | - | -
6.8 | Financial Report 2 submission | [8 empty] | - | - | -
6.9 | First iteration complete | [8 empty] | - | - | -
6.1 | Final test & integration plan | [8 empty] | - | - | -
6.11 | Financial Report 3 submission | [8 empty] | - | - | -
6.12 | Financial Summary Report submission | [8 empty] | - | - | -
6.13 | Demonstration / Sales presentation | [8 empty] | - | - | -
6.14 | Hand in of all deliverables | [8 empty] | - | - | -
Total For Team | [9 empty] | 100.75
Total Per Employee |  | 2 | 0 | 34 | 13 | 8.25 | 23.5 | 25.25 | 8.5 | 114.5
Forecast Per Employee |  | 18.2 | 7.1 | 27.2 | 8.48 | 18 | 20.3 | 22.3 | 8.6 | 130.18
Percentage Difference |  | -89.01% | -100% | 25% | 53.3% | -54.17% | 15.76% | 13.23% | -1.163% | -12.04%
exceptional circumstances 0.25

## wk11 1903
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | [8 empty] | 2.25 | 16 | 85.94%
1.1 | Meetings | [5 empty] | 2.25 |  |  | 2.25 | 8 | -
N/A | Minutes | [8 empty] | 0 | - | -
1.2 | Performance and Document reviews (QA) | [8 empty] | 0 | 8 | -
2 | Documentation | [8 empty] | 0 | 0 | N/A
2.1 | Functional Specification | [8 empty] | 0 | 0 | 0
2.1.1 | Functional Specification Generation | [8 empty] | - | - | -
2.1.2 | Generate User Stories | [8 empty] | - | - | -
2.1.3 | Functional Specification Compilation | [8 empty] | - | - | -
2.2 | QA Manual | [8 empty] | 0 | 0 | 0
2.2.1 | Generate QA Roles & Responsibilities | [8 empty] | - | - | -
2.2.2 | Compile QA Manual | [8 empty] | - | - | -
2.3 | Generate WBS, GANNT & PERT | [8 empty] | - | - | -
2.4 | Generate PWS | [8 empty] | - | - | -
2.5 | Negotiate Inter-group contracts | [8 empty] | 0 | - | -
2.6 | Create tender presentation | [8 empty] | - | - | -
2.7 | Create Product demo presentation | [8 empty] | - | - | -
2.8 | Compile hand in document of all deliverables | [8 empty] | - | - | -
2.9 | Give Presentation | [8 empty] | - | - | -
3 | Finance | [8 empty] | 0 | 13.75 | 100%
3.1 | Generate Financial Business Plan | [8 empty] | 0 | - | -
3.2 | Generate Financial Report 1 | [8 empty] | 0 | 12.5 | -
3.3 | Generate Financial Report 2 | [8 empty] | 0 | 1.25 | -
3.4 | Generate Financial Report 3 | [6 empty] | 0.5 |  | - | - | -
3.5 | Generate Financial Summary Report | [8 empty] | - | - | -
4 | Research & Design | [8 empty] | 0 | 0 | N/A
4.1 | Research & Analyze Market | [8 empty] | - | - | -
4.2 | Research advertizement Revenue | [8 empty] | - | - | -
4.3 | Develop Sales Strategies | [8 empty] | 0 | - | -
4.4 | Design | [8 empty] | 0 | 0 | 0
4.4.1 | Generate App Mockups | [8 empty] | - | - | -
4.4.2 | Design Logo | [8 empty] | - | - | -
4.4.3 | Create Class Diagrams | [8 empty] | - | - | -
5 | Development | [8 empty] | 14.5 | 100.59 | 85.59%
5.1 | Source Media for App | [8 empty] | - | 4.37 | -
5.2 | Generate Icons for App | [8 empty] | - | 3.75 | -
5.3 | Software | [8 empty] | 14.5 | 92.47 | 0
5.3.1 | GUI Development | [8 empty] | 0 | 38.77 | 0
5.3.1.1 | Prototype GUI Development | [8 empty] | 0 | 38.77 | -
5.3.1.2 | Final GUI Development | [8 empty] | - | - | -
5.3.2 | App Development | [8 empty] | 14.5 | 53.7 | 0
5.3.2.1 | Prototype App Development | [8 empty] | 0 | 53.7 | -
5.3.2.2 | Final App Development | [5 empty] | 9.5 |  | 5 | 14.5 | - | -
5.4 | Testing & Analysis | [8 empty] | 0 | 0 | 0
5.4.1 | GUI Testing | [8 empty] | - | - | -
5.4.2 | System Testing | [8 empty] | - | - | -
5.4.3 | Perform & gather consumer feedback | [8 empty] | - | - | -
6 | Deliverables | [8 empty] | 0 | 0 | N/A
6.1 | Functional Spec to supervisor | [8 empty] | - | - | -
6.2 | QA Manual uploaded to repository | [8 empty] | - | - | -
6.3 | Financial Business Plan submission | [8 empty] | - | - | -
6.4 | PWS Agreed between groups | [8 empty] | - | - | -
6.5 | Group tender presentations | [8 empty] | 0 | - | -
6.6 | Financial Report 1 sumbission | [8 empty] | - | - | -
6.7 | All contracts agreed and filed | [8 empty] | - | - | -
6.8 | Financial Report 2 submission | [8 empty] | - | - | -
6.9 | First iteration complete | [8 empty] | - | - | -
6.1 | Final test & integration plan | [8 empty] | - | - | -
6.11 | Financial Report 3 submission | [8 empty] | - | - | -
6.12 | Financial Summary Report submission | [8 empty] | - | - | -
6.13 | Demonstration / Sales presentation | [8 empty] | - | - | -
6.14 | Hand in of all deliverables | [8 empty] | - | - | -
Total For Team | [9 empty] | 16.75
Total Per Employee |  | 0 | 0 | 0 | 0 | 0 | 11.75 | 0.5 | 5 | 17.25
Forecast Per Employee |  | 18.2 | 7.1 | 27.2 | 8.48 | 18 | 20.3 | 22.3 | 8.6 | 130.18
Percentage Difference |  | -100% | -100% | -100% | -100% | -100% | -42.12% | -97.76% | -41.86% | -86.75%

## wk12 2603
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | [8 empty] | 0 | 16 | 100%
1.1 | Meetings | [8 empty] | 0 | 8 | -
N/A | Minutes | [8 empty] | 0 | - | -
1.2 | Performance and Document reviews (QA) | [8 empty] | 0 | 8 | -
2 | Documentation | [8 empty] | 0 | 0 | N/A
2.1 | Functional Specification | [8 empty] | 0 | 0 | 0
2.1.1 | Functional Specification Generation | [8 empty] | - | - | -
2.1.2 | Generate User Stories | [8 empty] | - | - | -
2.1.3 | Functional Specification Compilation | [8 empty] | - | - | -
2.2 | QA Manual | [8 empty] | 0 | 0 | 0
2.2.1 | Generate QA Roles & Responsibilities | [8 empty] | - | - | -
2.2.2 | Compile QA Manual | [8 empty] | - | - | -
2.3 | Generate WBS, GANNT & PERT | [8 empty] | - | - | -
2.4 | Generate PWS | [8 empty] | - | - | -
2.5 | Negotiate Inter-group contracts | [8 empty] | 0 | - | -
2.6 | Create tender presentation | [8 empty] | - | - | -
2.7 | Create Product demo presentation | [8 empty] | - | - | -
2.8 | Compile hand in document of all deliverables | [8 empty] | - | - | -
2.9 | Give Presentation | [8 empty] | - | - | -
3 | Finance | [8 empty] | 0 | 13.75 | 100%
3.1 | Generate Financial Business Plan | [8 empty] | 0 | - | -
3.2 | Generate Financial Report 1 | [8 empty] | 0 | 12.5 | -
3.3 | Generate Financial Report 2 | [8 empty] | 0 | 1.25 | -
3.4 | Generate Financial Report 3 | [6 empty] | 1 |  | - | - | -
3.5 | Generate Financial Summary Report | [8 empty] | - | - | -
4 | Research & Design | [8 empty] | 0 | 0 | N/A
4.1 | Research & Analyze Market | [8 empty] | - | - | -
4.2 | Research advertizement Revenue | [8 empty] | - | - | -
4.3 | Develop Sales Strategies | [8 empty] | 0 | - | -
4.4 | Design | [8 empty] | 0 | 0 | 0
4.4.1 | Generate App Mockups | [8 empty] | - | - | -
4.4.2 | Design Logo | [8 empty] | - | - | -
4.4.3 | Create Class Diagrams | [8 empty] | - | - | -
5 | Development | [8 empty] | 5.5 | 100.59 | 94.53%
5.1 | Source Media for App | [8 empty] | - | 4.37 | -
5.2 | Generate Icons for App | [8 empty] | - | 3.75 | -
5.3 | Software | [8 empty] | 5.5 | 92.47 | 0
5.3.1 | GUI Development | [8 empty] | 0 | 38.77 | 0
5.3.1.1 | Prototype GUI Development | [8 empty] | 0 | 38.77 | -
5.3.1.2 | Final GUI Development | [8 empty] | - | - | -
5.3.2 | App Development | [8 empty] | 5.5 | 53.7 | 0
5.3.2.1 | Prototype App Development | [8 empty] | 0 | 53.7 | -
5.3.2.2 | Final App Development | 1 |  |  |  |  | 4.25 | 0.25 |  | 5.5 | - | -
5.4 | Testing & Analysis | [8 empty] | 0 | 0 | 0
5.4.1 | GUI Testing | [8 empty] | - | - | -
5.4.2 | System Testing | [8 empty] | - | - | -
5.4.3 | Perform & gather consumer feedback | [8 empty] | - | - | -
6 | Deliverables | [8 empty] | 0 | 0 | N/A
6.1 | Functional Spec to supervisor | [8 empty] | - | - | -
6.2 | QA Manual uploaded to repository | [8 empty] | - | - | -
6.3 | Financial Business Plan submission | [8 empty] | - | - | -
6.4 | PWS Agreed between groups | [8 empty] | - | - | -
6.5 | Group tender presentations | [8 empty] | 0 | - | -
6.6 | Financial Report 1 sumbission | [8 empty] | - | - | -
6.7 | All contracts agreed and filed | [8 empty] | - | - | -
6.8 | Financial Report 2 submission | [8 empty] | - | - | -
6.9 | First iteration complete | [8 empty] | - | - | -
6.1 | Final test & integration plan | [8 empty] | - | - | -
6.11 | Financial Report 3 submission | [8 empty] | - | - | -
6.12 | Financial Summary Report submission | [8 empty] | - | - | -
6.13 | Demonstration / Sales presentation | [8 empty] | - | - | -
6.14 | Hand in of all deliverables | [8 empty] | - | - | -
Total For Team | [9 empty] | 5.5
Total Per Employee |  | 1 | 0 | 0 | 0 | 0 | 4.25 | 1.25 | 0 | 6.5
Forecast Per Employee |  | 18.2 | 7.1 | 27.2 | 8.48 | 18 | 20.3 | 22.3 | 8.6 | 130.18
Percentage Difference |  | -94.51% | -100% | -100% | -100% | -100% | -79.06% | -94.39% | -100% | -95.01%

## wk13 0204
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | [8 empty] | 0 | 16 | 100%
1.1 | Meetings | [8 empty] | 0 | 8 | -
N/A | Minutes | [8 empty] | 0 | - | -
1.2 | Performance and Document reviews (QA) | [8 empty] | 0 | 8 | -
2 | Documentation | [8 empty] | 0 | 0 | N/A
2.1 | Functional Specification | [8 empty] | 0 | 0 | 0
2.1.1 | Functional Specification Generation | [8 empty] | - | - | -
2.1.2 | Generate User Stories | [8 empty] | - | - | -
2.1.3 | Functional Specification Compilation | [8 empty] | - | - | -
2.2 | QA Manual | [8 empty] | 0 | 0 | 0
2.2.1 | Generate QA Roles & Responsibilities | [8 empty] | - | - | -
2.2.2 | Compile QA Manual | [8 empty] | - | - | -
2.3 | Generate WBS, GANNT & PERT | [8 empty] | - | - | -
2.4 | Generate PWS | [8 empty] | - | - | -
2.5 | Negotiate Inter-group contracts | [8 empty] | 0 | - | -
2.6 | Create tender presentation | [8 empty] | - | - | -
2.7 | Create Product demo presentation | [8 empty] | - | - | -
2.8 | Compile hand in document of all deliverables | [8 empty] | - | - | -
2.9 | Give Presentation | [8 empty] | - | - | -
3 | Finance | [8 empty] | 0 | 13.75 | 100%
3.1 | Generate Financial Business Plan | [8 empty] | 0 | - | -
3.2 | Generate Financial Report 1 | [8 empty] | 0 | 12.5 | -
3.3 | Generate Financial Report 2 | [8 empty] | 0 | 1.25 | -
3.4 | Generate Financial Report 3 | [6 empty] | 0.25 |  | - | - | -
3.5 | Generate Financial Summary Report | [8 empty] | - | - | -
4 | Research & Design | [8 empty] | 0 | 0 | N/A
4.1 | Research & Analyze Market | [8 empty] | - | - | -
4.2 | Research advertizement Revenue | [8 empty] | - | - | -
4.3 | Develop Sales Strategies | [8 empty] | 0 | - | -
4.4 | Design | [8 empty] | 0 | 0 | 0
4.4.1 | Generate App Mockups | [8 empty] | - | - | -
4.4.2 | Design Logo | [8 empty] | - | - | -
4.4.3 | Create Class Diagrams | [8 empty] | - | - | -
5 | Development | [8 empty] | 37.5 | 100.59 | 62.72%
5.1 | Source Media for App | [8 empty] | - | 4.37 | -
5.2 | Generate Icons for App | [8 empty] | - | 3.75 | -
5.3 | Software | [8 empty] | 37.5 | 92.47 | 0
5.3.1 | GUI Development | [8 empty] | 0 | 38.77 | 0
5.3.1.1 | Prototype GUI Development | [8 empty] | 0 | 38.77 | -
5.3.1.2 | Final GUI Development | [8 empty] | - | - | -
5.3.2 | App Development | [8 empty] | 37.5 | 53.7 | 0
5.3.2.1 | Prototype App Development |  |  | 1.75 | [5 empty] | 1.75 | 53.7 | -
5.3.2.2 | Final App Development |  | 5 | 2 | 2 |  | 24.25 | 2.5 |  | 35.75 | - | -
5.4 | Testing & Analysis | [8 empty] | 0 | 0 | 0
5.4.1 | GUI Testing | [8 empty] | - | - | -
5.4.2 | System Testing | [8 empty] | - | - | -
5.4.3 | Perform & gather consumer feedback | [8 empty] | - | - | -
6 | Deliverables | [8 empty] | 0 | 0 | N/A
6.1 | Functional Spec to supervisor | [8 empty] | - | - | -
6.2 | QA Manual uploaded to repository | [8 empty] | - | - | -
6.3 | Financial Business Plan submission | [8 empty] | - | - | -
6.4 | PWS Agreed between groups | [8 empty] | - | - | -
6.5 | Group tender presentations | [8 empty] | 0 | - | -
6.6 | Financial Report 1 sumbission | [8 empty] | - | - | -
6.7 | All contracts agreed and filed | [8 empty] | - | - | -
6.8 | Financial Report 2 submission | [8 empty] | - | - | -
6.9 | First iteration complete | [8 empty] | - | - | -
6.1 | Final test & integration plan | [8 empty] | - | - | -
6.11 | Financial Report 3 submission | [8 empty] | - | - | -
6.12 | Financial Summary Report submission | [8 empty] | - | - | -
6.13 | Demonstration / Sales presentation | [8 empty] | - | - | -
6.14 | Hand in of all deliverables | [8 empty] | - | - | -
Total For Team | [9 empty] | 37.5
Total Per Employee |  | 0 | 5 | 3.75 | 2 | 0 | 24.25 | 2.75 | 0 | 37.75
Forecast Per Employee |  | 18.2 | 7.1 | 27.2 | 8.48 | 18 | 20.3 | 22.3 | 8.6 | 130.18
Percentage Difference |  | -100% | -29.58% | -86.21% | -76.42% | -100% | 19.46% | -87.67% | -100% | -71%
contract

## wk14 0904
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | [8 empty] | 3.5 | 16 | 78.13%
1.1 | Meetings | [8 empty] | 0 | 8 | -
N/A | Minutes | [8 empty] | 0 | - | -
1.2 | Performance and Document reviews (QA) |  | 2 |  |  |  |  | 1.5 |  | 3.5 | 8 | -
2 | Documentation | [8 empty] | 0 | 0 | N/A
2.1 | Functional Specification | [8 empty] | 0 | 0 | 0
2.1.1 | Functional Specification Generation | [8 empty] | - | - | -
2.1.2 | Generate User Stories | [8 empty] | - | - | -
2.1.3 | Functional Specification Compilation | [8 empty] | - | - | -
2.2 | QA Manual | [8 empty] | 0 | 0 | 0
2.2.1 | Generate QA Roles & Responsibilities | [8 empty] | - | - | -
2.2.2 | Compile QA Manual | [8 empty] | - | - | -
2.3 | Generate WBS, GANNT & PERT | [8 empty] | - | - | -
2.4 | Generate PWS | [8 empty] | - | - | -
2.5 | Negotiate Inter-group contracts | [8 empty] | 0 | - | -
2.6 | Create tender presentation | [8 empty] | - | - | -
2.7 | Create Product demo presentation | [8 empty] | - | - | -
2.8 | Compile hand in document of all deliverables | [8 empty] | - | - | -
2.9 | Give Presentation | [8 empty] | - | - | -
3 | Finance | [8 empty] | 0 | 13.75 | 100%
3.1 | Generate Financial Business Plan | [8 empty] | 0 | - | -
3.2 | Generate Financial Report 1 | [8 empty] | 0 | 12.5 | -
3.3 | Generate Financial Report 2 | [8 empty] | 0 | 1.25 | -
3.4 | Generate Financial Report 3 | [6 empty] | 4 |  | - | - | -
3.5 | Generate Financial Summary Report | [8 empty] | - | - | -
4 | Research & Design | [8 empty] | 0 | 0 | N/A
4.1 | Research & Analyze Market | [8 empty] | - | - | -
4.2 | Research advertizement Revenue | [8 empty] | - | - | -
4.3 | Develop Sales Strategies | [8 empty] | 0 | - | -
4.4 | Design | [8 empty] | 0 | 0 | 0
4.4.1 | Generate App Mockups | [8 empty] | - | - | -
4.4.2 | Design Logo | [8 empty] | - | - | -
4.4.3 | Create Class Diagrams | [8 empty] | - | - | -
5 | Development | [8 empty] | 36.25 | 100.59 | 63.96%
5.1 | Source Media for App | [8 empty] | - | 4.37 | -
5.2 | Generate Icons for App | [8 empty] | - | 3.75 | -
5.3 | Software | [8 empty] | 36.25 | 92.47 | 0
5.3.1 | GUI Development | [8 empty] | 0 | 38.77 | 0
5.3.1.1 | Prototype GUI Development | [8 empty] | 0 | 38.77 | -
5.3.1.2 | Final GUI Development | [8 empty] | - | - | -
5.3.2 | App Development | [8 empty] | 36.25 | 53.7 | 0
5.3.2.1 | Prototype App Development |  |  | 14 | [5 empty] | 14 | 53.7 | -
5.3.2.2 | Final App Development |  | 5 | 5 |  |  | 6.25 |  | 6 | 22.25 | - | -
5.4 | Testing & Analysis | [8 empty] | 0 | 0 | 0
5.4.1 | GUI Testing | [8 empty] | - | - | -
5.4.2 | System Testing | [8 empty] | - | - | -
5.4.3 | Perform & gather consumer feedback | [8 empty] | - | - | -
6 | Deliverables | [8 empty] | 0 | 0 | N/A
6.1 | Functional Spec to supervisor | [8 empty] | - | - | -
6.2 | QA Manual uploaded to repository | [8 empty] | - | - | -
6.3 | Financial Business Plan submission | [8 empty] | - | - | -
6.4 | PWS Agreed between groups | [8 empty] | - | - | -
6.5 | Group tender presentations | [8 empty] | 0 | - | -
6.6 | Financial Report 1 sumbission | [8 empty] | - | - | -
6.7 | All contracts agreed and filed | [8 empty] | - | - | -
6.8 | Financial Report 2 submission | [8 empty] | - | - | -
6.9 | First iteration complete | [8 empty] | - | - | -
6.1 | Final test & integration plan | [8 empty] | - | - | -
6.11 | Financial Report 3 submission | [8 empty] | - | - | -
6.12 | Financial Summary Report submission | [8 empty] | - | - | -
6.13 | Demonstration / Sales presentation | [8 empty] | - | - | -
6.14 | Hand in of all deliverables | [8 empty] | - | - | -
Total For Team | [9 empty] | 39.75
Total Per Employee |  | 0 | 7 | 19 | 0 | 0 | 6.25 | 5.5 | 6 | 43.75
Forecast Per Employee |  | 18.2 | 7.1 | 27.2 | 8.48 | 18 | 20.3 | 22.3 | 8.6 | 130.18
Percentage Difference |  | -100% | -1.408% | -30.15% | -100% | -100% | -69.21% | -75.34% | -30.23% | -66.39%
contract

## wk15 1604
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | [8 empty] | 10 | 16 | 37.5%
1.1 | Meetings |  | 1 | 1 |  | 1 | 1 | 1 | 1 | 6 | 8 | -
N/A | Minutes |  | 1.5 | [6 empty] | 1.5 | - | -
1.2 | Performance and Document reviews (QA) |  | 2.5 | [6 empty] | 2.5 | 8 | -
2 | Documentation | [8 empty] | 0 | 0 | N/A
2.1 | Functional Specification | [8 empty] | 0 | 0 | 0
2.1.1 | Functional Specification Generation | [8 empty] | - | - | -
2.1.2 | Generate User Stories | [8 empty] | - | - | -
2.1.3 | Functional Specification Compilation | [8 empty] | - | - | -
2.2 | QA Manual | [8 empty] | 0 | 0 | 0
2.2.1 | Generate QA Roles & Responsibilities | [8 empty] | - | - | -
2.2.2 | Compile QA Manual | [8 empty] | - | - | -
2.3 | Generate WBS, GANNT & PERT | [8 empty] | - | - | -
2.4 | Generate PWS | [8 empty] | - | - | -
2.5 | Negotiate Inter-group contracts | [8 empty] | 0 | - | -
2.6 | Create tender presentation | [8 empty] | - | - | -
2.7 | Create Product demo presentation | [8 empty] | - | - | -
2.8 | Compile hand in document of all deliverables | [8 empty] | - | - | -
2.9 | Give Presentation | [8 empty] | - | - | -
3 | Finance | [8 empty] | 0 | 13.75 | 100%
3.1 | Generate Financial Business Plan | [8 empty] | 0 | - | -
3.2 | Generate Financial Report 1 | [8 empty] | 0 | 12.5 | -
3.3 | Generate Financial Report 2 | [8 empty] | 0 | 1.25 | -
3.4 | Generate Financial Report 3 | [6 empty] | 3.75 |  | - | - | -
3.5 | Generate Financial Summary Report | [8 empty] | - | - | -
4 | Research & Design | [8 empty] | 1 | 0 | N/A
4.1 | Research & Analyze Market | [8 empty] | - | - | -
4.2 | Research advertizement Revenue | [8 empty] | - | - | -
4.3 | Develop Sales Strategies | [7 empty] | 1 | 1 | - | -
4.4 | Design | [8 empty] | 0 | 0 | 0
4.4.1 | Generate App Mockups | [8 empty] | - | - | -
4.4.2 | Design Logo | [8 empty] | - | - | -
4.4.3 | Create Class Diagrams | [8 empty] | - | - | -
5 | Development | [8 empty] | 29.25 | 100.59 | 70.92%
5.1 | Source Media for App | 2.5 | [7 empty] | - | 4.37 | -
5.2 | Generate Icons for App | [8 empty] | - | 3.75 | -
5.3 | Software | [8 empty] | 29.25 | 92.47 | 0
5.3.1 | GUI Development | [8 empty] | 0 | 38.77 | 0
5.3.1.1 | Prototype GUI Development | [8 empty] | 0 | 38.77 | -
5.3.1.2 | Final GUI Development | [8 empty] | - | - | -
5.3.2 | App Development | [8 empty] | 29.25 | 53.7 | 0
5.3.2.1 | Prototype App Development | [8 empty] | 0 | 53.7 | -
5.3.2.2 | Final App Development | 6.25 | 4.5 | 5 |  | 3.5 |  |  | 10 | 29.25 | - | -
5.4 | Testing & Analysis | [8 empty] | 0 | 0 | 0
5.4.1 | GUI Testing | [8 empty] | - | - | -
5.4.2 | System Testing | [8 empty] | - | - | -
5.4.3 | Perform & gather consumer feedback | [8 empty] | - | - | -
6 | Deliverables | [8 empty] | 0 | 0 | N/A
6.1 | Functional Spec to supervisor | [8 empty] | - | - | -
6.2 | QA Manual uploaded to repository | [8 empty] | - | - | -
6.3 | Financial Business Plan submission | [8 empty] | - | - | -
6.4 | PWS Agreed between groups | [8 empty] | - | - | -
6.5 | Group tender presentations | [8 empty] | 0 | - | -
6.6 | Financial Report 1 sumbission | [8 empty] | - | - | -
6.7 | All contracts agreed and filed | [8 empty] | - | - | -
6.8 | Financial Report 2 submission | [8 empty] | - | - | -
6.9 | First iteration complete | [8 empty] | - | - | -
6.1 | Final test & integration plan | [8 empty] | - | - | -
6.11 | Financial Report 3 submission | [8 empty] | - | - | -
6.12 | Financial Summary Report submission | [8 empty] | - | - | -
6.13 | Demonstration / Sales presentation | [8 empty] | - | - | -
6.14 | Hand in of all deliverables | [8 empty] | - | - | -
Total For Team | [9 empty] | 40.25
Total Per Employee |  | 8.75 | 9.5 | 6 | 0 | 4.5 | 1 | 4.75 | 12 | 46.5
Forecast Per Employee |  | 18.2 | 7.1 | 27.2 | 8.48 | 18 | 20.3 | 22.3 | 8.6 | 130.18
Percentage Difference |  | -51.92% | 33.8% | -77.94% | -100% | -75% | -95.07% | -78.7% | 39.53% | -64.28%

## wk16 2304
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | [8 empty] | 9 | 16 | 43.75%
1.1 | Meetings | 1.5 | 1.5 | 1.5 |  |  |  | 1.5 | 1.5 | 7.5 | 8 | -
N/A | Minutes |  | 1.5 | [6 empty] | 1.5 | - | -
1.2 | Performance and Document reviews (QA) | [8 empty] | 0 | 8 | -
2 | Documentation | [8 empty] | 0 | 0 | N/A
2.1 | Functional Specification | [8 empty] | 0 | 0 | 0
2.1.1 | Functional Specification Generation | [8 empty] | - | - | -
2.1.2 | Generate User Stories | [8 empty] | - | - | -
2.1.3 | Functional Specification Compilation | [8 empty] | - | - | -
2.2 | QA Manual | [8 empty] | 0 | 0 | 0
2.2.1 | Generate QA Roles & Responsibilities | [8 empty] | - | - | -
2.2.2 | Compile QA Manual | [8 empty] | - | - | -
2.3 | Generate WBS, GANNT & PERT | [8 empty] | - | - | -
2.4 | Generate PWS | [8 empty] | - | - | -
2.5 | Negotiate Inter-group contracts | [8 empty] | 0 | - | -
2.6 | Create tender presentation | [8 empty] | - | - | -
2.7 | Create Product demo presentation | [8 empty] | - | - | -
2.8 | Compile hand in document of all deliverables | [8 empty] | - | - | -
2.9 | Give Presentation | [8 empty] | - | - | -
3 | Finance | [8 empty] | 0 | 13.75 | 100%
3.1 | Generate Financial Business Plan | [8 empty] | 0 | - | -
3.2 | Generate Financial Report 1 | [8 empty] | 0 | 12.5 | -
3.3 | Generate Financial Report 2 | [8 empty] | 0 | 1.25 | -
3.4 | Generate Financial Report 3 | [6 empty] | 4.5 |  | - | - | -
3.5 | Generate Financial Summary Report | [8 empty] | - | - | -
4 | Research & Design | [8 empty] | 0 | 0 | N/A
4.1 | Research & Analyze Market | [8 empty] | - | - | -
4.2 | Research advertizement Revenue | [8 empty] | - | - | -
4.3 | Develop Sales Strategies | [8 empty] | 0 | - | -
4.4 | Design | [8 empty] | 0 | 0 | 0
4.4.1 | Generate App Mockups | [8 empty] | - | - | -
4.4.2 | Design Logo | [8 empty] | - | - | -
4.4.3 | Create Class Diagrams | [8 empty] | - | - | -
5 | Development | [8 empty] | 13 | 100.59 | 87.08%
5.1 | Source Media for App | [8 empty] | - | 4.37 | -
5.2 | Generate Icons for App | [8 empty] | - | 3.75 | -
5.3 | Software | [8 empty] | 13 | 92.47 | 0
5.3.1 | GUI Development | [8 empty] | 0 | 38.77 | 0
5.3.1.1 | Prototype GUI Development | [8 empty] | 0 | 38.77 | -
5.3.1.2 | Final GUI Development | [8 empty] | - | - | -
5.3.2 | App Development | [8 empty] | 13 | 53.7 | 0
5.3.2.1 | Prototype App Development | [8 empty] | 0 | 53.7 | -
5.3.2.2 | Final App Development |  | 2 | 3 |  |  |  |  | 8 | 13 | - | -
5.4 | Testing & Analysis | [8 empty] | 0 | 0 | 0
5.4.1 | GUI Testing | [8 empty] | - | - | -
5.4.2 | System Testing | [8 empty] | - | - | -
5.4.3 | Perform & gather consumer feedback | [8 empty] | - | - | -
6 | Deliverables | [8 empty] | 0 | 0 | N/A
6.1 | Functional Spec to supervisor | [8 empty] | - | - | -
6.2 | QA Manual uploaded to repository | [8 empty] | - | - | -
6.3 | Financial Business Plan submission | [8 empty] | - | - | -
6.4 | PWS Agreed between groups | [8 empty] | - | - | -
6.5 | Group tender presentations | [8 empty] | 0 | - | -
6.6 | Financial Report 1 sumbission | [8 empty] | - | - | -
6.7 | All contracts agreed and filed | [8 empty] | - | - | -
6.8 | Financial Report 2 submission | [8 empty] | - | - | -
6.9 | First iteration complete | [8 empty] | - | - | -
6.1 | Final test & integration plan | [8 empty] | - | - | -
6.11 | Financial Report 3 submission | [8 empty] | - | - | -
6.12 | Financial Summary Report submission | [8 empty] | - | - | -
6.13 | Demonstration / Sales presentation | [8 empty] | - | - | -
6.14 | Hand in of all deliverables | [8 empty] | - | - | -
Total For Team | [9 empty] | 22
Total Per Employee |  | 1.5 | 5 | 4.5 | 0 | 0 | 0 | 6 | 9.5 | 26.5
Forecast Per Employee |  | 18.2 | 7.1 | 27.2 | 8.48 | 18 | 20.3 | 22.3 | 8.6 | 130.18
Percentage Difference |  | -91.76% | -29.58% | -83.46% | -100% | -100% | -100% | -73.09% | 10.47% | -79.64%

## wk17 3004
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | [8 empty] | 5 | 16 | 68.75%
1.1 | Meetings | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 3.5 | 8 | -
N/A | Minutes |  | 1.5 | [6 empty] | 1.5 | - | -
1.2 | Performance and Document reviews (QA) | [8 empty] | 0 | 8 | -
2 | Documentation | [8 empty] | 0 | 0 | N/A
2.1 | Functional Specification | [8 empty] | 0 | 0 | 0
2.1.1 | Functional Specification Generation | [8 empty] | - | - | -
2.1.2 | Generate User Stories | [8 empty] | - | - | -
2.1.3 | Functional Specification Compilation | [8 empty] | - | - | -
2.2 | QA Manual | [8 empty] | 0 | 0 | 0
2.2.1 | Generate QA Roles & Responsibilities | [8 empty] | - | - | -
2.2.2 | Compile QA Manual | [8 empty] | - | - | -
2.3 | Generate WBS, GANNT & PERT | [8 empty] | - | - | -
2.4 | Generate PWS | [8 empty] | - | - | -
2.5 | Negotiate Inter-group contracts | [8 empty] | 0 | - | -
2.6 | Create tender presentation | [8 empty] | - | - | -
2.7 | Create Product demo presentation | [8 empty] | - | - | -
2.8 | Compile hand in document of all deliverables | [8 empty] | - | - | -
2.9 | Give Presentation | [8 empty] | - | - | -
3 | Finance | [8 empty] | 0 | 13.75 | 100%
3.1 | Generate Financial Business Plan | [8 empty] | 0 | - | -
3.2 | Generate Financial Report 1 | [8 empty] | 0 | 12.5 | -
3.3 | Generate Financial Report 2 | [8 empty] | 0 | 1.25 | -
3.4 | Generate Financial Report 3 |  |  | 1.5 |  | 1.5 |  | 20.75 | 1.25 | - | - | -
3.5 | Generate Financial Summary Report | [8 empty] | - | - | -
4 | Research & Design | [8 empty] | 0 | 0 | N/A
4.1 | Research & Analyze Market | [8 empty] | - | - | -
4.2 | Research advertizement Revenue | [8 empty] | - | - | -
4.3 | Develop Sales Strategies | [8 empty] | 0 | - | -
4.4 | Design | [8 empty] | 0 | 0 | 0
4.4.1 | Generate App Mockups | [8 empty] | - | - | -
4.4.2 | Design Logo | [8 empty] | - | - | -
4.4.3 | Create Class Diagrams | [8 empty] | - | - | -
5 | Development | [8 empty] | 18 | 100.59 | 82.11%
5.1 | Source Media for App | [8 empty] | - | 4.37 | -
5.2 | Generate Icons for App | [8 empty] | - | 3.75 | -
5.3 | Software | [8 empty] | 18 | 92.47 | 0
5.3.1 | GUI Development | [8 empty] | 0 | 38.77 | 0
5.3.1.1 | Prototype GUI Development | [8 empty] | 0 | 38.77 | -
5.3.1.2 | Final GUI Development | [8 empty] | - | - | -
5.3.2 | App Development | [8 empty] | 18 | 53.7 | 0
5.3.2.1 | Prototype App Development | [8 empty] | 0 | 53.7 | -
5.3.2.2 | Final App Development | 5 |  | 1.5 |  |  |  | 2.25 | 9.25 | 18 | - | -
5.4 | Testing & Analysis | [8 empty] | 0 | 0 | 0
5.4.1 | GUI Testing | [8 empty] | - | - | -
5.4.2 | System Testing | [8 empty] | - | - | -
5.4.3 | Perform & gather consumer feedback | [8 empty] | - | - | -
6 | Deliverables | [8 empty] | 0 | 0 | N/A
6.1 | Functional Spec to supervisor | [8 empty] | - | - | -
6.2 | QA Manual uploaded to repository | [8 empty] | - | - | -
6.3 | Financial Business Plan submission | [8 empty] | - | - | -
6.4 | PWS Agreed between groups | [8 empty] | - | - | -
6.5 | Group tender presentations | [8 empty] | 0 | - | -
6.6 | Financial Report 1 sumbission | [8 empty] | - | - | -
6.7 | All contracts agreed and filed | [8 empty] | - | - | -
6.8 | Financial Report 2 submission | [8 empty] | - | - | -
6.9 | First iteration complete | [8 empty] | - | - | -
6.1 | Final test & integration plan | [8 empty] | - | - | -
6.11 | Financial Report 3 submission | [8 empty] | - | - | -
6.12 | Financial Summary Report submission | [8 empty] | - | - | -
6.13 | Demonstration / Sales presentation | [8 empty] | - | - | -
6.14 | Hand in of all deliverables | [8 empty] | - | - | -
Total For Team | [9 empty] | 23
Total Per Employee |  | 5.5 | 2 | 3.5 | 0.5 | 2 | 0 | 23.5 | 11 | 48
Forecast Per Employee |  | 18.2 | 7.1 | 27.2 | 8.48 | 18 | 20.3 | 22.3 | 8.6 | 130.18
Percentage Difference |  | -69.78% | -71.83% | -87.13% | -94.1% | -88.89% | -100% | 5.381% | 27.91% | -63.13%

## wk18 0705
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | [8 empty] | 6.75 | 16 | 57.81%
1.1 | Meetings | - | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 5.25 | 8 | -
N/A | Minutes |  | 1.5 | - | - | - | - | - | - | 1.5 | - | -
1.2 | Performance and Document reviews (QA) | [8 empty] | 0 | 8 | -
2 | Documentation | [8 empty] | 0 | 0 | N/A
2.1 | Functional Specification | [8 empty] | 0 | 0 | 0
2.1.1 | Functional Specification Generation | [8 empty] | - | - | -
2.1.2 | Generate User Stories | [8 empty] | - | - | -
2.1.3 | Functional Specification Compilation | [8 empty] | - | - | -
2.2 | QA Manual | [8 empty] | 0 | 0 | 0
2.2.1 | Generate QA Roles & Responsibilities |  | 1 | [6 empty] | - | - | -
2.2.2 | Compile QA Manual | [8 empty] | - | - | -
2.3 | Generate WBS, GANNT & PERT | [8 empty] | - | - | -
2.4 | Generate PWS | [8 empty] | - | - | -
2.5 | Negotiate Inter-group contracts | [8 empty] | 0 | - | -
2.6 | Create tender presentation | [8 empty] | - | - | -
2.7 | Create Product demo presentation | [8 empty] | - | - | -
2.8 | Compile hand in document of all deliverables | [8 empty] | - | - | -
2.9 | Give Presentation | [8 empty] | - | - | -
3 | Finance | [8 empty] | 0 | 13.75 | 100%
3.1 | Generate Financial Business Plan | [8 empty] | 0 | - | -
3.2 | Generate Financial Report 1 | [8 empty] | 0 | 12.5 | -
3.3 | Generate Financial Report 2 | [8 empty] | 0 | 1.25 | -
3.4 | Generate Financial Report 3 | [6 empty] | 0.25 |  | - | - | -
3.5 | Generate Financial Summary Report | [8 empty] | - | - | -
4 | Research & Design | [8 empty] | 0 | 0 | N/A
4.1 | Research & Analyze Market | [8 empty] | - | - | -
4.2 | Research advertizement Revenue | [8 empty] | - | - | -
4.3 | Develop Sales Strategies | [8 empty] | 0 | - | -
4.4 | Design | [8 empty] | 0 | 0 | 0
4.4.1 | Generate App Mockups | [8 empty] | - | - | -
4.4.2 | Design Logo | [8 empty] | - | - | -
4.4.3 | Create Class Diagrams | [8 empty] | - | - | -
5 | Development | [8 empty] | 17.25 | 100.59 | 82.85%
5.1 | Source Media for App | 0.75 | [7 empty] | - | 4.37 | -
5.2 | Generate Icons for App | [8 empty] | - | 3.75 | -
5.3 | Software | [8 empty] | 17.25 | 92.47 | 0
5.3.1 | GUI Development | [8 empty] | 0 | 38.77 | 0
5.3.1.1 | Prototype GUI Development | [8 empty] | 0 | 38.77 | -
5.3.1.2 | Final GUI Development | [8 empty] | - | - | -
5.3.2 | App Development | [8 empty] | 17.25 | 53.7 | 0
5.3.2.1 | Prototype App Development | [8 empty] | 0 | 53.7 | -
5.3.2.2 | Final App Development | 11.25 | 4 | [5 empty] | 2 | 17.25 | - | -
5.4 | Testing & Analysis | [8 empty] | 0 | 0 | 0
5.4.1 | GUI Testing | [8 empty] | - | - | -
5.4.2 | System Testing | [8 empty] | - | - | -
5.4.3 | Perform & gather consumer feedback | [8 empty] | - | - | -
6 | Deliverables | [8 empty] | 0 | 0 | N/A
6.1 | Functional Spec to supervisor | [8 empty] | - | - | -
6.2 | QA Manual uploaded to repository | [8 empty] | - | - | -
6.3 | Financial Business Plan submission | [8 empty] | - | - | -
6.4 | PWS Agreed between groups | [8 empty] | - | - | -
6.5 | Group tender presentations | [8 empty] | 0 | - | -
6.6 | Financial Report 1 sumbission | [8 empty] | - | - | -
6.7 | All contracts agreed and filed | [8 empty] | - | - | -
6.8 | Financial Report 2 submission | [8 empty] | - | - | -
6.9 | First iteration complete | [8 empty] | - | - | -
6.1 | Final test & integration plan | [8 empty] | - | - | -
6.11 | Financial Report 3 submission | [8 empty] | - | - | -
6.12 | Financial Summary Report submission | [8 empty] | - | - | -
6.13 | Demonstration / Sales presentation | [8 empty] | - | - | -
6.14 | Hand in of all deliverables | [8 empty] | - | - | -
Total For Team | [9 empty] | 24
Total Per Employee |  | 12 | 7.25 | 0.75 | 0.75 | 0.75 | 0.75 | 1 | 2.75 | 26
Forecast Per Employee |  | 18.2 | 7.1 | 27.2 | 8.48 | 18 | 20.3 | 22.3 | 8.6 | 130.18
Percentage Difference |  | -34.07% | 2.113% | -97.24% | -91.16% | -95.83% | -96.31% | -95.52% | -68.02% | -80.03%