## Monday to Wednesday Page One
Time Sheet For Miranda Lowther of SG3 Enterprise For Week Starting |  | 2018-03-12
Day | Description of Work Done | Start Time | End Time
Section/Task
Monday | Date: 12/03/2018
1 | Software Engineer: Discussed with another team member about how the recipes will be displayed in our app (layouts, views etc), since this will affect how my code is written. | 13:00 | 15:00
Team Meeting | Software Manager: The Software Manager updated the team on the current state of our app so far, and outlined the tasks that were still to be completed. | 15:00 | 16:00
2 | Software Engineer: Changed my code so far following the aforementioned discussion. | 16:00 | 18:00
3 | Finance Manager: Finished filling in timesheet for week commencing 5/3/18 | 20:00 | 20:15
Tuesday | Date: 13/03/2018
1 | Software Engineer: Researched and finalised what other code I wanted/needed to utilise. | 13:00 | 18:00
Wednesday | Date: 14/03/2018
1 | Software Engineer: Finished the rest of my code and ran it to make sure my code worked before committing/pushing it to Github. | 13:00 | 16:15
2 | Team Member: Went to the General Office with the PM and a course representative for our year to ask about applying for exceptional circumstances for our year. | 16:15 | 16:30
3 | Software Engineer: Helped with the icon images by removing the background on the timers and then creating a generic timer symbol for our app. | 16:30 | 17:45

## Monday to Wednesday Page Two
Time Sheet For Miranda Lowther of SG3 Enterprise For Week Starting |  | 2018-02-12
Day | Time spent per Milestone/Deliverable | Total Time in Hours (Rounded to the nearest 15 minutes) | Total Wages (To be calculated by the Finance Manager)
Section/Task
Monday | Date: 12/02/2018
1 | 2-M5.1.4.1: Develop App Functionality Code. | 2 | 25
Team Meeting | 1-Meeting. | 1 | 12.5
2 | 2-M5.1.4.1: Develop App Functionality Code. | 2 | 25
3 | 0.25-D14: Hand in of All Deliverables. | 0.25 | 3.125
|  | 0 | 0
Total |  | 5.25 | 65.625
Tuesday | Date: 13/02/2018
1 | 5-M5.1.4.1: Develop App Functionality Code. | 5 | 62.5
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Total |  | 5 | 62.5
Wednesday | Date: 14/02/2018
1 | 3.5-M5.1.4.1: Develop App Functionality Code. | 3.5 | 43.75
2 | 0.25-M5.1: Create App Prototype. | 0.25 | 3.125
3 | 1.25-Either M2: Design or M5.1: Create App Prototype. | 1.25 | 15.625
|  | 0 | 0
|  | 0 | 0
Total |  | 5 | 62.5

## Thursday to Sunday Page One
Time Sheet For Miranda Lowther of SG3 Enterprise For Week Starting |  | 2018-02-12
Day | Description of Work Done | Start Time | End Time
Section/Task
Thursday | Date: 15/03/2018
1 | Team Member: Went back to the General Office, and after consulting with Trudy Hilary we were advised to apply for our exceptional circumstances for our team. | 9:00 | 9:15
2 | Software Engineer: Researched and looked into testing in Android Studio, and what method of testing would be most suitable for my work. | 13:00 | 18:00
3 | Software Engineer: Researched the most suitable code for testing my work. | 20:00 | 22:00
Friday | Date: 16/03/2018
1 | Team Member: Filled in the exceptional circumstances form for myself/my team, and submitted it, as well as evidence provided by the Project Manager. | 8:30 | 10:00
2 | Software Engineer: Wrote the test for my code and commited/pushed the code for the Software Manager. | 10:45 | 11:45
Saturday | Date: 17/03/2018
Sunday | Date: 18/03/2018
1 | Finance Manager: Filled in timesheet for 12/3/18 | 10:00 | 10:30

## Thursday to Sunday Page Two
Time Sheet For Miranda Lowther of SG3 Enterprise For Week Starting |  | 2018-02-12
Day | Time spent per Milestone/Deliverable | Total Time in Hours (Rounded to the nearest 15 minutes) | Total Wages (To be calculated by the Finance Manager)
Section/Task
Thursday | Date: 15/02/2018
1 | 0.25-M5.1: Create App Prototype. | 0.25 | 3.125
2 | 5-M5.1.4.2: Test App Functionality. | 5 | 62.5
3 | 2-M5.1.4.2: Test App Functionality. | 2 | 25
|  | 0 | 0
|  | 0 | 0
Total |  | 7.25 | 90.625
Friday | Date: 16/02/2018
1 | 1.5-M5.1: Create App Prototype. | 1.5 | 18.75
2 | 1-M5.1.4.2: Test App Functionality. | 1 | 12.5
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Total |  | 2.5 | 31.25
Saturday | Date: 17/02/2018
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Total |  | 0 | 0
Sunday | Date: 18/02/2018
1 |  | 0.5 | 6.25
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Total |  | 0.5 | 6.25
|  | Week Total Hours | 25.5
|  | Week Total Wages | 318.75