## Week 17 30-04
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | 0.5 | 2 | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 5 | 16 | -68.75%
1.1 | Meetings | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | - | 0.5 | 0.5 | 3.5 | 8 | -56.25%
N/A | Minutes |  | 1.5 | - | - | - | - | - | - | 1.5 | - | N/A
1.2 | Performance and Document reviews (QA) | - | - | - | - | - | - | - | - | 0 | 8 | -100%
2 | Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1 | Functional Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1.1 | Functional Specification Generation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.2 | Generate User Stories | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.3 | Functional Specification Compilation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
2.2 | QA Manual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.2.1 | Generate QA Roles & Responsibilities | - | - | - | - | - | - | - | - | 0 | - | N/A
2.2.2 | Compile QA Manual | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
2.3 | Generate WBS, GANNT & PERT | - | - |  |  |  |  | - | - | 0 | - | N/A
2.4 | Generate PWS | - | - |  |  |  |  | - | - | 0 | - | N/A
2.5 | Negotiate Inter-group contracts | - | - | - | - | - | - | - | - | 0 | - | N/A
2.6 | Create tender presentation | [8 empty] | 0 | - | N/A
2.7 | Create Product demo presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.8 | Compile hand in document of all deliverables | - | - | - | - | - | - | - | 0 | 0 | - | N/A
2.9 | Give Presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
3 | Finance | 0 | 0 | 1.5 | 0 | 1.5 | 0 | 20.75 | 1.25 | 25 | 7.35 | 240.1%
3.1 | Generate Financial Business Plan | - | - | - | - | - | - | - | - | 0 | - | N/A
3.2 | Generate Financial Report 1 | - | - | - |  | - | - | - | - | 0 | - | N/A
3.3 | Generate Financial Report 2 | - | - | - | - | - | - | - | - | 0 |  | N/A
3.4 | Generate Financial Report 3 | - | - | 1.5 | - | 1.5 | - | 20.75 | 1.25 | 25 | 4 | 525%
3.5 | Generate Financial Summary Report | - | - | - | - | - | - | - | - | 0 | 3.35 | -100%
N/A
4 | Research & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.1 | Research & Analyze Market | - | - | - | - | - | - | - |  | 0 | - | N/A
4.2 | Research advertizement Revenue | - | - | - | - | - | - | - | - | 0 | - | N/A
4.3 | Develop Sales Strategies | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4.1 | Generate App Mockups | - | - | - |  | - | - | - | - | 0 | - | N/A
4.4.2 | Design Logo | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.3 | Create Class Diagrams | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
5 | Development | 5 | 0 | 1.5 | 0 | 0 | 0 | 2.25 | 9.25 | 18 | 49.5 | -63.64%
5.1 | Source Media for App | - | - | - | - | - | - | - | - | 0 | - | N/A
5.2 | Generate Icons for App |  | - | - | - | - | - | - | - | 0 | - | N/A
5.3 | Software | 5 | 0 | 1.5 | 0 | 0 | 0 | 2.25 | 9.25 | 18 | 15.47 | 16.35%
5.3.1 | GUI Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.17 | -100%
5.3.1.1 | Prototype GUI Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.1.2 | Final GUI Development | - | - | - | - | - | - | - | - | 0 | 9.17 | -100%
5.3.2 | App Development | 5 | 0 | 1.5 | 0 | 0 | 0 | 2.25 | 9.25 | 18 | 6.3 | 185.7%
5.3.2.1 | Prototype App Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.2.2 | Final App Development | 5 | - | 1.5 | - | - | - | 2.25 | 9.25 | 18 | 6.3 | 185.7%
5.4 | Testing & Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.03 | -100%
5.4.1 | GUI Testing | - | - | - | - | - | - | - | - | 0 | 4.43 | -100%
5.4.2 | System Testing | - | - | - | - | - | - | - | - | 0 | 29.6 | -100%
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | - | - | - | 0 | - | N/A
[10 empty] | 0 |  | N/A
6 | Deliverables | 5 | 0 | 3 | 0 | 1.5 | 0 | 23 | 10.5 | 43 | 0 | -
6.1 | Functional Spec to supervisor | - | - | - | - | - | - | - | - | 0 | - | N/A
6.2 | QA Manual uploaded to repository | - | - | - | - | - | - | - | - | 0 | - | N/A
6.3 | Financial Business Plan submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.4 | PWS Agreed between groups | - | - | - | - | - | - | - | - | 0 | - | N/A
6.5 | Group tender presentations | - | - | - | - | - | - | - | - | 0 | - | N/A
6.6 | Financial Report 1 sumbission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.7 | All contracts agreed and filed | - | - | - | - | - | - | - | - | 0 | - | N/A
6.8 | Financial Report 2 submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.9 | First iteration complete | - | - | - | - | - | - | - | - | 0 | - | N/A
6.1 | Final test & integration plan | 5 | - | 1.5 | - | - | - | 2.25 | 9.25 | 18 | - | N/A
6.11 | Financial Report 3 submission | - | - | 1.5 | - | 1.5 | - | 20.75 | 1.25 | 25 | - | N/A
6.12 | Financial Summary Report submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.13 | Demonstration / Sales presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
6.14 | Hand in of all deliverables | - | - | - | - | - | - | - | - | 0 | - | N/A
Total For Team | [9 empty] | 48 | 72.85 | -34.11%
Total Per Employee |  | 5.5 | 2 | 3.5 | 0.5 | 2 | 0 | 23.5 | 11 | 48 |  | N/A
Forecast Per Employee |  | 18.2 | 7.1 | 27.2 | 8.48 | 18 | 20.3 | 24.6 | 8.6 | 132.48 |  | N/A
Percentage Difference |  | -69.78% | -71.83% | -87.13% | -94.1% | -88.89% | -100% | -4.472% | 27.91% | -63.77% |  | N/A

## Week 18 7-05
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | 0 | 2.25 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 6.75 | 16 | -57.81%
1.1 | Meetings | - | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 5.25 | 8 | -34.38%
N/A | Minutes | - | 1.5 | - | - | - | - | - | - | 1.5 | - | N/A
1.2 | Performance and Document reviews (QA) | - | - | - | - | - | - | - | - | 0 | 8 | -100%
2 | Documentation | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -
2.1 | Functional Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1.1 | Functional Specification Generation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.2 | Generate User Stories | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.3 | Functional Specification Compilation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
2.2 | QA Manual | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | -
2.2.1 | Generate QA Roles & Responsibilities | - | 1 | - | - | - | - | - | - | 1 | - | N/A
2.2.2 | Compile QA Manual | - | - | - | - | - | - | - | - | 0 | - | N/A
2.3 | Generate WBS, GANNT & PERT | - | - | - | - | - | - | - | - | 0 | - | N/A
2.4 | Generate PWS | - | - | - | - | - | - | - | - | 0 | - | N/A
2.5 | Negotiate Inter-group contracts | - | - | - | - | - | - | - | - | 0 | - | N/A
2.6 | Create tender presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.7 | Create Product demo presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.8 | Compile hand in document of all deliverables | - | - | - | - | - | - | - | - | 0 | - | N/A
2.9 | Give Presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
3 | Finance | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0.25 | 20.1 | -98.76%
3.1 | Generate Financial Business Plan | - | - | - | - | - | - | - | - | 0 | - | N/A
3.2 | Generate Financial Report 1 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.3 | Generate Financial Report 2 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.4 | Generate Financial Report 3 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.5 | Generate Financial Summary Report | - | - | - | - | - | - | 0.25 | - | 0.25 | 20.1 | -98.76%
N/A
4 | Research & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.1 | Research & Analyze Market | - | - | - | - | - | - | - |  | 0 | - | N/A
4.2 | Research advertizement Revenue | - | - | - | - | - | - | - | - | 0 | - | N/A
4.3 | Develop Sales Strategies | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4.1 | Generate App Mockups | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.2 | Design Logo | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.3 | Create Class Diagrams | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
5 | Development | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 18 | 55.47 | -67.55%
5.1 | Source Media for App | 0.75 | - | - | - | - | - | - | - | 0.75 | - | N/A
5.2 | Generate Icons for App | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3 | Software | 11.25 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 17.25 | 0 | -
5.3.1 | GUI Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5.3.1.1 | Prototype GUI Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.1.2 | Final GUI Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.2 | App Development | 11.25 | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 17.25 | 0 | -
5.3.2.1 | Prototype App Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.2.2 | Final App Development | 11.25 | 4 | - | - | - | - | - | 2 | 17.25 | - | N/A
5.4 | Testing & Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.47 | -100%
5.4.1 | GUI Testing | - | - | - | - | - | - | - | - | 0 | 9.57 | -100%
5.4.2 | System Testing | - | - | - | - | - | - | - | - | 0 | 44.4 | -100%
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | - | - | - | 0 | 1.5 | -100%
[10 empty] | 0 |  | N/A
6 | Deliverables | 13 | 4 | 0 | 0 | 0 | 0 | 8.25 | 6.5 | 31.75 | 0 | -
6.1 | Functional Spec to supervisor | - | - | - | - | - | - | - | - | 0 | - | N/A
6.2 | QA Manual uploaded to repository | - | - | - | - | - | - | - | - | 0 | - | N/A
6.3 | Financial Business Plan submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.4 | PWS Agreed between groups | - | - | - | - | - | - | - | - | 0 | - | N/A
6.5 | Group tender presentations | - | - | - | - | - | - | - | - | 0 | - | N/A
6.6 | Financial Report 1 sumbission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.7 | All contracts agreed and filed | - | - | - | - | - | - | - | - | 0 | - | N/A
6.8 | Financial Report 2 submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.9 | First iteration complete | - | - | - | - | - | - | - | - | 0 | - | N/A
6.1 | Final test & integration plan | 13 | 4 | - | - | - | - | 8 | 6.5 | 31.5 | - | N/A
6.11 | Financial Report 3 submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.12 | Financial Summary Report submission | - | - | - | - | - | - | 0.25 | - | 0.25 | - | N/A
6.13 | Demonstration / Sales presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
6.14 | Hand in of all deliverables | - | - | - | - | - | - | - | - | 0 | - | N/A
Total For Team | [9 empty] | 26 | 91.57 | -71.61%
Total Per Employee |  | 12 | 7.25 | 0.75 | 0.75 | 0.75 | 0.75 | 1 | 2.75 | 26 |  | N/A
Forecast Per Employee |  | 12 | 6.68 | 28.1 | 8.48 | 18 | 18.6 | 13.4 | 7.88 | 113.14 |  | N/A
Percentage Difference |  | 0% | 8.533% | -97.33% | -91.16% | -95.83% | -95.97% | -92.54% | -65.1% | -77.02% |  | N/A

## Week 19 14-05
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | -100%
1.1 | Meetings | - | - | - | - | - | - | - | - | 0 | 8 | -100%
N/A | Minutes | - | - | - | - | - | - | - | - | 0 | - | N/A
1.2 | Performance and Document reviews (QA) | - | - | - | - | - | - | - | - | 0 | 8 | -100%
2 | Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.1 | -100%
2.1 | Functional Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1.1 | Functional Specification Generation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.2 | Generate User Stories | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.3 | Functional Specification Compilation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
2.2 | QA Manual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.2.1 | Generate QA Roles & Responsibilities | - | - | - | - | - | - | - | - | 0 | - | N/A
2.2.2 | Compile QA Manual | - | - | - | - | - | - | - | - | 0 | - | N/A
2.3 | Generate WBS, GANNT & PERT | - | - | - | - | - | - | - | - | 0 | - | N/A
2.4 | Generate PWS | - | - | - | - | - | - | - | - | 0 | - | N/A
2.5 | Negotiate Inter-group contracts | - | - | - | - | - | - | - | - | 0 | - | N/A
2.6 | Create tender presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.7 | Create Product demo presentation | - | - | - | - | - | - | - | - | 0 | 26.1 | -100%
2.8 | Compile hand in document of all deliverables | - | - | - | - | - | - | - | - | 0 | - | N/A
2.9 | Give Presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
3 | Finance | 0 | 0 | 0 | 3 | 0 | 0 | 4.75 | 0 | 7.75 | 20.1 | -61.44%
3.1 | Generate Financial Business Plan | - | - | - | - | - | - | - | - | 0 | - | N/A
3.2 | Generate Financial Report 1 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.3 | Generate Financial Report 2 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.4 | Generate Financial Report 3 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.5 | Generate Financial Summary Report | - | - | - | 3 | - | - | 4.75 | - | 7.75 | 20.1 | -61.44%
N/A
4 | Research & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.1 | Research & Analyze Market | - | - | - | - | - | - | - |  | 0 | - | N/A
4.2 | Research advertizement Revenue | - | - | - | - | - | - | - | - | 0 | - | N/A
4.3 | Develop Sales Strategies | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4.1 | Generate App Mockups | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.2 | Design Logo | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.3 | Create Class Diagrams | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
5 | Development | 5.5 | 0 | 5.25 | 0 | 3 | 0 | 0 | 0 | 13.75 | 7.5 | 83.33%
5.1 | Source Media for App | 4.5 | - | - | - | - | - | - | - | 4.5 | - | N/A
5.2 | Generate Icons for App | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3 | Software | 1 | 0 | 5.25 | 0 | 3 | 0 | 0 | 0 | 9.25 | 0 | -
5.3.1 | GUI Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5.3.1.1 | Prototype GUI Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.1.2 | Final GUI Development | - | - | - | - | - | - | - | - | 0 |  | N/A
5.3.2 | App Development | 1 | 0 | 5.25 | 0 | 3 | 0 | 0 | 0 | 9.25 | 0 | -
5.3.2.1 | Prototype App Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.2.2 | Final App Development | 1 | - | 5.25 | - | 3 | - | - | - | 9.25 | - | N/A
5.4 | Testing & Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | -100%
5.4.1 | GUI Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.2 | System Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | - | - | - | 0 | 7.5 | -100%
[10 empty] | 0 |  | N/A
6 | Deliverables | 5.5 | 0 | 5.25 | 3 | 3 | 0 | 4.75 | 0 | 21.5 | 0 | -
6.1 | Functional Spec to supervisor | - | - | - | - | - | - | - | - | 0 | - | N/A
6.2 | QA Manual uploaded to repository | - | - | - | - | - | - | - | - | 0 | - | N/A
6.3 | Financial Business Plan submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.4 | PWS Agreed between groups | - | - | - | - | - | - | - | - | 0 | - | N/A
6.5 | Group tender presentations | - | - | - | - | - | - | - | - | 0 | - | N/A
6.6 | Financial Report 1 sumbission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.7 | All contracts agreed and filed | - | - | - | - | - | - | - | - | 0 | - | N/A
6.8 | Financial Report 2 submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.9 | First iteration complete | - | - | - | - | - | - | - | - | 0 | - | N/A
6.1 | Final test & integration plan | 5.5 | - | 5.25 | - | 3 | - | - | - | 13.75 | - | N/A
6.11 | Financial Report 3 submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.12 | Financial Summary Report submission | - | - | - | 3 | - | - | 4.75 | - | 7.75 | - | N/A
6.13 | Demonstration / Sales presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
6.14 | Hand in of all deliverables | - | - | - | - | - | - | - | - | 0 | - | N/A
Total For Team | [9 empty] | 21.5 | 69.7 | -69.15%
Total Per Employee |  | 5.5 | 0 | 5.25 | 3 | 3 | 0 | 4.75 | 0 | 21.5 |  | N/A
Forecast Per Employee |  | 12 | 6.68 | 28.1 | 8.48 | 18 | 18.6 | 13.4 | 7.88 | 113.14 |  | N/A
Percentage Difference |  | -54.17% | -100% | -81.32% | -64.62% | -83.33% | -100% | -64.55% | -100% | -81% |  | N/A

## Week 20 21-05
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | 0.75 | 1.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0 | 6.25 | 16 | -60.94%
1.1 | Meetings | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 |  | 5.25 | 8 | -34.38%
N/A | Minutes | - | 1 | - | - | - | - | - | - | 1 | - | N/A
1.2 | Performance and Document reviews (QA) | - | - | - | - | - | - | - | - | 0 | 8 | -100%
2 | Documentation | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 45.3 | -95.58%
2.1 | Functional Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1.1 | Functional Specification Generation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.2 | Generate User Stories | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.3 | Functional Specification Compilation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
2.2 | QA Manual | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | -
2.2.1 | Generate QA Roles & Responsibilities | - | - | - | - | - | - | - | - | 0 | - | N/A
2.2.2 | Compile QA Manual | - | 2 | - | - | - | - | - | - | 2 | - | N/A
2.3 | Generate WBS, GANNT & PERT | - | - | - | - | - | - | - | - | 0 | - | N/A
2.4 | Generate PWS | - | - | - | - | - | - | - | - | 0 | - | N/A
2.5 | Negotiate Inter-group contracts | - | - | - | - | - | - | - | - | 0 | - | N/A
2.6 | Create tender presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.7 | Create Product demo presentation | - | - | - | - | - | - | - | - | 0 | 36.23 | -100%
2.8 | Compile hand in document of all deliverables | - | - | - | - | - | - | - | - | 0 | 9.07 | -100%
2.9 | Give Presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
3 | Finance | 0.25 | 0 | 0.5 | 8.25 | 0 | 1.5 | 31.5 | 1.5 | 43.5 | 16 | 171.9%
3.1 | Generate Financial Business Plan | - | - | - | - | - | - | - | - | 0 | - | N/A
3.2 | Generate Financial Report 1 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.3 | Generate Financial Report 2 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.4 | Generate Financial Report 3 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.5 | Generate Financial Summary Report | 0.25 | - | 0.5 | 8.25 | - | 1.5 | 31.5 | 1.5 | 43.5 | 16 | 171.9%
N/A
4 | Research & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.25 | 10.25 | 0 | +
4.1 | Research & Analyze Market | - | - | - | - | - | - | - | 10.25 | 10.25 | - | N/A
4.2 | Research advertizement Revenue | - | - | - | - | - | - | - | - | 0 | - | N/A
4.3 | Develop Sales Strategies | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4.1 | Generate App Mockups | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.2 | Design Logo | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.3 | Create Class Diagrams | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
5 | Development | 8.5 | 5.75 | 35.75 | 1.75 | 18.75 | 2.5 | 0 | 15.25 | 88.25 | 7.5 | 1077%
5.1 | Source Media for App | 1.75 | - | - | 1.75 | 1.75 | - | - | - | 5.25 | - | N/A
5.2 | Generate Icons for App | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3 | Software | 6.75 | 5.75 | 35.75 | 0 | 17 | 2.5 | 0 | 15.25 | 83 | 0 | -
5.3.1 | GUI Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5.3.1.1 | Prototype GUI Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.1.2 | Final GUI Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.2 | App Development | 6.75 | 5.75 | 35.75 | 0 | 17 | 2.5 | 0 | 15.25 | 83 | 0 | -
5.3.2.1 | Prototype App Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.2.2 | Final App Development | 6.75 | 5.75 | 35.75 | - | 17 | 2.5 | - | 15.25 | 83 | - | N/A
5.4 | Testing & Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | -100%
5.4.1 | GUI Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.2 | System Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | - | - | - | 0 | 7.5 | -100%
[10 empty] | 0 |  | N/A
6 | Deliverables | 8.5 | 7.75 | 36.25 | 8.25 | 18.75 | 4 | 31.5 | 27 | 142 | 0 | -
6.1 | Functional Spec to supervisor | - | - | - | - | - | - | - | - | 0 | - | N/A
6.2 | QA Manual uploaded to repository | - | 2 | - | - | - | - | - | - | 2 | - | N/A
6.3 | Financial Business Plan submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.4 | PWS Agreed between groups | - | - | - | - | - | - | - | - | 0 | - | N/A
6.5 | Group tender presentations | - | - | - | - | - | - | - | - | 0 | - | N/A
6.6 | Financial Report 1 sumbission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.7 | All contracts agreed and filed | - | - | - | - | - | - | - | - | 0 | - | N/A
6.8 | Financial Report 2 submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.9 | First iteration complete | - | - | - | - | - | - | - | - | 0 | - | N/A
6.1 | Final test & integration plan | 8.5 | 5.75 | 35.75 | - | 18.75 | 2.5 | - | 15.25 | 86.5 | - | N/A
6.11 | Financial Report 3 submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.12 | Financial Summary Report submission | - | - | 0.5 | 8.25 |  | 1.5 | 31.5 | 11.75 | 53.5 | - | N/A
6.13 | Demonstration / Sales presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
6.14 | Hand in of all deliverables | - | - | - | - | - | - | - | - | 0 | - | N/A
Total For Team | [9 empty] | 150.25 | 84.8 | 77.18%
Total Per Employee |  | 9.5 | 9.5 | 37 | 10.75 | 19.5 | 4.75 | 32.25 | 27 | 150.25 |  | N/A
Forecast Per Employee |  | 12 | 6.68 | 28.1 | 8.48 | 18 | 18.6 | 13.4 | 7.88 | 113.14 |  | N/A
Percentage Difference |  | -20.83% | 42.22% | 31.67% | 26.77% | 8.333% | -74.46% | 140.7% | 242.6% | 32.8% |  | N/A

## Week 21 28-05
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | 0.75 | 1.25 | 0.75 | 0 | 0.75 | 1.25 | 0.5 | 1.25 | 6.5 | 16 | -59.38%
1.1 | Meetings | 0.75 | 1.25 | 0.75 | - | 0.75 | 1.25 | 0.5 | 1.25 | 6.5 | 8 | -18.75%
N/A | Minutes | - | - | - | - | - | - | - | - | 0 | - | N/A
1.2 | Performance and Document reviews (QA) | - | - | - | - | - | - | - | - | 0 | 8 | -100%
2 | Documentation | 6.25 | 7.75 | 0 | 8 | 6.5 | 9.75 | 10.5 | 14 | 62.75 | 79.5 | -21.07%
2.1 | Functional Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1.1 | Functional Specification Generation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.2 | Generate User Stories | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.3 | Functional Specification Compilation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
2.2 | QA Manual | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | -
2.2.1 | Generate QA Roles & Responsibilities | - | - | - | - | - | - | - | - | 0 | - | N/A
2.2.2 | Compile QA Manual | - | 0.75 | - | - | - | - | - | - | 0.75 | - | N/A
2.3 | Generate WBS, GANNT & PERT | - | - | - | - | - | - | - | - | 0 | - | N/A
2.4 | Generate PWS | - | - | - | - | - | - | - | - | 0 | - | N/A
2.5 | Negotiate Inter-group contracts | - | - | - | - | - | - | - | - | 0 | - | N/A
2.6 | Create tender presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.7 | Create Product demo presentation | 6.25 | 4.5 | - | 6 | 6.5 | 2.5 | 10.5 | 14 | 50.25 | 34.2 | 46.93%
2.8 | Compile hand in document of all deliverables | - | 2.5 | - | 2 | - | 7.25 | - | - | 11.75 | 45.3 | -74.06%
2.9 | Give Presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
3 | Finance | 0 | 0 | 0 | 2 | 0 | 0 | 17.25 | 0 | 19.25 | 16 | 20.31%
3.1 | Generate Financial Business Plan | - | - | - | - | - | - | - | - | 0 | - | N/A
3.2 | Generate Financial Report 1 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.3 | Generate Financial Report 2 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.4 | Generate Financial Report 3 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.5 | Generate Financial Summary Report | - | - | - | 2 | - | - | 17.25 | - | 19.25 | 16 | 20.31%
N/A
4 | Research & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.1 | Research & Analyze Market | - | - | - | - | - | - | - | - | 0 | - | N/A
4.2 | Research advertizement Revenue | - | - | - | - | - | - | - | - | 0 | - | N/A
4.3 | Develop Sales Strategies | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4.1 | Generate App Mockups | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.2 | Design Logo | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.3 | Create Class Diagrams | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
5 | Development | 5 | 13.25 | 40 | 6 | 31.75 | 2 | 33.25 | 22.5 | 153.75 | 3.5 | 4293%
5.1 | Source Media for App | - | - | - | - | 5.25 | - | - | - | 5.25 | - | N/A
5.2 | Generate Icons for App | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3 | Software | 5 | 13.25 | 40 | 6 | 26.5 | 2 | 33.25 | 22.5 | 148.5 | 0 | -
5.3.1 | GUI Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5.3.1.1 | Prototype GUI Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.1.2 | Final GUI Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.2 | App Development | 5 | 13.25 | 40 | 6 | 26.5 | 2 | 33.25 | 22.5 | 148.5 | 0 | -
5.3.2.1 | Prototype App Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.2.2 | Final App Development | 5 | 13.25 | 40 | 6 | 26.5 | 2 | 33.25 | 22.5 | 148.5 | - | N/A
5.4 | Testing & Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | -100%
5.4.1 | GUI Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.2 | System Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | - | - | - | 0 | 3.5 | -100%
[10 empty] | 0 |  | N/A
6 | Deliverables | 11.25 | 20.25 | 40 | 16 | 38.25 | 11.75 | 61 | 37 | 235.5 | 0 | -
6.1 | Functional Spec to supervisor | - | - | - | - | - | - | - | - | 0 | - | N/A
6.2 | QA Manual uploaded to repository | - | - | - | - | - | - | - | - | 0 | - | N/A
6.3 | Financial Business Plan submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.4 | PWS Agreed between groups | - | - | - | - | - | - | - | - | 0 | - | N/A
6.5 | Group tender presentations | - | - | - | - | - | - | - | - | 0 | - | N/A
6.6 | Financial Report 1 sumbission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.7 | All contracts agreed and filed | - | - | - | - | - | - | - | - | 0 | - | N/A
6.8 | Financial Report 2 submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.9 | First iteration complete | - | - | - | - | - | - | - | - | 0 | - | N/A
6.1 | Final test & integration plan | 5 | 13.25 | 40 | 6 | 31.75 | 2 | 33.25 | 22.5 | 153.75 | - | N/A
6.11 | Financial Report 3 submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.12 | Financial Summary Report submission | - | - | - | 2 |  | - | 17.25 | 14.5 | 33.75 | - | N/A
6.13 | Demonstration / Sales presentation | 6.25 | 4.5 | - | 6 | 6.5 | 2.5 | 10.5 | - | 36.25 | - | N/A
6.14 | Hand in of all deliverables | - | 2.5 | - | 2 | - | 7.25 | - | - | 11.75 | - | N/A
Total For Team | [9 empty] | 242.25 | 115 | 110.7%
Total Per Employee |  | 12 | 22.25 | 40.75 | 16 | 39 | 13 | 61.5 | 37.75 | 242.25 |  | N/A
Forecast Per Employee |  | 12 | 6.68 | 28.1 | 8.48 | 18 | 18.6 | 13.4 | 7.88 | 113.14 |  | N/A
Percentage Difference |  | 0% | 233.1% | 45.02% | 88.68% | 116.7% | -30.11% | 359% | 379.1% | 114.1% |  | N/A

## WBS F Vs A Stacked Column Chart
ACTUAL (hrs) | [7 empty] | FORECAST (hrs)
WBS | Date | 2018-04-30 | 2018-05-07 | 2018-05-14 | 2018-05-21 | 2018-05-28 | TOTAL | Date | 2018-04-30 | 2018-05-07 | 2018-05-14 | 2018-05-21 | 2018-05-28 | TOTAL
1 | Meetings | 5 | 6.75 | 0 | 6.25 | 6.5 | 24.5 | Meetings | 16 | 16 | 16 | 16 | 16 | 80
1.1 | Meetings | 3.5 | 5.25 | 0 | 5.25 | 6.5 | 20.5 | Meetings | 8 | 8 | 8 | 8 | 8 | 40
N/A | Minutes | 1.5 | 1.5 | 0 | 1 | 0 | 4 | Minutes | - | - | - | - | - | 0
1.2 | Performance and Document reviews (QA) | 0 | 0 | 0 | 0 | 0 | 0 | Performance and Document reviews (QA) | 8 | 8 | 8 | 8 | 8 | 40
2 | Documentation | 0 | 1 | 0 | 2 | 62.75 | 65.75 | Documentation | 0 | 0 | 26.1 | 45.3 | 45.3 | 116.7
2.1 | Functional Specification | 0 | 0 | 0 | 0 | 0 | 0 | Functional Specification | 0 | 0 | 0 | 0 | 0 | 0
2.1.1 | Functional Specification Generation | 0 | 0 | 0 | 0 | 0 | 0 | Functional Specification Generation | - | - | - | - | - | 0
2.1.2 | Generate User Stories | 0 | 0 | 0 | 0 | 0 | 0 | Generate User Stories | - | - | - | - | - | 0
2.1.3 | Functional Specification Compilation | 0 | 0 | 0 | 0 | 0 | 0 | Functional Specification Compilation | - | - | - | - | - | 0
[9 empty] | 0 | 0 | 0 | 0 | 0
2.2 | QA Manual | 0 | 1 | 0 | 2 | 0.75 | 3.75 | QA Manual | 0 | 0 | 0 | 0 | 0 | 0
2.2.1 | Generate QA Roles & Responsibilities | 0 | 1 | 0 | 0 | 0 | 1 | Generate QA Roles & Responsibilities | - | - | - | - | - | 0
2.2.2 | Compile QA Manual | 0 | 0 | 0 | 2 | 0.75 | 2.75 | Compile QA Manual | - | - | - | - | - | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2.3 | Generate WBS, GANNT & PERT | 0 | 0 | 0 | 0 | 0 | 0 | Generate WBS, GANNT & PERT | - | - | - | - | - | 0
2.4 | Generate PWS | 0 | 0 | 0 | 0 | 0 | 0 | Generate PWS | - | - | - | - | - | 0
2.5 | Negotiate Inter-group contracts | 0 | 0 | 0 | 0 | 0 | 0 | Negotiate Inter-group contracts | - | - | - | - | - | 0
2.6 | Create tender presentation | 0 | 0 | 0 | 0 | 0 | 0 | Create tender presentation | - | - | - | - | - | 0
2.7 | Create Product demo presentation | 0 | 0 | 0 | 0 | 50.25 | 50.25 | Create Product demo presentation | - | - | 26.1 | 36.23 | 36.23 | 98.56
2.8 | Compile hand in document of all deliverables | 0 | 0 | 0 | 0 | 11.75 | 11.75 | Compile hand in document of all deliverables | - | - | - | 9.07 | 9.07 | 18.14
2.9 | Give Presentation | 0 | 0 | 0 | 0 | 0 | 0 | Give Presentation | - | - | - | - | - | 0
[9 empty] | 0 | 0 | 0 | 0 | 0
3 | Finance | 25 | 0.25 | 7.75 | 43.5 | 19.25 | 95.75 | Finance | 7.35 | 20.1 | 20.1 | 16 | 16 | 79.55
3.1 | Generate Financial Business Plan | 0 | 0 | 0 | 0 | 0 | 0 | Generate Financial Business Plan | - | - | - | - | - | 0
3.2 | Generate Financial Report 1 | 0 | 0 | 0 | 0 | 0 | 0 | Generate Financial Report 1 | - | - | - | - | - | 0
3.3 | Generate Financial Report 2 | 0 | 0 | 0 | 0 | 0 | 0 | Generate Financial Report 2 | 0 | - | - | - | - | 0
3.4 | Generate Financial Report 3 | 25 | 0 | 0 | 0 | 0 | 25 | Generate Financial Report 3 | 4 | - | - | - | - | 4
3.5 | Generate Financial Summary Report | 0 | 0.25 | 7.75 | 43.5 | 19.25 | 70.75 | Generate Financial Summary Report | 3.35 | 20.1 | 20.1 | 16 | 16 | 75.55
[9 empty] | 0 | 0 | 0 | 0 | 0
4 | Research & Design | 0 | 0 | 0 | 10.25 | 0 | 10.25 | Research & Design | 0 | 0 | 0 | 0 | 0 | 0
4.1 | Research & Analyze Market | 0 | 0 | 0 | 10.25 | 0 | 10.25 | Research & Analyze Market | - | - | - | - | - | 0
4.2 | Research advertizement Revenue | 0 | 0 | 0 | 0 | 0 | 0 | Research advertizement Revenue | - | - | - | - | - | 0
4.3 | Develop Sales Strategies | 0 | 0 | 0 | 0 | 0 | 0 | Develop Sales Strategies | - | - | - | - | - | 0
4.4 | Design | 0 | 0 | 0 | 0 | 0 | 0 | Design | 0 | 0 | 0 | 0 | 0 | 0
4.4.1 | Generate App Mockups | 0 | 0 | 0 | 0 | 0 | 0 | Generate App Mockups | - | - | - | - | - | 0
4.4.2 | Design Logo | 0 | 0 | 0 | 0 | 0 | 0 | Design Logo | - | - | - | - | - | 0
4.4.3 | Create Class Diagrams | 0 | 0 | 0 | 0 | 0 | 0 | Create Class Diagrams | - | - | - | - | - | 0
[9 empty] | 0 | 0 | 0 | 0 | 0
5 | Development | 18 | 18 | 13.75 | 88.25 | 153.75 | 291.75 | Development | 49.5 | 55.47 | 7.5 | 7.5 | 7.5 | 127.47
5.1 | Source Media for App | 0 | 0.75 | 4.5 | 5.25 | 5.25 | 15.75 | Source Media for App | - | - | - | - | - | 0
5.2 | Generate Icons for App | 0 | 0 | 0 | 0 | 0 | 0 | Generate Icons for App | - | - | - | - | - | 0
5.3 | Software | 18 | 17.25 | 9.25 | 83 | 148.5 | 276 | Software | 15.47 | 0 | 0 | 0 | 0 | 15.47
5.3.1 | GUI Development | 0 | 0 | 0 | 0 | 0 | 0 | GUI Development | 9.17 | 0 | 0 | 0 | 0 | 9.17
5.3.1.1 | Prototype GUI Development | 0 | 0 | 0 | 0 | 0 | 0 | Prototype GUI Development | - | - | 0 | - | - | 0
5.3.1.2 | Final GUI Development | 0 | 0 | 0 | 0 | 0 | 0 | Final GUI Development | 9.17 | - | - | - | - | 9.17
5.3.2 | App Development | 18 | 17.25 | 9.25 | 83 | 148.5 | 276 | App Development | 6.3 | 0 | 0 | 0 | 0 | 6.3
5.3.2.1 | Prototype App Development | 0 | 0 | 0 | 0 | 0 | 0 | Prototype App Development | - | - | - | - | - | 0
5.3.2.2 | Final App Development | 18 | 17.25 | 9.25 | 83 | 148.5 | 276 | Final App Development | 6.3 | - | - | - | - | 6.3
5.4 | Testing & Analysis | 0 | 0 | 0 | 0 | 0 | 0 | Testing & Analysis | 34.03 | 55.47 | 7.5 | 7.5 | 7.5 | 112
5.4.1 | GUI Testing | 0 | 0 | 0 | 0 | 0 | 0 | GUI Testing | 4.43 | 9.57 | - | - | - | 14
5.4.2 | System Testing | 0 | 0 | 0 | 0 | 0 | 0 | System Testing | 29.6 | 44.4 | - | - | - | 74
5.4.3 | Perform & gather consumer feedback | 0 | 0 | 0 | 0 | 0 | 0 | Perform & gather consumer feedback | - | 1.5 | 7.5 | 7.5 | 7.5 | 24
[5 empty] | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0
6 | Deliverables | 43 | 31.75 | 21.5 | 142 | 235.5 | 473.75 | Deliverables | 0 | 0 | 0 | 0 | 0 | 0
6.1 | Functional Spec to supervisor | 0 | 0 | 0 | 0 | 0 | 0 | Functional Spec to supervisor | - | - | - | - | - | 0
6.2 | QA Manual uploaded to repository | 0 | 0 | 0 | 2 | 0 | 2 | QA Manual uploaded to repository | - | - | - | - | - | 0
6.3 | Financial Business Plan submission | 0 | 0 | 0 | 0 | 0 | 0 | Financial Business Plan submission | - | - | - | - | - | 0
6.4 | PWS Agreed between groups | 0 | 0 | 0 | 0 | 0 | 0 | PWS Agreed between groups | - | - | - | - | - | 0
6.5 | Group tender presentations | 0 | 0 | 0 | 0 | 0 | 0 | Group tender presentations | - | - | - | - | - | 0
6.6 | Financial Report 1 sumbission | 0 | 0 | 0 | 0 | 0 | 0 | Financial Report 1 sumbission | - | - | - | - | - | 0
6.7 | All contracts agreed and filed | 0 | 0 | 0 | 0 | 0 | 0 | All contracts agreed and filed | - | - | - | - | - | 0
6.8 | Financial Report 2 submission | 0 | 0 | 0 | 0 | 0 | 0 | Financial Report 2 submission | - | - | - | - | - | 0
6.9 | First iteration complete | 0 | 0 | 0 | 0 | 0 | 0 | First iteration complete | - | - | - | - | - | 0
6.1 | Final test & integration plan | 18 | 31.5 | 13.75 | 86.5 | 153.75 | 303.5 | Final test & integration plan | - | - | - | - | - | 0
6.11 | Financial Report 3 submission | 25 | 0 | 0 | 0 | 0 | 25 | Financial Report 3 submission | - | - | - | - | - | 0
6.12 | Financial Summary Report submission | 0 | 0.25 | 7.75 | 53.5 | 33.75 | 95.25 | Financial Summary Report submission | - | - | - | - | - | 0
6.13 | Demonstration / Sales presentation | 0 | 0 | 0 | 0 | 36.25 | 36.25 | Demonstration / Sales presentation | - | - | - | - | - | 0
6.14 | Hand in of all deliverables | 0 | 0 | 0 | 0 | 11.75 | 11.75 | Hand in of all deliverables | - | - | - | - | - | 0

## WBS F Vs A Cluster Column Chart
Week # | 17 | 18 | 19 | 20 | 21
Date | 2018-04-30 | 2018-05-07 | 2018-05-14 | 2018-05-21 | 2018-05-28
Forecast Work Hours | 72.85 | 91.57 | 69.7 | 84.8 | 84.8
Actual Hours Worked | 48 | 26 | 21.5 | 150.25 | 242.25
Difference (%) | -34.11% | -71.61% | -69.15% | 77.18% | 185.7%

## TEMPLATE
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | +
1.1 | Meetings | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A | Minutes | - | - | - | - | - | - | - | - | 0 | - | N/A
1.2 | Performance and Document reviews (QA) | - | - | - | - | - | - | - | - | 0 | - | N/A
2 | Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1 | Functional Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1.1 | Functional Specification Generation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.2 | Generate User Stories | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.3 | Functional Specification Compilation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
2.2 | QA Manual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.2.1 | Generate QA Roles & Responsibilities | - | - | - | - | - | - | - | - | 0 | - | N/A
2.2.2 | Compile QA Manual | - | - | - | - | - | - | - | - | 0 | - | N/A
2.3 | Generate WBS, GANNT & PERT | - | - | - | - | - | - | - | - | 0 | - | N/A
2.4 | Generate PWS | - | - | - | - | - | - | - | - | 0 | - | N/A
2.5 | Negotiate Inter-group contracts | - | - | - | - | - | - | - | - | 0 | - | N/A
2.6 | Create tender presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.7 | Create Product demo presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.8 | Compile hand in document of all deliverables | - | - | - | - | - | - | - | - | 0 | - | N/A
2.9 | Give Presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
3 | Finance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
3.1 | Generate Financial Business Plan | - | - | - | - | - | - | - | - | 0 | - | N/A
3.2 | Generate Financial Report 1 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.3 | Generate Financial Report 2 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.4 | Generate Financial Report 3 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.5 | Generate Financial Summary Report | - | - | - | - | - | - | - | - | 0 | - | N/A
4 | Research & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.1 | Research & Analyze Market | - | - | - | - | - | - | - |  | 0 | - | N/A
4.2 | Research advertizement Revenue | - | - | - | - | - | - | - | - | 0 | - | N/A
4.3 | Develop Sales Strategies | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4.1 | Generate App Mockups | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.2 | Design Logo | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.3 | Create Class Diagrams | - | - | - | - | - | - | - | - | 0 | - | N/A
5 | Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5.1 | Source Media for App | - | - | - | - | - | - | - | - | 0 | - | N/A
5.2 | Generate Icons for App |  | - | - | - | - | - | - | - | 0 | - | N/A
5.3 | Software | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5.3.1 | GUI Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5.3.1.1 | Prototype GUI Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.1.2 | Final GUI Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.2 | App Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5.3.2.1 | Prototype App Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.2.2 | Final App Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4 | Testing & Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5.4.1 | GUI Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.2 | System Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | - | - | - | 0 | - | N/A
6 | Deliverables | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
6.1 | Functional Spec to supervisor | - | - | - | - | - | - | - | - | 0 | - | N/A
6.2 | QA Manual uploaded to repository | - | - | - | - | - | - | - | - | 0 | - | N/A
6.3 | Financial Business Plan submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.4 | PWS Agreed between groups | - | - | - | - | - | - | - | - | 0 | - | N/A
6.5 | Group tender presentations | - | - | - | - | - | - | - | - | 0 | - | N/A
6.6 | Financial Report 1 sumbission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.7 | All contracts agreed and filed | - | - | - | - | - | - | - | - | 0 | - | N/A
6.8 | Financial Report 2 submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.9 | First iteration complete | - | - | - | - | - | - | - | - | 0 | - | N/A
6.1 | Final test & integration plan | - | - | - | - | - | - | - | - | 0 | - | N/A
6.11 | Financial Report 3 submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.12 | Financial Summary Report submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.13 | Demonstration / Sales presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
6.14 | Hand in of all deliverables | - | - | - | - | - | - | - | - | 0 | - | N/A
Total For Team | [9 empty] | 0 | 0 | 0%
Total Per Employee |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | N/A
Forecast Per Employee |  | - | - | - | - | - | - | - | - | 0 |  | N/A
Percentage Difference |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #DIV/0! |  | N/A