## Week 9 5-03
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | 1 | 1.25 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 0.25 | 5.5 | 16 | -65.63%
1.1 | Meetings | 1 | 0.75 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 0.25 | 5 | 8 | -37.5%
N/A | Minutes | - | 0.5 | - | - | - | - | - | - | 0.5 | - | N/A
1.2 | Performance and Document reviews (QA) | - | - | - | - | - | - | - | - | 0 | 8 | -100%
2 | Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1 | Functional Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1.1 | Functional Specification Generation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.2 | Generate User Stories | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.3 | Functional Specification Compilation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
2.2 | QA Manual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.2.1 | Generate QA Roles & Responsibilities | - | - | - | - | - | - | - | - | 0 | - | N/A
2.2.2 | Compile QA Manual | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
2.3 | Generate WBS, GANNT & PERT | - | - | - | - | - | - | - | - | 0 | - | N/A
2.4 | Generate PWS | - | - | - | - | - | - | - | - | 0 | - | N/A
2.5 | Negotiate Inter-group contracts | - | - | - | - | - | - | - | - | 0 | - | N/A
2.6 | Create tender presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.7 | Create Product demo presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.8 | Compile hand in document of all deliverables | - | - | - | - | - | - | - | - | 0 | - | N/A
2.9 | Give Presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
3 | Finance | 0 | 2.25 | 0 | 0 | 1 | 0 | 20.75 | 1 | 25 | 16 | 56.25%
3.1 | Generate Financial Business Plan | - | - | - | - | - | - | - | - | 0 | - | N/A
3.2 | Generate Financial Report 1 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.3 | Generate Financial Report 2 | - | 2.25 | - | - | 1 | - | 20.75 | 1 | 25 | 15 | 66.67%
3.4 | Generate Financial Report 3 | - | - | - | - | - | - | - | - | 0 | 1 | -100%
3.5 | Generate Financial Summary Report | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
4 | Research & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.1 | Research & Analyze Market | - | - | - | - | - | - | - | - | 0 | - | N/A
4.2 | Research advertizement Revenue | - | - | - | - | - | - | - | - | 0 | - | N/A
4.3 | Develop Sales Strategies | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4.1 | Generate App Mockups | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.2 | Design Logo | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.3 | Create Class Diagrams | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
5 | Development | 12.5 | 9.5 | 39.25 | 6.5 | 15 | 2.5 | 23.75 | 6.25 | 115.25 | 100.52 | 14.65%
5.1 | Source Media for App | - | - | - | - | - | - | - | - | 0 | 4.37 | -100%
5.2 | Generate Icons for App | - | - | - | - | - | - | - | 1 | 1 | 3.75 | -73.33%
5.3 | Software | 12.5 | 9.5 | 39.25 | 6.5 | 15 | 2.5 | 23.75 | 5.25 | 114.25 | 92.4 | 23.65%
5.3.1 | GUI Development | 12.5 | 5 | 0 | 6.5 | 15 | 0 | 12 | 0 | 51 | 38.7 | 31.78%
5.3.1.1 | Prototype GUI Development | 12.5 | 5 | - | 6.5 | 15 | 0 | 12 | - | 51 | 38.7 | 31.78%
5.3.1.2 | Final GUI Development | - | - | - | - | - | - | - | - | 0 |  | N/A
5.3.2 | App Development | 0 | 4.5 | 39.25 | 0 | 0 | 2.5 | 11.75 | 3.75 | 61.75 | 53.7 | 14.99%
5.3.2.1 | Prototype App Development | - | 4.5 | 39.25 | - | - | 2.5 | 11.75 | 3.75 | 61.75 | 53.7 | 14.99%
5.3.2.2 | Final App Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4 | Testing & Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | +
5.4.1 | GUI Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.2 | System Testing | - | - | - | - | - | - | - | 1.5 | 1.5 | 0 | +
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | - | - | - | 0 | - | N/A
[10 empty] | 0 |  | N/A
6 | Deliverables | 12.5 | 11.75 | 39.25 | 6.5 | 16 | 2.5 | 44.5 | 5.5 | 138.5 | 0 | +
6.1 | Functional Spec to supervisor | - | - | - | - | - | - | - | - | 0 | - | N/A
6.2 | QA Manual uploaded to repository | - | - | - | - | - | - | - | - | 0 | - | N/A
6.3 | Financial Business Plan submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.4 | PWS Agreed between groups | - | - | - | - | - | - | - | - | 0 | - | N/A
6.5 | Group tender presentations | - | - | - | - | - | - | - | - | 0 | - | N/A
6.6 | Financial Report 1 sumbission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.7 | All contracts agreed and filed | - | - | - | - | - | - | - | - | 0 | - | N/A
6.8 | Financial Report 2 submission | - | 2.25 | - | - | 1 | - | 20.75 | 1 | 25 | - | N/A
6.9 | First iteration complete | 12.5 | 9.5 | 39.25 | 6.5 | 15 | 2.5 | 23.75 | 3 | 112 | - | N/A
6.1 | Final test & integration plan | - | - | - | - | - | - | - | 1.5 | 1.5 | - | N/A
6.11 | Financial Report 3 submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.12 | Financial Summary Report submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.13 | Demonstration / Sales presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
6.14 | Hand in of all deliverables | - | - | - | - | - | - | - | - | 0 | - | N/A
Total For Team | [9 empty] | 145.75 | 132.52 | 9.98%
Total Per Employee |  | 13.5 | 13 | 39.75 | 7.5 | 16.5 | 3 | 45 | 7.5 | 145.75 |  | N/A
Forecast Per Employee |  | 18.2 | 7.1 | 27.2 | 8.48 | 18 | 20.3 | 24.6 | 8.6 | 132.48 |  | N/A
Percentage Difference |  | -25.82% | 83.1% | 46.14% | -11.56% | -8.333% | -85.22% | 82.93% | -12.79% | 10.02% |  | N/A

## Week 10 12-03
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8 | 16 | -50%
1.1 | Meetings | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 8 | 8 | 0%
N/A | Minutes | - | - | - | - | - | - | - | - | 0 | - | N/A
1.2 | Performance and Document reviews (QA) | - | - | - | - | - | - | - | - | 0 | 8 | -100%
2 | Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1 | Functional Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1.1 | Functional Specification Generation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.2 | Generate User Stories | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.3 | Functional Specification Compilation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
2.2 | QA Manual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.2.1 | Generate QA Roles & Responsibilities | - | - | - | - | - | - | - | - | 0 | - | N/A
2.2.2 | Compile QA Manual | - | - | - | - | - | - | - | - | 0 | - | N/A
2.3 | Generate WBS, GANNT & PERT | - | - | - | - | - | - | - | - | 0 | - | N/A
2.4 | Generate PWS | - | - | - | - | - | - | - | - | 0 | - | N/A
2.5 | Negotiate Inter-group contracts | - | - | - | - | - | - | - | - | 0 | - | N/A
2.6 | Create tender presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.7 | Create Product demo presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.8 | Compile hand in document of all deliverables | - | - | - | - | - | - | - | - | 0 | - | N/A
2.9 | Give Presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
3 | Finance | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0.75 | 5 | -85%
3.1 | Generate Financial Business Plan | - | - | - | - | - | - | - | - | 0 | - | N/A
3.2 | Generate Financial Report 1 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.3 | Generate Financial Report 2 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.4 | Generate Financial Report 3 | - | - | - | - | - | - | 0.75 | - | 0.75 | 5 | -85%
3.5 | Generate Financial Summary Report | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
4 | Research & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.1 | Research & Analyze Market | - | - | - | - | - | - | - |  | 0 | - | N/A
4.2 | Research advertizement Revenue | - | - | - | - | - | - | - | - | 0 | - | N/A
4.3 | Develop Sales Strategies | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4.1 | Generate App Mockups | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.2 | Design Logo | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.3 | Create Class Diagrams | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
5 | Development | 1 | 1.5 | 33 | 12 | 7.25 | 22.5 | 23.75 | 7.5 | 108.5 | 92.4 | 17.42%
5.1 | Source Media for App | - | - | - | - | - | - | - | - | 0 | 4.37 | -100%
5.2 | Generate Icons for App |  | - | - | - | - | - | - | - | 0 | 0.5 | -100%
5.3 | Software | 1 | 1.5 | 33 | 12 | 7.25 | 22.5 | 23.75 | 7.5 | 108.5 | 87.53 | 23.96%
5.3.1 | GUI Development | 1 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 6 | 34.73 | -82.72%
5.3.1.1 | Prototype GUI Development | 1 | - | - | 5 | - | - | - | - | 6 | 33.3 | -81.98%
5.3.1.2 | Final GUI Development | - | - | - | - | - | - | - | - | 0 | 1.43 | -100%
5.3.2 | App Development | 0 | 1.5 | 23 | 7 | 7.25 | 22.5 | 15.75 | 3 | 80 | 52.8 | 51.52%
5.3.2.1 | Prototype App Development | - | 1.5 | 23 | 7 | 7.25 | 22.5 | 15.75 | 3 | 80 | 42.9 | 86.48%
5.3.2.2 | Final App Development | - | - | - | - | - | - | - | - | 0 | 9.9 | -100%
5.4 | Testing & Analysis | 0 | 0 | 10 | 0 | 0 | 0 | 8 | 4.5 | 22.5 | 0 | +
5.4.1 | GUI Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.2 | System Testing | - | - | 10 | - | - | - | 8 | 4.5 | 22.5 | 0 | +
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | - | - | - | 0 | - | N/A
[10 empty] | 0 |  | N/A
6 | Deliverables | 1 | 1.5 | 33 | 12 | 7.25 | 22.5 | 24.5 | 7.5 | 109.25 | 0 | +
6.1 | Functional Spec to supervisor | - | - | - | - | - | - | - | - | 0 | - | N/A
6.2 | QA Manual uploaded to repository | - | - | - | - | - | - | - | - | 0 | - | N/A
6.3 | Financial Business Plan submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.4 | PWS Agreed between groups | - | - | - | - | - | - | - | - | 0 | - | N/A
6.5 | Group tender presentations | - | - | - | - | - | - | - | - | 0 | - | N/A
6.6 | Financial Report 1 sumbission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.7 | All contracts agreed and filed | - | - | - | - | - | - | - | - | 0 | - | N/A
6.8 | Financial Report 2 submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.9 | First iteration complete | 1 | 1.5 | 23 | 12 | 7.25 | 22.5 | 15.75 | 3 | 86 | - | N/A
6.1 | Final test & integration plan | - | - | 10 | - | - | - | 8 | 4.5 | 22.5 | - | N/A
6.11 | Financial Report 3 submission | - | - | - | - | - | - | 0.75 | - | 0.75 | - | N/A
6.12 | Financial Summary Report submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.13 | Demonstration / Sales presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
6.14 | Hand in of all deliverables | - | - | - | - | - | - | - | - | 0 | - | N/A
Total For Team | [9 empty] | 117.25 | 113.4 | 3.4%
Total Per Employee |  | 2 | 2.5 | 34 | 13 | 8.25 | 23.5 | 25.5 | 8.5 | 117.25 |  | N/A
Forecast Per Employee |  | 12 | 6.68 | 28.1 | 8.48 | 18 | 18.6 | 13.4 | 7.88 | 113.14 |  | N/A
Percentage Difference |  | -83.33% | -62.57% | 21% | 53.3% | -54.17% | 26.34% | 90.3% | 7.868% | 3.633% |  | N/A

## Week 11 19-03
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | +
1.1 | Meetings | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A | Minutes | - | - | - | - | - | - | - | - | 0 | - | N/A
1.2 | Performance and Document reviews (QA) | - | - | - | - | - | - | - | - | 0 | - | N/A
2 | Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1 | Functional Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1.1 | Functional Specification Generation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.2 | Generate User Stories | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.3 | Functional Specification Compilation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
2.2 | QA Manual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.2.1 | Generate QA Roles & Responsibilities | - | - | - | - | - | - | - | - | 0 | - | N/A
2.2.2 | Compile QA Manual | - | - | - | - | - | - | - | - | 0 | - | N/A
2.3 | Generate WBS, GANNT & PERT | - | - | - | - | - | - | - | - | 0 | - | N/A
2.4 | Generate PWS | - | - | - | - | - | - | - | - | 0 | - | N/A
2.5 | Negotiate Inter-group contracts | - | - | - | - | - | - | - | - | 0 | - | N/A
2.6 | Create tender presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.7 | Create Product demo presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.8 | Compile hand in document of all deliverables | - | - | - | - | - | - | - | - | 0 | - | N/A
2.9 | Give Presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
3 | Finance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | -100%
3.1 | Generate Financial Business Plan | - | - | - | - | - | - | - | - | 0 | - | N/A
3.2 | Generate Financial Report 1 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.3 | Generate Financial Report 2 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.4 | Generate Financial Report 3 | - | - | - | - | - | - | - | - | 0 | 5 | -100%
3.5 | Generate Financial Summary Report | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
4 | Research & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.1 | Research & Analyze Market | - | - | - | - | - | - | - |  | 0 | - | N/A
4.2 | Research advertizement Revenue | - | - | - | - | - | - | - | - | 0 | - | N/A
4.3 | Develop Sales Strategies | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4.1 | Generate App Mockups | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.2 | Design Logo | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.3 | Create Class Diagrams | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
5 | Development | 0 | 0 | 0 | 0 | 0 | 9.5 | 0 | 5 | 14.5 | 70.97 | -79.57%
5.1 | Source Media for App | - | - | - | - | - | - | - | - | 0 | 4.37 | -100%
5.2 | Generate Icons for App |  | - | - | - | - | - | - | - | 0 | - | N/A
5.3 | Software | 0 | 0 | 0 | 0 | 0 | 9.5 | 0 | 5 | 14.5 | 66.6 | -78.23%
5.3.1 | GUI Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.1 | -100%
5.3.1.1 | Prototype GUI Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.1.2 | Final GUI Development | - | - | - | - | - | - | - | - | 0 | 17.1 | -100%
5.3.2 | App Development | 0 | 0 | 0 | 0 | 0 | 9.5 | 0 | 5 | 14.5 | 49.5 | -70.71%
5.3.2.1 | Prototype App Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.2.2 | Final App Development | - | - | - | - | - | 9.5 | - | 5 | 14.5 | 49.5 | -70.71%
5.4 | Testing & Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5.4.1 | GUI Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.2 | System Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | - | - | - | 0 | - | N/A
[10 empty] | 0 |  | N/A
6 | Deliverables | 0 | 0 | 0 | 0 | 0 | 9.5 | 0 | 5 | 14.5 | 0 | +
6.1 | Functional Spec to supervisor | - | - | - | - | - | - | - | - | 0 | - | N/A
6.2 | QA Manual uploaded to repository | - | - | - | - | - | - | - | - | 0 | - | N/A
6.3 | Financial Business Plan submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.4 | PWS Agreed between groups | - | - | - | - | - | - | - | - | 0 | - | N/A
6.5 | Group tender presentations | - | - | - | - | - | - | - | - | 0 | - | N/A
6.6 | Financial Report 1 sumbission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.7 | All contracts agreed and filed | - | - | - | - | - | - | - | - | 0 | - | N/A
6.8 | Financial Report 2 submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.9 | First iteration complete | - | - | - | - | - | - | - | - | 0 | - | N/A
6.1 | Final test & integration plan | - | - | - | - | - | - | - | - | 0 | - | N/A
6.11 | Financial Report 3 submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.12 | Financial Summary Report submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.13 | Demonstration / Sales presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
6.14 | Hand in of all deliverables | - | - | - | - | - | 9.5 | - | 5 | 14.5 | - | N/A
Total For Team | [9 empty] | 14.5 | 75.97 | -80.91%
Total Per Employee |  | 0 | 0 | 0 | 0 | 0 | 9.5 | 0 | 5 | 14.5 |  | N/A
Forecast Per Employee |  | 8.82 | 3 | 30 | 2.97 | 6.98 | 10.2 | 11 | 3 | 75.97 |  | N/A
Percentage Difference |  | -100% | -100% | -100% | -100% | -100% | -6.863% | -100% | 66.67% | -80.91% |  | N/A

## Week 12 26-03
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | +
1.1 | Meetings | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A | Minutes | - | - | - | - | - | - | - | - | 0 | - | N/A
1.2 | Performance and Document reviews (QA) | - | - | - | - | - | - | - | - | 0 | - | N/A
2 | Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1 | Functional Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1.1 | Functional Specification Generation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.2 | Generate User Stories | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.3 | Functional Specification Compilation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
2.2 | QA Manual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.2.1 | Generate QA Roles & Responsibilities | - | - | - | - | - | - | - | - | 0 | - | N/A
2.2.2 | Compile QA Manual | - | - | - | - | - | - | - | - | 0 | - | N/A
2.3 | Generate WBS, GANNT & PERT | - | - | - | - | - | - | - | - | 0 | - | N/A
2.4 | Generate PWS | - | - | - | - | - | - | - | - | 0 | - | N/A
2.5 | Negotiate Inter-group contracts | - | - | - | - | - | - | - | - | 0 | - | N/A
2.6 | Create tender presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.7 | Create Product demo presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.8 | Compile hand in document of all deliverables | - | - | - | - | - | - | - | - | 0 | - | N/A
2.9 | Give Presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
3 | Finance | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0.5 | 5 | -90%
3.1 | Generate Financial Business Plan | - | - | - | - | - | - | - | - | 0 | - | N/A
3.2 | Generate Financial Report 1 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.3 | Generate Financial Report 2 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.4 | Generate Financial Report 3 | - | - | - | - | - | - | 0.5 | - | 0.5 | 5 | -90%
3.5 | Generate Financial Summary Report | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
4 | Research & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.1 | Research & Analyze Market | - | - | - | - | - | - | - |  | 0 | - | N/A
4.2 | Research advertizement Revenue | - | - | - | - | - | - | - | - | 0 | - | N/A
4.3 | Develop Sales Strategies | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4.1 | Generate App Mockups | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.2 | Design Logo | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.3 | Create Class Diagrams | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
5 | Development | 1 | 0 | 0 | 0 | 0 | 4.25 | 0.25 | 0 | 5.5 | 69.77 | -92.12%
5.1 | Source Media for App | - | - | - | - | - | - | - | - | 0 | 4.37 | -100%
5.2 | Generate Icons for App |  | - | - | - | - | - | - | - | 0 | - | N/A
5.3 | Software | 1 | 0 | 0 | 0 | 0 | 4.25 | 0.25 | 0 | 5.5 | 65.4 | -91.59%
5.3.1 | GUI Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.1 | -100%
5.3.1.1 | Prototype GUI Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.1.2 | Final GUI Development | - | - | - | - | - | - | - | - | 0 | 17.1 | -100%
5.3.2 | App Development | 1 | 0 | 0 | 0 | 0 | 4.25 | 0.25 | 0 | 5.5 | 48.3 | -88.61%
5.3.2.1 | Prototype App Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.2.2 | Final App Development | 1 | - | - | - | - | 4.25 | 0.25 | - | 5.5 | 48.3 | -88.61%
5.4 | Testing & Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5.4.1 | GUI Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.2 | System Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | - | - | - | 0 | - | N/A
[10 empty] | 0 |  | N/A
6 | Deliverables | 1 | 0 | 0 | 0 | 0 | 4.25 | 0.75 | 0 | 6 | 0 | +
6.1 | Functional Spec to supervisor | - | - | - | - | - | - | - | - | 0 | - | N/A
6.2 | QA Manual uploaded to repository | - | - | - | - | - | - | - | - | 0 | - | N/A
6.3 | Financial Business Plan submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.4 | PWS Agreed between groups | - | - | - | - | - | - | - | - | 0 | - | N/A
6.5 | Group tender presentations | - | - | - | - | - | - | - | - | 0 | - | N/A
6.6 | Financial Report 1 sumbission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.7 | All contracts agreed and filed | - | - | - | - | - | - | - | - | 0 | - | N/A
6.8 | Financial Report 2 submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.9 | First iteration complete | - | - | - | - | - | - | - | - | 0 | - | N/A
6.1 | Final test & integration plan | - | - | - | - | - | - | - | - | 0 | - | N/A
6.11 | Financial Report 3 submission | - | - | - | - | - | - | 0.5 | - | 0.5 | - | N/A
6.12 | Financial Summary Report submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.13 | Demonstration / Sales presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
6.14 | Hand in of all deliverables | 1 | - | - | - | - | 4.25 | 0.25 | - | 5.5 | - | N/A
Total For Team | [9 empty] | 6 | 74.77 | -91.98%
Total Per Employee |  | 1 | 0 | 0 | 0 | 0 | 4.25 | 0.75 | 0 | 6 |  | N/A
Forecast Per Employee |  | 8.82 | 3 | 30 | 2.97 | 6.98 | 10.2 | 9.8 | 3 | 74.77 |  | N/A
Percentage Difference |  | -88.66% | -100% | -100% | -100% | -100% | -58.33% | -92.35% | -100% | -91.98% |  | N/A

## Week 13 02-04
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | +
1.1 | Meetings | - | - | - | - | - | - | - | - | 0 | 0 | 0%
N/A | Minutes | - | - | - | - | - | - | - | - | 0 | - | N/A
1.2 | Performance and Document reviews (QA) | - | - | - | - | - | - | - | - | 0 | - | N/A
2 | Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1 | Functional Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1.1 | Functional Specification Generation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.2 | Generate User Stories | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.3 | Functional Specification Compilation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
2.2 | QA Manual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.2.1 | Generate QA Roles & Responsibilities | - | - | - | - | - | - | - | - | 0 | - | N/A
2.2.2 | Compile QA Manual | - | - | - | - | - | - | - | - | 0 | - | N/A
2.3 | Generate WBS, GANNT & PERT | - | - | - | - | - | - | - | - | 0 | - | N/A
2.4 | Generate PWS | - | - | - | - | - | - | - | - | 0 | - | N/A
2.5 | Negotiate Inter-group contracts | - | - | - | - | - | - | - | - | 0 | - | N/A
2.6 | Create tender presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.7 | Create Product demo presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.8 | Compile hand in document of all deliverables | - | - | - | - | - | - | - | - | 0 | - | N/A
2.9 | Give Presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
3 | Finance | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0.25 | 5 | -95%
3.1 | Generate Financial Business Plan | - | - | - | - | - | - | - | - | 0 | - | N/A
3.2 | Generate Financial Report 1 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.3 | Generate Financial Report 2 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.4 | Generate Financial Report 3 | - | - | - | - | - | - | 0.25 | - | 0.25 | 5 | -95%
3.5 | Generate Financial Summary Report | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
4 | Research & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.1 | Research & Analyze Market | - | - | - | - | - | - | - |  | 0 | - | N/A
4.2 | Research advertizement Revenue | - | - | - | - | - | - | - | - | 0 | - | N/A
4.3 | Develop Sales Strategies | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4.1 | Generate App Mockups | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.2 | Design Logo | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.3 | Create Class Diagrams | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
5 | Development | 0 | 5 | 3.75 | 2 | 0 | 24.25 | 2.5 | 0 | 37.5 | 60.6 | -38.12%
5.1 | Source Media for App | - | - | - | - | - | - | - | - | 0 | - | N/A
5.2 | Generate Icons for App |  | - | - | - | - | - | - | - | 0 | - | N/A
5.3 | Software | 0 | 5 | 3.75 | 2 | 0 | 24.25 | 2.5 | 0 | 37.5 | 60.6 | -38.12%
5.3.1 | GUI Development | 0 | 0 | 0 | 2 | 0 | 0 | 2.5 | 0 | 4.5 | 17.1 | -73.68%
5.3.1.1 | Prototype GUI Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.1.2 | Final GUI Development | - | - | - | 2 | - | - | 2.5 | - | 4.5 | 17.1 | -73.68%
5.3.2 | App Development | 0 | 5 | 3.75 | 0 | 0 | 24.25 | 0 | 0 | 33 | 43.5 | -24.14%
5.3.2.1 | Prototype App Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.2.2 | Final App Development | - | 5 | 3.75 | - | - | 24.25 | - | - | 33 | 43.5 | -24.14%
5.4 | Testing & Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5.4.1 | GUI Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.2 | System Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | - | - | - | 0 | - | N/A
[10 empty] | 0 |  | N/A
6 | Deliverables | 0 | 5 | 3.75 | 0 | 0 | 24.25 | 2.75 | 0 | 35.75 | 0 | +
6.1 | Functional Spec to supervisor | - | - | - | - | - | - | - | - | 0 | - | N/A
6.2 | QA Manual uploaded to repository | - | - | - | - | - | - | - | - | 0 | - | N/A
6.3 | Financial Business Plan submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.4 | PWS Agreed between groups | - | - | - | - | - | - | - | - | 0 | - | N/A
6.5 | Group tender presentations | - | - | - | - | - | - | - | - | 0 | - | N/A
6.6 | Financial Report 1 sumbission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.7 | All contracts agreed and filed | - | - | - | - | - | - | - | - | 0 | - | N/A
6.8 | Financial Report 2 submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.9 | First iteration complete | - | - | - | - | - | - | - | - | 0 | - | N/A
6.1 | Final test & integration plan | - | - | - | - | - | - | - | - | 0 | - | N/A
6.11 | Financial Report 3 submission | - | - | - | - | - | - | 0.25 | - | 0.25 | - | N/A
6.12 | Financial Summary Report submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.13 | Demonstration / Sales presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
6.14 | Hand in of all deliverables | - | 5 | 3.75 | - | - | 24.25 | 2.5 | - | 35.5 | - | N/A
Total For Team | [9 empty] | 37.75 | 65.6 | -42.45%
Total Per Employee |  | 0 | 5 | 3.75 | 2 | 0 | 24.25 | 2.75 | 0 | 37.75 |  | N/A
Forecast Per Employee |  | 8.82 | 3 | 30 | 2.97 | 6.98 | 10.2 | 5 | 3 | 69.97 |  | N/A
Percentage Difference |  | -100% | 66.67% | -87.5% | -32.66% | -100% | 137.7% | -45% | -100% | -46.05% |  | N/A

## Week 14 09-04
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | +
1.1 | Meetings | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A | Minutes | - | - | - | - | - | - | - | - | 0 | - | N/A
1.2 | Performance and Document reviews (QA) | - | 2 | - | - | - | - | - | - | 2 | - | N/A
2 | Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 1.5 | 0 | +
2.1 | Functional Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1.1 | Functional Specification Generation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.2 | Generate User Stories | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.3 | Functional Specification Compilation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
2.2 | QA Manual | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 1.5 | 0 | +
2.2.1 | Generate QA Roles & Responsibilities | - | - | - | - | - | - | - | - | 0 | - | N/A
2.2.2 | Compile QA Manual | - | - | - | - | - | - | 1.5 | - | 1.5 | - | N/A
2.3 | Generate WBS, GANNT & PERT | - | - | - | - | - | - | - | - | 0 | - | N/A
2.4 | Generate PWS | - | - | - | - | - | - | - | - | 0 | - | N/A
2.5 | Negotiate Inter-group contracts | - | - | - | - | - | - | - | - | 0 | - | N/A
2.6 | Create tender presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.7 | Create Product demo presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.8 | Compile hand in document of all deliverables | - | - | - | - | - | - | - | - | 0 | - | N/A
2.9 | Give Presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
3 | Finance | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 5 | -20%
3.1 | Generate Financial Business Plan | - | - | - | - | - | - | - | - | 0 | - | N/A
3.2 | Generate Financial Report 1 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.3 | Generate Financial Report 2 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.4 | Generate Financial Report 3 | - | - | - | - | - | - | 4 | - | 4 | 5 | -20%
3.5 | Generate Financial Summary Report | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
4 | Research & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.1 | Research & Analyze Market | - | - | - | - | - | - | - |  | 0 | - | N/A
4.2 | Research advertizement Revenue | - | - | - | - | - | - | - | - | 0 | - | N/A
4.3 | Develop Sales Strategies | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4.1 | Generate App Mockups | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.2 | Design Logo | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.3 | Create Class Diagrams | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
5 | Development | 0 | 5 | 19 | 0 | 0 | 6.25 | 0 | 0 | 30.25 | 33.18 | -8.83%
5.1 | Source Media for App | - | - | - | - | - | - | - | - | 0 | 0.58 | -100%
5.2 | Generate Icons for App |  | - | - | - | - | - | - | - | 0 | - | N/A
5.3 | Software | 0 | 5 | 19 | 0 | 0 | 6.25 | 0 | 0 | 30.25 | 32.6 | -7.21%
5.3.1 | GUI Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.1 | -100%
5.3.1.1 | Prototype GUI Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.1.2 | Final GUI Development | - | - | - | - | - | - | - | - | 0 | 17.1 | -100%
5.3.2 | App Development | 0 | 5 | 19 | 0 | 0 | 6.25 | 0 | 0 | 30.25 | 15.5 | 95.16%
5.3.2.1 | Prototype App Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.2.2 | Final App Development | - | 5 | 19 | - | - | 6.25 | - | 0 | 30.25 | 15.5 | 95.16%
5.4 | Testing & Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5.4.1 | GUI Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.2 | System Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | - | - | - | 0 | - | N/A
[10 empty] | 0 |  | N/A
6 | Deliverables | 0 | 5 | 19 | 0 | 0 | 6.25 | 5.5 | 0 | 35.75 | 0 | +
6.1 | Functional Spec to supervisor | - | - | - | - | - | - | - | - | 0 | - | N/A
6.2 | QA Manual uploaded to repository | - | - | - | - | - | - | 1.5 | - | 1.5 | - | N/A
6.3 | Financial Business Plan submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.4 | PWS Agreed between groups | - | - | - | - | - | - | - | - | 0 | - | N/A
6.5 | Group tender presentations | - | - | - | - | - | - | - | - | 0 | - | N/A
6.6 | Financial Report 1 sumbission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.7 | All contracts agreed and filed | - | - | - | - | - | - | - | - | 0 | - | N/A
6.8 | Financial Report 2 submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.9 | First iteration complete | - | - | - | - | - | - | - | - | 0 | - | N/A
6.1 | Final test & integration plan | - | - | - | - | - | - | - | - | 0 | - | N/A
6.11 | Financial Report 3 submission | - | - | - | - | - | - | 4 | - | 4 | - | N/A
6.12 | Financial Summary Report submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.13 | Demonstration / Sales presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
6.14 | Hand in of all deliverables | - | 5 | 19 | - | - | 6.25 | - | 0 | 30.25 | - | N/A
Total For Team | [9 empty] | 37.75 | 38.18 | -1.13%
Total Per Employee |  | 0 | 7 | 19 | 0 | 0 | 6.25 | 5.5 | 0 | 37.75 |  | N/A
Forecast Per Employee |  | 5.02 | 3 | 2 | 2.97 | 6.98 | 10.2 | 5 | 3 | 38.17 |  | N/A
Percentage Difference |  | -100% | 133.3% | 850% | -100% | -100% | -38.73% | 10% | -100% | -1.1% |  | N/A

## Week 15 16-04
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | 0 | 5 | 1 | 0 | 1 | 1 | 1 | 1 | 10 | 16 | -37.5%
1.1 | Meetings | - | 1 | 1 | - | 1 | 1 | 1 | 1 | 6 | 8 | -25%
N/A | Minutes | - | 1.5 | - | - | - | - | - | - | 1.5 | - | N/A
1.2 | Performance and Document reviews (QA) | - | 2.5 | - | - | - | - | - | - | 2.5 | 8 | -68.75%
2 | Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1 | Functional Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1.1 | Functional Specification Generation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.2 | Generate User Stories | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.3 | Functional Specification Compilation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
2.2 | QA Manual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.2.1 | Generate QA Roles & Responsibilities | - | - | - | - | - | - | - | - | 0 | - | N/A
2.2.2 | Compile QA Manual | - | - | - | - | - | - | - | - | 0 | - | N/A
2.3 | Generate WBS, GANNT & PERT | - | - | - | - | - | - | - | - | 0 | - | N/A
2.4 | Generate PWS | - | - | - | - | - | - | - | - | 0 | - | N/A
2.5 | Negotiate Inter-group contracts | - | - | - | - | - | - | - | - | 0 | - | N/A
2.6 | Create tender presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.7 | Create Product demo presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.8 | Compile hand in document of all deliverables | - | - | - | - | - | - | - | - | 0 | - | N/A
2.9 | Give Presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
3 | Finance | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 5 | -60%
3.1 | Generate Financial Business Plan | - | - | - | - | - | - | - | - | 0 | - | N/A
3.2 | Generate Financial Report 1 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.3 | Generate Financial Report 2 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.4 | Generate Financial Report 3 | - | - | - | - | - | - | 2 | - | 2 | 5 | -60%
3.5 | Generate Financial Summary Report | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
4 | Research & Design | 0 | 0 | 0 | 0 | 0 | 0 | 1.75 | 1 | 2.75 | 0 | +
4.1 | Research & Analyze Market | - | - | - | - | - | - | - |  | 0 | - | N/A
4.2 | Research advertizement Revenue | - | - | - | - | - | - | 1.75 | 1 | 2.75 | 0 | +
4.3 | Develop Sales Strategies | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4.1 | Generate App Mockups | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.2 | Design Logo | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.3 | Create Class Diagrams | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
5 | Development | 8.75 | 4.5 | 5 | 0 | 3.5 | 0 | 0 | 10 | 31.75 | 30.6 | 3.76%
5.1 | Source Media for App | - | - | - | - | - | - | - | - | 0 | - | N/A
5.2 | Generate Icons for App |  | - | - | - | - | - | - | - | 0 | - | N/A
5.3 | Software | 8.75 | 4.5 | 5 | 0 | 3.5 | 0 | 0 | 10 | 31.75 | 30.6 | 3.76%
5.3.1 | GUI Development | 0 | 0 | 0 | 0 | 3.5 | 0 | 0 | 0 | 3.5 | 17.1 | -79.53%
5.3.1.1 | Prototype GUI Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.1.2 | Final GUI Development | - | - | - | - | 3.5 | - | - | - | 3.5 | 17.1 | -79.53%
5.3.2 | App Development | 8.75 | 4.5 | 5 | 0 | 0 | 0 | 0 | 10 | 28.25 | 13.5 | 109.3%
5.3.2.1 | Prototype App Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.2.2 | Final App Development | 8.75 | 4.5 | 5 | - | 0 | - | - | 10 | 28.25 | 13.5 | 109.3%
5.4 | Testing & Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5.4.1 | GUI Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.2 | System Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | - | - | - | 0 | - | N/A
[10 empty] | 0 |  | N/A
6 | Deliverables | 8.75 | 4.5 | 5 | 0 | 3.5 | 0 | 3.75 | 1 | 26.5 | 0 | +
6.1 | Functional Spec to supervisor | - | - | - | - | - | - | - | - | 0 | - | N/A
6.2 | QA Manual uploaded to repository | - | - | - | - | - | - | - | - | 0 | - | N/A
6.3 | Financial Business Plan submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.4 | PWS Agreed between groups | - | - | - | - | - | - | - | - | 0 | - | N/A
6.5 | Group tender presentations | - | - | - | - | - | - | - | - | 0 | - | N/A
6.6 | Financial Report 1 sumbission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.7 | All contracts agreed and filed | - | - | - | - | - | - | - | - | 0 | - | N/A
6.8 | Financial Report 2 submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.9 | First iteration complete | - | - | - | - | - | - | - | - | 0 | - | N/A
6.1 | Final test & integration plan | - | - | - | - | - | - | - | - | 0 | - | N/A
6.11 | Financial Report 3 submission | - | - | - | - | - | - | 2 | - | 2 | - | N/A
6.12 | Financial Summary Report submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.13 | Demonstration / Sales presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
6.14 | Hand in of all deliverables | 8.75 | 4.5 | 5 | - | 3.5 | - | 1.75 | 1 | 24.5 | - | N/A
Total For Team | [9 empty] | 46.5 | 51.6 | -9.88%
Total Per Employee |  | 8.75 | 9.5 | 6 | 0 | 4.5 | 1 | 4.75 | 12 | 46.5 |  | N/A
Forecast Per Employee |  | 6.43 | 5 | 2 | 4.97 | 8.98 | 12.2 | 7 | 5 | 51.58 |  | N/A
Percentage Difference |  | 36.08% | 90% | 200% | -100% | -49.89% | -91.8% | -32.14% | 140% | -9.849% |  | N/A

## Week 16 23-04
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | 1.5 | 3 | 1.5 | 0 | 0 | 0 | 1.5 | 0 | 7.5 | 16 | -53.13%
1.1 | Meetings | 1.5 | 1.5 | 1.5 | - | - | - | 1.5 | - | 6 | 8 | -25%
N/A | Minutes | - | 1.5 | - | - | - | - | - | - | 1.5 | - | N/A
1.2 | Performance and Document reviews (QA) | - | - | - | - | - | - | - | - | 0 | 8 | -100%
2 | Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1 | Functional Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.1.1 | Functional Specification Generation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.2 | Generate User Stories | - | - | - | - | - | - | - | - | 0 | - | N/A
2.1.3 | Functional Specification Compilation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
2.2 | QA Manual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
2.2.1 | Generate QA Roles & Responsibilities | - | - | - | - | - | - | - | - | 0 | - | N/A
2.2.2 | Compile QA Manual | - | - | - | - | - | - | - | - | 0 | - | N/A
2.3 | Generate WBS, GANNT & PERT | - | - | - | - | - | - | - | - | 0 | - | N/A
2.4 | Generate PWS | - | - | - | - | - | - | - | - | 0 | - | N/A
2.5 | Negotiate Inter-group contracts | - | - | - | - | - | - | - | - | 0 | - | N/A
2.6 | Create tender presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.7 | Create Product demo presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
2.8 | Compile hand in document of all deliverables | - | - | - | - | - | - | - | - | 0 | - | N/A
2.9 | Give Presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
3 | Finance | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 0 | 4.5 | 5 | -10%
3.1 | Generate Financial Business Plan | - | - | - | - | - | - | - | - | 0 | - | N/A
3.2 | Generate Financial Report 1 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.3 | Generate Financial Report 2 | - | - | - | - | - | - | - | - | 0 | - | N/A
3.4 | Generate Financial Report 3 | - | - | - | - | - | - | 4.5 | - | 4.5 | 5 | -10%
3.5 | Generate Financial Summary Report | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
4 | Research & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.1 | Research & Analyze Market | - | - | - | - | - | - | - |  | 0 | - | N/A
4.2 | Research advertizement Revenue | - | - | - | - | - | - | - | - | 0 | - | N/A
4.3 | Develop Sales Strategies | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
4.4.1 | Generate App Mockups | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.2 | Design Logo | - | - | - | - | - | - | - | - | 0 | - | N/A
4.4.3 | Create Class Diagrams | - | - | - | - | - | - | - | - | 0 | - | N/A
N/A
5 | Development | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 8 | 13 | 30.6 | -57.52%
5.1 | Source Media for App | - | - | - | - | - | - | - | - | 0 |  | N/A
5.2 | Generate Icons for App |  | - | - | - | - | - | - | - | 0 | - | N/A
5.3 | Software | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 8 | 13 | 30.6 | -57.52%
5.3.1 | GUI Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.1 | -100%
5.3.1.1 | Prototype GUI Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.1.2 | Final GUI Development | - | - | - | - | - | - | - | - | 0 | 17.1 | -100%
5.3.2 | App Development | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 8 | 13 | 13.5 | -3.7%
5.3.2.1 | Prototype App Development | - | - | - | - | - | - | - | - | 0 | - | N/A
5.3.2.2 | Final App Development | - | 2 | 3 | - | - | - | - | 8 | 13 | 13.5 | -3.7%
5.4 | Testing & Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
5.4.1 | GUI Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.2 | System Testing | - | - | - | - | - | - | - | - | 0 | - | N/A
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | - | - | - | 0 | - | N/A
[10 empty] | 0 |  | N/A
6 | Deliverables | 0 | 2 | 3 | 0 | 0 | 0 | 4.5 | 0 | 9.5 | 0 | +
6.1 | Functional Spec to supervisor | - | - | - | - | - | - | - | - | 0 | - | N/A
6.2 | QA Manual uploaded to repository | - | - | - | - | - | - | - | - | 0 | - | N/A
6.3 | Financial Business Plan submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.4 | PWS Agreed between groups | - | - | - | - | - | - | - | - | 0 | - | N/A
6.5 | Group tender presentations | - | - | - | - | - | - | - | - | 0 | - | N/A
6.6 | Financial Report 1 sumbission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.7 | All contracts agreed and filed | - | - | - | - | - | - | - | - | 0 | - | N/A
6.8 | Financial Report 2 submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.9 | First iteration complete | - | - | - | - | - | - | - | - | 0 | - | N/A
6.1 | Final test & integration plan | - | - | - | - | - | - | - | - | 0 | - | N/A
6.11 | Financial Report 3 submission | - | - | - | - | - | - | 4.5 | - | 4.5 | - | N/A
6.12 | Financial Summary Report submission | - | - | - | - | - | - | - | - | 0 | - | N/A
6.13 | Demonstration / Sales presentation | - | - | - | - | - | - | - | - | 0 | - | N/A
6.14 | Hand in of all deliverables | - | 2 | 3 | - | - | - | - | - | 5 | - | N/A
Total For Team | [9 empty] | 25 | 51.6 | -51.55%
Total Per Employee |  | 1.5 | 5 | 4.5 | 0 | 0 | 0 | 6 | 8 | 25 |  | N/A
Forecast Per Employee |  | 6.43 | 5 | 2 | 4.97 | 8.98 | 12.2 | 7 | 5 | 51.58 |  | N/A
Percentage Difference |  | -76.67% | 0% | 125% | -100% | -100% | -100% | -14.29% | 60% | -51.53% |  | N/A

## WBS F Vs A Stacked Column Chart
ACTUAL (hrs) | [10 empty] | FORECAST (hrs)
WBS | Date | 2018-03-05 | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | TOTAL | Date | 2018-03-05 | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | TOTAL
1 | Meetings | 5.5 | 8 | 0 | 0 | 0 | 2 | 10 | 7.5 | 33 | Meetings | 16 | 16 | 0 | 0 | 0 | 0 | 16 | 16 | 64
1.1 | Meetings | 5 | 8 | 0 | 0 | 0 | 0 | 6 | 6 | 25 | Meetings | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 8 | 32
N/A | Minutes | 0.5 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 3.5 | Minutes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | Performance and Document reviews (QA) | 0 | 0 | 0 | 0 | 0 | 2 | 2.5 | 0 | 4.5 | Performance and Document reviews (QA) | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 8 | 32
2 | Documentation | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 1.5 | Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Functional Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Functional Specification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1 | Functional Specification Generation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Functional Specification Generation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.2 | Generate User Stories | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Generate User Stories | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.3 | Functional Specification Compilation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Functional Specification Compilation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 | QA Manual | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 1.5 | QA Manual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.1 | Generate QA Roles & Responsibilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Generate QA Roles & Responsibilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.2 | Compile QA Manual | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 1.5 | Compile QA Manual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3 | Generate WBS, GANNT & PERT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Generate WBS, GANNT & PERT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.4 | Generate PWS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Generate PWS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.5 | Negotiate Inter-group contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Negotiate Inter-group contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.6 | Create tender presentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Create tender presentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.7 | Create Product demo presentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Create Product demo presentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.8 | Compile hand in document of all deliverables | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Compile hand in document of all deliverables | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.9 | Give Presentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Give Presentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Finance | 25 | 0.75 | 0 | 0.5 | 0.25 | 4 | 2 | 4.5 | 37 | Finance | 16 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 51
3.1 | Generate Financial Business Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Generate Financial Business Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2 | Generate Financial Report 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Generate Financial Report 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3 | Generate Financial Report 2 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | Generate Financial Report 2 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
3.4 | Generate Financial Report 3 | 0 | 0.75 | 0 | 0.5 | 0.25 | 4 | 2 | 4.5 | 12 | Generate Financial Report 3 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 36
3.5 | Generate Financial Summary Report | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Generate Financial Summary Report | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Research & Design | 0 | 0 | 0 | 0 | 0 | 0 | 2.75 | 0 | 2.75 | Research & Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1 | Research & Analyze Market | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Research & Analyze Market | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2 | Research advertizement Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 2.75 | 0 | 2.75 | Research advertizement Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3 | Develop Sales Strategies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Develop Sales Strategies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4.1 | Generate App Mockups | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Generate App Mockups | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4.2 | Design Logo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Design Logo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4.3 | Create Class Diagrams | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Create Class Diagrams | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Development | 115.25 | 108.5 | 14.5 | 5.5 | 37.5 | 30.25 | 31.75 | 13 | 356.25 | Development | 100.52 | 92.4 | 70.97 | 69.77 | 60.6 | 33.18 | 30.6 | 30.6 | 488.64
5.1 | Source Media for App | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Source Media for App | 4.37 | 4.37 | 4.37 | 4.37 | - | 0.58 | - | 0 | 18.06
5.2 | Generate Icons for App | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Generate Icons for App | 3.75 | 0.5 | - | - | - | - | - | - | 4.25
5.3 | Software | 114.25 | 108.5 | 14.5 | 5.5 | 37.5 | 30.25 | 31.75 | 13 | 355.25 | Software | 92.4 | 87.53 | 66.6 | 65.4 | 60.6 | 32.6 | 30.6 | 30.6 | 466.33
5.3.1 | GUI Development | 51 | 6 | 0 | 0 | 4.5 | 0 | 3.5 | 0 | 65 | GUI Development | 38.7 | 34.73 | 17.1 | 17.1 | 17.1 | 17.1 | 17.1 | 17.1 | 176.03
5.3.1.1 | Prototype GUI Development | 51 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | Prototype GUI Development | 38.7 | 33.3 | 0 | 0 | 0 | 0 | 0 | 0 | 72
5.3.1.2 | Final GUI Development | 0 | 0 | 0 | 0 | 4.5 | 0 | 3.5 | 0 | 8 | Final GUI Development | 0 | 1.43 | 17.1 | 17.1 | 17.1 | 17.1 | 17.1 | 17.1 | 104.03
5.3.2 | App Development | 61.75 | 80 | 14.5 | 5.5 | 33 | 30.25 | 28.25 | 13 | 266.25 | App Development | 53.7 | 52.8 | 49.5 | 48.3 | 43.5 | 15.5 | 13.5 | 13.5 | 290.3
5.3.2.1 | Prototype App Development | 61.75 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 141.75 | Prototype App Development | 53.7 | 42.9 | 0 | 0 | 0 | 0 | 0 | 0 | 96.6
5.3.2.2 | Final App Development | 0 | 0 | 14.5 | 5.5 | 33 | 30.25 | 28.25 | 13 | 124.5 | Final App Development | 0 | 9.9 | 49.5 | 48.3 | 43.5 | 15.5 | 13.5 | 13.5 | 193.7
5.4 | Testing & Analysis | 1.5 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | Testing & Analysis | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.4.1 | GUI Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | GUI Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.4.2 | System Testing | 1.5 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | System Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.4.3 | Perform & gather consumer feedback | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Perform & gather consumer feedback | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Deliverables | 138.5 | 109.25 | 14.5 | 6 | 35.75 | 35.75 | 26.5 | 9.5 | 375.75 | Deliverables | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1 | Functional Spec to supervisor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Functional Spec to supervisor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.2 | QA Manual uploaded to repository | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 1.5 | QA Manual uploaded to repository | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.3 | Financial Business Plan submission | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Financial Business Plan submission | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.4 | PWS Agreed between groups | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PWS Agreed between groups | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.5 | Group tender presentations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Group tender presentations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.6 | Financial Report 1 sumbission | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Financial Report 1 sumbission | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.7 | All contracts agreed and filed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | All contracts agreed and filed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.8 | Financial Report 2 submission | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | Financial Report 2 submission | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.9 | First iteration complete | 112 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 198 | First iteration complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1 | Final test & integration plan | 1.5 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | Final test & integration plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.11 | Financial Report 3 submission | 0 | 0.75 | 0 | 0.5 | 0.25 | 4 | 2 | 4.5 | 12 | Financial Report 3 submission | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.12 | Financial Summary Report submission | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Financial Summary Report submission | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.13 | Demonstration / Sales presentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Demonstration / Sales presentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.14 | Hand in of all deliverables | 0 | 0 | 14.5 | 5.5 | 35.5 | 30.25 | 24.5 | 5 | 115.25 | Hand in of all deliverables | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## WBS F Vs A Cluster Column Chart
Week # | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Date | 2018-03-05 | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23
Forecast Work Hours | 132.52 | 113.4 | 75.97 | 74.77 | 65.6 | 38.18 | 51.6 | 51.6
Actual Hours Worked | 145.75 | 117.25 | 14.5 | 6 | 37.75 | 37.75 | 46.5 | 25
Difference (%) | 9.983% | 3.395% | -80.91% | -91.98% | -42.45% | -1.126% | -9.884% | -51.55%