## WK7 1902
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | [8 empty] | 10.5 | 16 | 34.38%
1.1 | Meetings | 1 | 1.5 |  |  | 1 | 0.75 | 0.75 | 2.25 | 7.25 | 8 | -
N/A | Minutes |  | 0.5 | - | - | - | - | - | - | 0.5 | - | -
1.2 | Performance and Document reviews (QA) | 0.5 | 1.5 | - | - | - | 0.75 | - | - | 2.75 | 8 | -
2 | Documentation | [8 empty] | 1.25 | 0 | N/A
2.1 | Functional Specification | [8 empty] | 0 | 0 | 0
2.1.1 | Functional Specification Generation | - | - | - | - | - | - | - | - | - | - | -
2.1.2 | Generate User Stories | - | - | - | - | - | - | - | - | - | - | -
2.1.3 | Functional Specification Compilation | - | - | - | - | - | - | - | - | - | - | -
2.2 | QA Manual | [8 empty] | 0 | 0 | 0
2.2.1 | Generate QA Roles & Responsibilities | - | - | - | - | - | - | - | - | - | - | -
2.2.2 | Compile QA Manual | - | - | - | - | - | - | - | - | - | - | -
2.3 | Generate WBS, GANNT & PERT | - | - |  |  |  |  | - | - | - | - | -
2.4 | Generate PWS | - | - |  |  |  |  | - | - | - | - | -
2.5 | Negotiate Inter-group contracts | - | - | 1.25 | - | - | - | - | - | 1.25 | - | -
2.6 | Create tender presentation | [8 empty] | - | - | -
2.7 | Create Product demo presentation | - | - | - | - | - | - | - | - | - | - | -
2.8 | Compile hand in document of all deliverables | - | - | - | - | - | - | - | - | - | - | -
2.9 | Give Presentation | - | - | - | - | - | - | - | - | - | - | -
3 | Finance | [8 empty] | 44.25 | 13.75 | -221.8%
3.1 | Generate Financial Business Plan | - | - | - | - | - | 3 | 13 | - | 16 | - | -
3.2 | Generate Financial Report 1 | 2 | 4.25 | 4 |  | 2 |  | 12.5 | 2.5 | 27.25 | 12.5 | -
3.3 | Generate Financial Report 2 | - | - | 1 | - | - | - | - | - | 1 | 1.25 | -
3.4 | Generate Financial Report 3 | - | - | - | - | - | - | - | - | - | - | -
3.5 | Generate Financial Summary Report | - | - | - | - | - | - | - | - | - | - | -
4 | Research & Design | [8 empty] | 0.75 | 0 | N/A
4.1 | Research & Analyze Market | - | - | - | - | - | - | - |  | - | - | -
4.2 | Research advertizement Revenue | - | - | - | - | - | - | - | - | - | - | -
4.3 | Develop Sales Strategies | - | - | - | - | - | - | - | 0.75 | 0.75 | - | -
4.4 | Design | [8 empty] | 0 | 0 | 0
4.4.1 | Generate App Mockups | - | - | - |  | - | - | - | - | - | - | -
4.4.2 | Design Logo | - | - | - | - | - | - | - | - | - | - | -
4.4.3 | Create Class Diagrams | - | - | - | - | - | - | - | - | - | - | -
5 | Development | [8 empty] | 55 | 100.59 | 45.32%
5.1 | Source Media for App | - | - | - | - | - | - | - | - | - | 4.37 | -
5.2 | Generate Icons for App |  | - | - | - | - | - | - | - | - | 3.75 | -
5.3 | Software | [8 empty] | 55 | 92.47 | 0
5.3.1 | GUI Development | [8 empty] | 5 | 38.77 | 0
5.3.1.1 | Prototype GUI Development | - | - | - | - | 5 | - | - | - | 5 | 38.77 | -
5.3.1.2 | Final GUI Development | - | - | - | - | - | - | - | - | - | - | -
5.3.2 | App Development | [8 empty] | 50 | 53.7 | 0
5.3.2.1 | Prototype App Development | 3 | 4.75 | 27 | 2 |  | 7.75 |  | 5.5 | 50 | 53.7 | -
5.3.2.2 | Final App Development | - | - | - | - | - | - | - | - | - | - | -
5.4 | Testing & Analysis | [8 empty] | 0 | 0 | 0
5.4.1 | GUI Testing | - | - | - | - | - | - | - | - | - | - | -
5.4.2 | System Testing | - | - | - | - | - | - | - | - | - | - | -
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | - | - | - | - | - | -
6 | Deliverables | [8 empty] | 12 | 0 | N/A
6.1 | Functional Spec to supervisor | - | - | - | - | - | - | - | - | - | - | -
6.2 | QA Manual uploaded to repository | - | - | - | - | - | - | - | - | - | - | -
6.3 | Financial Business Plan submission | - | - | - | - | - | - | - | - | - | - | -
6.4 | PWS Agreed between groups | - | - | - | - | - | - | - | - | - | - | -
6.5 | Group tender presentations | 2.25 | 1.5 | 1.75 | 2.25 | - | 1.5 | 2.25 | 0.5 | 12 | - | -
6.6 | Financial Report 1 sumbission | - | - | - | - | - | - | - | - | - | - | -
6.7 | All contracts agreed and filed | - | - | - | - | - | - | - | - | - | - | -
6.8 | Financial Report 2 submission | - | - | - | - | - | - | - | - | - | - | -
6.9 | First iteration complete | - | - | - | - | - | - | - | - | - | - | -
6.1 | Final test & integration plan | - | - | - | - | - | - | - | - | - | - | -
6.11 | Financial Report 3 submission | - | - | - | - | - | - | - | - | - | - | -
6.12 | Financial Summary Report submission | - | - | - | - | - | - | - | - | - | - | -
6.13 | Demonstration / Sales presentation | - | - | - | - | - | - | - | - | - | - | -
6.14 | Hand in of all deliverables | - | - | - | - | - | - | - | - | - | - | -
Total For Team | [9 empty] | 111.75
Total Per Employee |  | 6.5 | 12.5 | 33.25 | 2 | 8 | 12.25 | 26.25 | 11 | 111.75
Forecast Per Employee |  | 18.2 | 7.1 | 27.2 | 8.48 | 18 | 20.3 | 22.3 | 8.6 | 130.18
Percentage Difference |  | -64.29% | 76.06% | 22.24% | -76.42% | -55.56% | -39.66% | 17.71% | 27.91% | -14.16%

## WK8 2602
WBS | Task Name | Alex B | Alex F | Jack | Jeremy | Kevin | Marco | Miranda | St.John | Total Hours Per Task For Entire Group | Forecast | Percentage Difference
1 | Meetings | [8 empty] | 7.75 | 16 | 51.56%
1.1 | Meetings | 1 | 0.25 |  | 1.25 | 1 | 1 | 1.5 | 1.25 | 7.25 | 8 | -
N/A | Minutes | - | - | - | - | - | - | - | - | - | - | -
1.2 | Performance and Document reviews (QA) | - | 0.5 | - | - | - |  | - | - | 0.5 | 8 | -
2 | Documentation | [8 empty] | 10.75 | 0 | N/A
2.1 | Functional Specification | [8 empty] | 0 | 0 | 0
2.1.1 | Functional Specification Generation | - | - | - | - | - | - | - | - | - | - | -
2.1.2 | Generate User Stories | - | - | - | - | - | - | - | - | - | - | -
2.1.3 | Functional Specification Compilation | - | - | - | - | - | - | - | - | - | - | -
2.2 | QA Manual | [8 empty] | 5.5 | 0 | 0
2.2.1 | Generate QA Roles & Responsibilities | - | - | - | - | - | - | - | 0.25 | 0.25 | - | -
2.2.2 | Compile QA Manual | - | - | - | - | - | - | - | - | 0 | - | -
[10 empty] | 0 | - | -
2.3 | Generate WBS, GANNT & PERT | - | - | - | - | - | - | - | - | 0 | - | -
2.4 | Generate PWS | - | - | - | - | - | - | - | - | 0 | - | -
2.5 | Negotiate Inter-group contracts | - | 1.25 | 2.5 | - | - | 1.5 | - | - | 5.25 | - | -
2.6 | Create tender presentation | - | [7 empty] | 0 | - | -
2.7 | Create Product demo presentation | - | - | - | - | - | - | - | - | 0 | - | -
2.8 | Compile hand in document of all deliverables | - | - | - | - | - | - | - | - | 0 | - | -
2.9 | Give Presentation | - | - | - | - | - | - | - | - | 0 | - | -
3 | Finance | [8 empty] | 0.5 | 18.75 | 97.33%
3.1 | Generate Financial Business Plan | - | - | - | - | - | - |  | - | - | - | -
3.2 | Generate Financial Report 1 | [7 empty] | - | - | - | -
3.3 | Generate Financial Report 2 | 0.25 | - | - | - | - | - | 0.25 | - | 0.5 | 18.75 | -
3.4 | Generate Financial Report 3 | - | - | - | - | - | - | - | - | - | - | -
3.5 | Generate Financial Summary Report | - | - | - | - | - | - | - | - | - | - | -
4 | Research & Design | [8 empty] | 3 | 0 | N/A
4.1 | Research & Analyze Market | - | - | - | - | - | - | - |  | - | - | -
4.2 | Research advertizement Revenue | - | - | - | - | - | - | - | - | - | - | -
4.3 | Develop Sales Strategies | - | - | - | - | - | - | - | 3 | 3 | - | -
4.4 | Design | [8 empty] | 0 | 0 | 0
4.4.1 | Generate App Mockups | - | - | - |  | - | - | - | - | - | - | -
4.4.2 | Design Logo | - | - | - | - | - | - | - | - | - | - | -
4.4.3 | Create Class Diagrams | - | - | - | - | - | - | - | - | - | - | -
5 | Development | [8 empty] | 71.75 | 100.59 | 28.67%
5.1 | Source Media for App | - | - | - | - | - | - | - | - | - | 4.37 | -
5.2 | Generate Icons for App |  | - | - | - | - | - | - | - | - | 3.75 | -
5.3 | Software | [8 empty] | 71.75 | 92.47 | 0
5.3.1 | GUI Development | [8 empty] | 3 | 38.77 | 0
5.3.1.1 | Prototype GUI Development | - | - | - | - | 3 | - | - | - | 3 | 38.77 | -
5.3.1.2 | Final GUI Development | - | - | - | - | - | - | - | - | - | - | -
5.3.2 | App Development | [8 empty] | 68.75 | 53.7 | 0
5.3.2.1 | Prototype App Development | 3 | 4.5 | 24.25 | 7.75 |  |  | 21.25 | 8 | 68.75 | 53.7 | -
5.3.2.2 | Final App Development | - | - | - | - | - | - | - | - | - | - | -
5.4 | Testing & Analysis | [8 empty] | 0 | 0 | 0
5.4.1 | GUI Testing | - | - | - | - | - | - | - | - | - | - | -
5.4.2 | System Testing | - | - | - | - | - | - | - | - | - | - | -
5.4.3 | Perform & gather consumer feedback | - | - | - | - | - | - | - | - | - | - | -
6 | Deliverables | [8 empty] | 0 | 0 | N/A
6.1 | Functional Spec to supervisor | - | - | - | - | - | - | - | - | - | - | -
6.2 | QA Manual uploaded to repository | - | - | - | - | - | - | - | - | - | - | -
6.3 | Financial Business Plan submission | - | - | - | - | - | - | - | - | - | - | -
6.4 | PWS Agreed between groups | - | - | - | - | - | - | - | - | - | - | -
6.5 | Group tender presentations |  | - | - | - | - | - | - | - | 0 | - | -
6.6 | Financial Report 1 sumbission | - | - | - | - | - | - | - | - | - | - | -
6.7 | All contracts agreed and filed | - | - | - | - | - | - | - | - | - | - | -
6.8 | Financial Report 2 submission | - | - | - | - | - | - | - | - | - | - | -
6.9 | First iteration complete | - | - | - | - | - | - |  | - | - | - | -
6.1 | Final test & integration plan | - | - | - | - | - | - | - | - | - | - | -
6.11 | Financial Report 3 submission | - | - | - | - | - | - | - | - | - | - | -
6.12 | Financial Summary Report submission | - | - | - | - | - | - | - | - | - | - | -
6.13 | Demonstration / Sales presentation | - | - | - | - | - | - | - | - | - | - | -
6.14 | Hand in of all deliverables | - | - | - | - | - | - | - | - | - | - | -
Total For Team | [9 empty] | 93.75
Total Per Employee |  | 4.25 | 6.5 | 26.75 | 9 | 4 | 2.5 | 23 | 12.5 | 88.5
Forecast Per Employee |  | 18.2 | 7.1 | 27.2 | 8.48 | 18 | 20.3 | 27.3 | 8.6 | 135.18
Percentage Difference |  | -76.65% | -8.451% | -1.654% | 6.132% | -77.78% | -87.68% | -15.75% | 45.35% | -34.53%

## WBS F Vs A Stacked Column Chart
|  | ACTUAL (hrs) |  |  | FORECAST (hrs)
WBS | Date | 2018-02-19 | 2018-02-26 | Task Name | 19/02/2018 | 26/02/2018
1 | Meetings | 10.5 | 7.75 | Meetings | 16 | 16
1.1 | Meetings | 7.25 | 7.25 | Meetings | 8 | 8
N/A | Minutes | 0.5 | - | Minutes | - | -
1.2 | Performance and Document reviews (QA) | 2.75 | 0.5 | Performance and Document reviews (QA) | 8 | 8
2 | Documentation | 1.25 | 10.75 | Documentation | 0 | 0
2.1 | Functional Specification | 0 | 0 | Functional Specification | 0 | 0
2.1.1 | Functional Specification Generation | - | - | Functional Specification Generation | - | -
2.1.2 | Generate User Stories | - | - | Generate User Stories | - | -
2.1.3 | Functional Specification Compilation | - | - | Functional Specification Compilation | - | -
|  | 0 | 0 |  | 0 | 0
2.2 | QA Manual | 0 | 5.5 | QA Manual | 0 | 0
2.2.1 | Generate QA Roles & Responsibilities | - | 0.25 | Generate QA Roles & Responsibilities | - | -
2.2.2 | Compile QA Manual | - | 0 | Compile QA Manual | - | -
|  | 0 | 0 |  | 0 | -
2.3 | Generate WBS, GANNT & PERT | - | 0 | Generate WBS, GANNT & PERT | - | -
2.4 | Generate PWS | - | 0 | Generate PWS | - | -
2.5 | Negotiate Inter-group contracts | 1.25 | 5.25 | Negotiate Inter-group contracts | - | -
2.6 | Create tender presentation | - | 0 | Create tender presentation | - | -
2.7 | Create Product demo presentation | - | 0 | Create Product demo presentation | - | -
2.8 | Compile hand in document of all deliverables | - | 0 | Compile hand in document of all deliverables | - | -
2.9 | Give Presentation | - | 0 | Give Presentation | - | -
|  | 0 | 0 |  | 0 | 0
3 | Finance | 44.25 | 0.5 | Finance | 13.75 | 18.75
3.1 | Generate Financial Business Plan | 16 | - | Generate Financial Business Plan | - | -
3.2 | Generate Financial Report 1 | 27.25 | - | Generate Financial Report 1 | 12.5 | -
3.3 | Generate Financial Report 2 | 1 | 0.5 | Generate Financial Report 2 | 1.25 | 18.75
3.4 | Generate Financial Report 3 | - | - | Generate Financial Report 3 | - | -
3.5 | Generate Financial Summary Report | - | - | Generate Financial Summary Report | - | -
|  | 0 | 0 |  | 0 | 0
4 | Research & Design | 0.75 | 3 | Research & Design | 0 | 0
4.1 | Research & Analyze Market | - | - | Research & Analyze Market | - | -
4.2 | Research advertizement Revenue | - | - | Research advertizement Revenue | - | -
4.3 | Develop Sales Strategies | 0.75 | 3 | Develop Sales Strategies | - | -
4.4 | Design | 0 | 0 | Design | 0 | 0
4.4.1 | Generate App Mockups | - | - | Generate App Mockups | - | -
4.4.2 | Design Logo | - | - | Design Logo | - | -
4.4.3 | Create Class Diagrams | - | - | Create Class Diagrams | - | -
|  | 0 | 0 |  | 0 | 0
5 | Development | 55 | 71.75 | Development | 100.59 | 100.59
5.1 | Source Media for App | - | - | Source Media for App | 4.37 | 4.37
5.2 | Generate Icons for App | - | - | Generate Icons for App | 3.75 | 3.75
5.3 | Software | 55 | 71.75 | Software | 92.47 | 92.47
5.3.1 | GUI Development | 5 | 3 | GUI Development | 38.77 | 38.77
5.3.1.1 | Prototype GUI Development | 5 | 3 | Prototype GUI Development | 38.77 | 38.77
5.3.1.2 | Final GUI Development | - | - | Final GUI Development | - | -
5.3.2 | App Development | 50 | 68.75 | App Development | 53.7 | 53.7
5.3.2.1 | Prototype App Development | 50 | 68.75 | Prototype App Development | 53.7 | 53.7
5.3.2.2 | Final App Development | - | - | Final App Development | - | -
5.4 | Testing & Analysis | 0 | 0 | Testing & Analysis | 0 | 0
5.4.1 | GUI Testing | - | - | GUI Testing | - | -
5.4.2 | System Testing | - | - | System Testing | - | -
5.4.3 | Perform & gather consumer feedback | - | - | Perform & gather consumer feedback | - | -
|  | 0 | 0 |  | 0 | 0
6 | Deliverables | 12 | 0 | Deliverables | 0 | 0
6.1 | Functional Spec to supervisor | - | - | Functional Spec to supervisor | - | -
6.2 | QA Manual uploaded to repository | - | - | QA Manual uploaded to repository | - | -
6.3 | Financial Business Plan submission | - | - | Financial Business Plan submission | - | -
6.4 | PWS Agreed between groups | - | - | PWS Agreed between groups | - | -
6.5 | Group tender presentations | 12 | 0 | Group tender presentations | - | -
6.6 | Financial Report 1 sumbission | - | - | Financial Report 1 sumbission | - | -
6.7 | All contracts agreed and filed | - | - | All contracts agreed and filed | - | -
6.8 | Financial Report 2 submission | - | - | Financial Report 2 submission | - | -
6.9 | First iteration complete | - | - | First iteration complete | - | -
6.1 | Final test & integration plan | - | - | Final test & integration plan | - | -
6.11 | Financial Report 3 submission | - | - | Financial Report 3 submission | - | -
6.12 | Financial Summary Report submission | - | - | Financial Summary Report submission | - | -
6.13 | Demonstration / Sales presentation | - | - | Demonstration / Sales presentation | - | -
6.14 | Hand in of all deliverables | - | - | Hand in of all deliverables | - | -

## WBS F Vs A Cluster Column Chart
Week No. | 2 | 3
Commencing Date of Week | 2018-02-19 | 2018-02-26
Actual | 111.75 | 85.5
Forecast | 130.18 | 135.18
Difference (%) | -14.16% | -34.53%