## Monday to Wednesday Page One
Time Sheet For Jack Rookes of SG3 Enterprise For Week Starting |  | 2018-02-12
Day | Description of Work Done | Start Time | End Time
Section/Task
Monday | Date: 12/02/2018
1.1 | Team meeting | 15:00 | 18:00
5.3 | Software Manager: Fixed a GitHub repository error where the commits contained build files. This was fixed by including the correct .gitignore on the master branch | 18:30 | 19:30
Tuesday | Date: 13/02/2018
6.4 | Software Manager: Attended the project wide standard meeting | 11:00 | 12:00
5.3.2 | Software Engineer: Wrote more client to server code that handles and parses a provided XML file from the HTTP server. | 15:00 | 17:15
Wednesday | Date: 14/02/2018
5.3.2 | Software Engineer: More XML client to server code written. | 11:00 | 12:00
6.4 | Software Manager: Committed a corrected version of the PWS schema to GitHub | 20:00 | 22:00

## Monday to Wednesday Page Two
Time Sheet For Jack Rookes of SG3 Enterprise For Week Starting |  | 2018-02-12
Day | Time spent per Milestone/Deliverable | Total Time in Hours (Rounded to the nearest 15 minutes) | Total Wages (To be calculated by the Finance Manager)
Section/Task
Monday | Date: 12/02/2018
1.1 | 3 - First iteration | 3 | 37.5
5.3 | 1 - First iteration | 1 | 12.5
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Total |  | 4 | 50
Tuesday | Date: 13/02/2018
6.4 | 1 - PWS | 1 | 12.5
5.3.2 | 2.25 - First iteration | 2.25 | 28.125
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Total |  | 3.25 | 40.625
Wednesday | Date: 14/02/2018
5.3.2 | 1 - First iteration | 1 | 12.5
6.4 | 2 - PWS | 2 | 25
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Total |  | 3 | 37.5

## Thursday to Sunday Page One
Time Sheet For Jack Rookes of SG3 Enterprise For Week Starting |  | 2018-02-12
Day | Description of Work Done | Start Time | End Time
Section/Task
Thursday | Date: 15/02/2018
1.1/5.3.2 | Software Manager/Engineer: Group meeting. Worked on XML parser code. | 15:00 | 17:00
Friday | Date: 16/02/2018
1.1/5.3.2 | Software Manager/Engineer: Programming session with group. Worked on more XML parser code, and helped group members with the IDE installation and using Git | 09:00/15:00 | 12:00/17:30
Saturday | Date: 17/02/2018
Sunday | Date: 18/02/2018

## Thursday to Sunday Page Two
Time Sheet For Jack Rookes of SG3 Enterprise For Week Starting |  | 2018-02-12
Day | Time spent per Milestone/Deliverable | Total Time in Hours (Rounded to the nearest 15 minutes) | Total Wages (To be calculated by the Finance Manager)
Section/Task
Thursday | Date: 15/02/2018
1.1/5.3.2 | 2 - First iteration | 2 | 25
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Total |  | 2 | 25
Friday | Date: 16/02/2018
1.1/5.3.2 | 5.5 - First iteration | 5.5 | 68.75
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Total |  | 5.5 | 68.75
Saturday | Date: 17/02/2018
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Total |  | 0 | 0
Sunday | Date: 18/02/2018
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Total |  | 0 | 0
|  | Week Total Hours | 17.75
|  | Week Total Wages | 221.875