## Monday to Wednesday Page One
Time Sheet For STJOHN of SG3 Enterprise For Week Starting |  | 2018-04-16
Day | Description of Work Done | Start Time | End Time
Section/Task
Monday | Date: 16/04/2018
Role: Marketing and Research manager
Group Meeting | Group meeting with customer | 15:00 | 16:00
Tuesday | Date: 17/04/2018
Wednesday | Date: 18/04/2018

## Monday to Wednesday Page Two
Time Sheet For STJOHN of SG3 Enterprise For Week Starting |  | 2018-04-19
Day | Time spent per Milestone/Deliverable | Total Time in Hours (Rounded to the nearest 15 minutes) | Total Wages (To be calculated by the Finance Manager)
Section/Task
Monday | Date: 19/04/2018
Group Meeting | 1 - Discussion on progress and chat with customer | 1 | 12.5
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Total |  | 1 | 12.5
Tuesday | Date: 20/04/2018
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Total |  | 0 | 0
Wednesday | Date: 21/04/2018
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Total |  | 0 | 0

## Thursday to Sunday Page One
Time Sheet For STJOHN of SG3 Enterprise For Week Starting |  | 2018-04-16
Day | Description of Work Done | Start Time | End Time
Section/Task
Thursday | Date: 19/04/2018
5.3.2.2 | Tidying up multiple select and add to shopping list. Trying to make sense of the favourites handler class | 16:30 | 18:00
Friday | Date: 20/04/2018
5.3.2.2 | Attempted to make some progress with adding the filters into the search. Realised laptop not capable of running emulator started writing an algorithm for search | 13:00 | 15:30
4.3 | Meeting with miranda to discuss business model | 15:30 | 16:30
5.3.2.2 | Developed search algorithm, found out it had already been done discussed with jack and marco where to go from here in terms of emulation | 16:30 | 17:00
Saturday | Date: 21/04/2018
Sunday | Date: 22/04/2018
5.3.2.2 | Read and practised HTML resulting in creation of HTML tour webpage with link to the virtual tour document already created. Edited and added some parts to this | 13:00 | 16:00
5.3.2.2 | Downloading and installing everything required to carry on with the project on different laptop. Tried to make sense of code and thought about how to edit classes to include filter | 16:00 | 18:30

## Thursday to Sunday Page Two
Time Sheet For STJOHN of SG3 Enterprise For Week Starting |  | 2018-04-19
Day | Time spent per Milestone/Deliverable | Total Time in Hours (Rounded to the nearest 15 minutes) | Total Wages (To be calculated by the Finance Manager)
Section/Task
Thursday | Date: 22/04/2018
5.3.2.2 | 1.5 - Programming for second iteration | 1.5 | 18.75
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Total |  | 1.5 | 18.75
Friday | Date: 23/04/2018
5.3.2.2 | 2.5 - programming for second iteration | 2.5 | 31.25
4.3 | 1 - Marketing and finance catch up, business model discussion | 1 | 12.5
5.3.2.2 | 0.5 - programming for second iteration | 0.5 | 6.25
|  | 0 | 0
|  | 0 | 0
Total |  | 4 | 50
Saturday | Date: 24/04/2018
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Total |  | 0 | 0
Sunday | Date: 25/04/2018
5.3.2.2 | 3 - VIrtual Tour development | 3 | 37.5
5.3.2.2 | 2.5 - Programming fdor second iteration | 2.5 | 31.25
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Total |  | 5.5 | 68.75
|  | Week Total Hours | 12
|  | Week Total Wages | 150